## Notes
Instructions to use MDL:
R1 | This submittal log shall only be maintained by Document Control.
R2 | Links between MDL and submittal log are fixed. Changing file location will need updates to formulas.
R3
R4
R5
R6
R7
R8
R9
R10
R11
Notes from S.O.:
1
2

## SubmittalLog
SNo. | Prolog No. | Prolog Rev | Prolog Subject | Document No. | Revision | Submitted By | Submission Date | Review Period | Target Return Date | Actual Return Date | Review Turnaround Days | Review Delay Days | Submission Status | Approval Status | Resubmission Required | Notes
ICA
1 | 0028 |  | Vendor Information For Pressure Gauge (BAUMER SINGAPORE PTE LTD) | 131236-WSW46-VI-I-0001 | 0 | Ricky | 2026-04-13 | 20 | 2026-05-03 | 2026-05-15 | 32 | 12 | NTS | APP | NO
2 | 0031 |  | Vendor Information For Cable Raceway (TRI-STAR INDUSTRIES PTE LTD) | 131236-WSW46-VI-I-0002 | 0 | Ricky | 2026-04-15 | 20 | 2026-05-05 | 2026-05-25 | 40 | 20 | RTR | AWC | YES
3 | 0037 |  | Vendor Information For Temperature Transmitter c/w RTD (ENDRESS + HAUSER S.E.A. PTE LTD) | 131236-WSW46-VI-I-0003 | 0 | Ricky | 2026-04-28 | 20 | 2026-05-18 | 2026-05-15 | 17 | -3 | NTS | APP | NO
4 | 0038 |  | Vendor Information For Pressure Transmitter (EMERSON ASIA PACIFIC PTE. LTD.) | 131236-WSW46-VI-I-0004 | 0 | Ricky | 2026-04-29 | 20 | 2026-05-19 | 2026-05-15 | 16 | -4 | RTR | APP | YES
5 | 0040 |  | Vendor Information For Level Transmitter Radar (Non-Contacting) (ENDRESS + HAUSER S.E.A. PTE LTD) | 131236-WSW46-VI-I-0005 | 0 | Ricky | 2026-04-30 | 20 | 2026-05-20 | 2026-05-15 | 15 | -5 | RTR | AWC | YES
6 | 0041 |  | Vendor Information For Pressure Switch(WIKA INSTRUMENTATION PTE. LTD.) | 131236-WSW46-VI-I-0006 | 0 | Ricky | 2026-04-30 | 20 | 2026-05-20 | 2026-05-25 | 25 | 5 | RTR | APP | YES
7 | 0046 |  | Vendor Information For Level Transmitter – RF Admittance(ENDRESS + HAUSER S.E.A. PTE LTD) | 131236-WSW46-VI-I-0007 | 0 | Ricky | 2026-05-08 | 20 | 2026-05-28 | 2026-05-15 | 7 | -13 | RTR | AWC | YES
8 | 0048 |  | Vendor Information For Auto Sampler (ENDRESS + HAUSER S.E.A. PTE LTD) | 131236-WSW46-VI-I-0008 | 0 | Ricky | 2026-05-11 | 20 | 2026-05-31 | 2026-05-25 | 14 | -6 | RTR | AWC | YES
9 | 0050 |  | Vendor Information For Low Point Leak Detector (IFM ELECTRONIC PTE LTD) | 131236-WSW46-VI-I-0009 | 0 | Ricky | 2026-05-12 | 20 | 2026-06-01 | 2026-05-25 | 13 | -7 | RTR | APP | YES
10 | 0051 |  | Vendor Information For Thermal Mass Flowmeter (ENDRESS + HAUSER S.E.A. PTE LTD) | 131236-WSW46-VI-I-0010 | 0 | Ricky | 2026-05-13 | 20 | 2026-06-02 | 2026-05-31 | 18 | -2 | RTR | AWC | YES
11 | 0055 |  | Vendor Information For Thermal Flow Switch (ENDRESS + HAUSER S.E.A. PTE LTD) | 131236-WSW46-VI-I-0011 | 0 | Ricky | 2026-05-14 | 20 | 2026-06-03 | 2026-05-31 | 17 | -3 | NTS | AWC | NO
12 | 0057 |  | Vendor Information For Turbidity Analyser (HACH WATER QUALITY SINGAPORE PTE LTD) | 131236-WSW46-VI-I-0012 | 0 | Ricky | 2026-05-18 | 20 | 2026-06-07 | 2026-05-31 | 13 | -7 | NTS | AWC | NO
13 | 0063 |  | Vendor Information For Level Switch – Conductive Probe (ENDRESS + HAUSER S.E.A. PTE LTD) | 131236-WSW46-VI-I-0013 | 0 | Ricky | 2026-05-26 | 20 | 2026-06-15 | 2026-06-03 | 8 | -12 | NTS | AWC | NO
14 | 0067 |  | Vendor Information For pH Analyser (EMERSON ASIA PACIFIC PTE. LTD.) | 131236-WSW46-VI-I-0014 | 0 | Ricky | 2026-05-28 | 20 | 2026-06-17 | 2026-06-22 | 25 | 5 | RTR | AWC | YES
15 | 0102 |  | Vendor Information For Room Temperature Sensor (KELE & ASSOCIATES PTE LTD - VAISALA) | 131236-WSW46-VI-I-0015 | 0 | Ricky | 2026-07-16 | 20 | 2026-08-05 | 2026-07-29 | 13 | -7 | NTS | AWC | NO
16 | 0115 |  | Vendor Information For Local Display (ENDRESS + HAUSER S.E.A. PTE LTD) | 131236-WSW46-VI-I-0016 | 0 | Ricky | 2026-08-13 | 20 | 2026-09-02 | 2026-08-28 | 15 | -5 | NTS | AWC | NO
17 | 0151 |  | Vendor Information For Cable (LV Power, Signal & Control) (C-KINGDOM CABLE TECHNOLOGY CO., LTD.) | 131236-WSW46-VI-I-0017 | 0 | Ricky | 2026-09-21 | 20 | 2026-10-11 |  | 32 | 12 | SUR
18 | 0152 |  | Vendor Information For SS316 Tube Fittings (YANGZHONG SINYA AUTO-CONTROL ENGINEERING CO.,LTD.) | 131236-WSW46-VI-I-0018 | 0 | Ricky | 2026-09-21 | 20 | 2026-10-11 |  | 32 | 12 | SUR
19 | 0159 |  | Vendor Information For Cable (LV Power, Signal & Control)(KEI INDUSTRIES LTD) | 131236-WSW46-VI-I-0019 | 0 | Ricky | 2026-09-29 | 20 | 2026-10-19 |  | 24 | 4 | SUR
20 | 0166 |  | Vendor Information For Flowmeter - Electromagnetic (ENDRESS + HAUSER S.E.A. PTE LTD) | 131236-WSW46-VI-I-0020 | 0 | Ricky | 2026-10-03 | 20 | 2026-10-23 |  | 20 | 0 | SUR
21 | 0033 |  | Vendor Information For Hydrogen Sulfide Gas Detector (DRAEGER SINGAPORE PTE LTD) | 131236-WIL21-VI-I-0001 | 0 | Ricky | 2026-04-17 | 20 | 2026-05-07 | 2026-05-15 | 28 | 8 | RTR | AWC | YES
22 | 0034 |  | Vendor Information For Carbon Monoxide Gas Detector (DRAEGER SINGAPORE PTE LTD) | 131236-WIL21-VI-I-0002 | 0 | Ricky | 2026-04-17 | 20 | 2026-05-07 | 2026-05-15 | 28 | 8 | RTR | AWC | YES
23 | 0035 |  | Vendor Information For Flammable (LEL) Gas Detector (DRAEGER SINGAPORE PTE LTD) | 131236-WIL21-VI-I-0003 | 0 | Ricky | 2026-04-17 | 20 | 2026-05-07 | 2026-05-15 | 28 | 8 | RTR | AWC | YES
24 | 0036 |  | Vendor Information For Weight Transmitter (METTLER – TOLEDO (S) PTE LTD) | 131236-WIL21-VI-I-0004 | 0 | Ricky | 2026-04-28 | 20 | 2026-05-18 | 2026-05-31 | 33 | 13 | RTR | AWC | YES
25 | 0061 |  | Vendor Information For Toxicity Analyser (AI ANALYTICAL PTE LTD) | 131236-WIL21-VI-I-0005 | 0 | Ricky | 2026-05-26 | 20 | 2026-06-15 | 2026-06-03 | 8 | -12 | RTR | AWC | YES
26 | 0062 |  | Vendor Information For Motion Switch (IFM ELECTRONIC PTE LTD) | 131236-WIL21-VI-I-0006 | 0 | Ricky | 2026-05-26 | 20 | 2026-06-15 | 2026-06-04 | 9 | -11 | RTR | APP | YES
27 | 0072 |  | Vendor Information For Volatile Organic Compound (VOC) Gas Analyser (HONEYWELL RAE SYSTEMS) | 131236-WIL21-VI-I-0007 | 0 | Ricky | 2026-06-03 | 20 | 2026-06-23 | 2026-06-11 | 8 | -12 | RTR | APP | YES
28 | 0049 |  | Vendor Information For Total Solid Analyser (VALMET - WETEC PTE LTD) | 131236-WIL22-VI-I-0001 | 0 | Ricky | 2026-05-12 | 20 | 2026-06-01 | 2026-05-15 | 3 | -17 | RTR | AWC | YES
29 | 0078 |  | Vendor Information For Level Switch Sludge Blanket – Ultrasonic (PULSAR – MAESTRO ASIA) | 131236-WIL22-VI-I-0002 | 0 | Ricky | 2026-06-09 | 20 | 2026-06-29 | 2026-06-28 | 19 | -1 | RTR | APP | YES
30 | 0042 |  | Vendor Information For Level Switch – Tuning Fork (ENDRESS + HAUSER S.E.A. PTE LTD) | 131236-WIL23-VI-I-0001 | 0 | Ricky | 2026-05-04 | 20 | 2026-05-24 | 2026-06-19 | 46 | 26 | RTR | APP | YES
31 | 0043 |  | Vendor Information For Orthophosphate Analyser(ENDRESS + HAUSER S.E.A. PTE LTD) | 131236-WIL23-VI-I-0002 | 0 | Ricky | 2026-05-06 | 20 | 2026-05-26 | 2026-05-15 | 9 | -11 | RTR | AWC | YES
32 | 0045 |  | Vendor Information For Conductivity Analyser(ENDRESS + HAUSER S.E.A. PTE LTD) | 131236-WIL23-VI-I-0003 | 0 | Ricky | 2026-05-08 | 20 | 2026-05-28 | 2026-05-15 | 7 | -13 | RTR | APP | YES
33 | 0047 |  | Vendor Information For ORP Analyser(YOKOGAWA ENGINEERING ASIA PTE LTD) | 131236-WIL23-VI-I-0004 | 0 | Ricky | 2026-05-11 | 20 | 2026-05-31 | 2026-05-15 | 4 | -16 | RTR | APP | YES
34 | 0059 |  | Vendor Information For Total Suspended Solid (MLSS) Analyser (HACH WATER QUALITY SINGAPORE PTE LTD) | 131236-WIL23-VI-I-0005 | 0 | Ricky | 2026-05-26 | 20 | 2026-06-15 | 2026-06-03 | 8 | -12 | RTR | AWC | YES
35 | 0060 |  | Vendor Information For Ammonia Analyser (HACH WATER QUALITY SINGAPORE PTE LTD) | 131236-WIL23-VI-I-0006 | 0 | Ricky | 2026-05-26 | 20 | 2026-06-15 | 2026-06-03 | 8 | -12 | RTR | AWC | YES
36 | 0068 |  | Vendor Information For Dissolved Oxygen Analyser (EMERSON ASIA PACIFIC PTE. LTD.) | 131236-WIL23-VI-I-0007 | 0 | Ricky | 2026-05-28 | 20 | 2026-06-17 | 2026-06-22 | 25 | 5 | RTR | AWC | YES
37 | 0069 |  | Vendor Information For Nitrate / Nitrite Analyser (HACH WATER QUALITY SINGAPORE PTE LTD) | 131236-WIL23-VI-I-0008 | 0 | Ricky | 2026-05-28 | 20 | 2026-06-17 | 2026-06-28 | 31 | 11 | RTR | REJ | YES
38 | 0039 |  | Vendor Information For Differential Pressure Transmitter (EMERSON ASIA PACIFIC PTE. LTD.) | 131236-WNS03-VI-I-0001 | 0 | Ricky | 2026-04-29 | 20 | 2026-05-19 | 2026-05-15 | 16 | -4 | RTR | AWC | YES
39 | 0158 |  | Instrument Master List | 131236-WSW46-SH-I-0001 | 0 | Ricky | 2026-09-23 | 20 | 2026-10-13 |  | 30 | 10 | SUR
40 | 0171 |  | Detailed Engineering FOIP (Fiber Optic Interface Panel) & FOBOT (Fiber Optic Break-Out Tray) Master List | 131236-WSW46-SH-I-0002 | 0 | Ricky | 2026-10-06 | 20 | 2026-10-26 |  | 17 | -3 | SUR
41 | 0172 |  | Detailed Engineering UPSDB Master List | 131236-WSW46-SH-I-0003 | 0 | Ricky | 2026-10-06 | 20 | 2026-10-26 |  | 17 | -3 | SUR
42 | 0174 |  | RIO Panel Master List | 131236-WSW46-SH-I-0004 | 0 | Ricky | 2026-10-07 | 20 | 2026-10-27 |  | 16 | -4 | SUR
43 | 0083 |  | Datasheet For Flammable (LEL) Gas Detector (DRAEGER SINGAPORE PTE LTD) | 131236-WIL21-DS-I-0001 | 0 | Ricky | 2026-06-25 | 20 | 2026-07-15 | 2026-07-17 | 22 | 2 | NTS | AWC | NO
44 | 0084 |  | Datasheet For CO Gas Detector (DRAEGER SINGAPORE PTE LTD) | 131236-WIL21-DS-I-0002 | 0 | Ricky | 2026-06-25 | 20 | 2026-07-15 | 2026-07-28 | 33 | 13 | NTS | AWC | NO
45 | 0105 |  | Datasheet For H2S Gas Detector (DRAEGER SINGAPORE PTE LTD) | 131236-WIL21-DS-I-0003 | 0 | Ricky | 2026-07-17 | 20 | 2026-08-06 | 2026-08-06 | 20 | 0 | NTS | AWC | NO
46 | 0106 |  | Datasheet For Motion Switch (IFM ELECTRONIC PTE LTD) | 131236-WIL21-DS-I-0004 | 0 | Ricky | 2026-07-17 | 20 | 2026-08-06 | 2026-08-06 | 20 | 0 | RTR | NAP | YES
47 | 0116 |  | Datasheet For Weight Transmitter with Load Cell (METTLER TOLEDO (S) PTE. LTD.) | 131236-WIL21-DS-I-0005 | 0 | Ricky | 2026-08-13 | 20 | 2026-09-02 | 2026-08-28 | 15 | -5 | RTR | NAP | YES
48 | 0134 |  | Datasheet For ORP Analyser (YOKOGAWA ENGINEERING ASIA PTE LTD) | 131236-WIL23-DS-I-0001 | 0 | Ricky | 2026-08-27 | 20 | 2026-09-16 | 2026-09-22 | 26 | 6 | NTS | APP | NO
49 | 0104 |  | Datasheet For Low Point Leak Detector (IFM ELECTRONIC PTE LTD) | 131236-WSW46-DS-I-0001 | 0 | Ricky | 2026-07-17 | 20 | 2026-08-06 | 2026-07-29 | 12 | -8 | NTS | APP | NO
50 | 0135 |  | Datasheet For pH Analyser (EMERSON ASIA PACIFIC PTE. LTD.) | 131236-WSW46-DS-I-0002 | 0 | Ricky | 2026-08-28 | 20 | 2026-09-17 | 2026-09-22 | 25 | 5 | RTR | NAP | YES
51 | 0131 |  | INSTRUMENT HOOKUP DRAWINGS FOR DIFFERENTIAL PRESSURE TRANSMITTER (SHEET 1 OF 1) | 131236-WNS03-DR-I-7000 | 0 | Ricky | 2026-08-26 | 20 | 2026-09-15 | 2026-09-22 | 27 | 7 | NTS | AWC | NO
52 | 0116 |  | Datasheet For Weight Transmitter (METTLER – TOLEDO (S) PTE LTD) | 131236-WIL21-DS-I-0006 | 0 | Ricky | 2026-08-13 | 20 | 2026-09-02 | 2026-08-06 | -7 | -27 | RTR | NAP | YES
53 | 00031 | 0031-1 | Vendor Information For Cable Raceway (TRI-STAR INDUSTRIES PTE LTD) | 131236-WSW46-VI-I-0002 | 1 | Ricky | 2026-07-08 | 14 | 2026-07-22 | 2026-07-17 | 9 | -5 | NTS | APP | NO
54 | 00031 | 0031-2 | Vendor Information For Cable Raceway (TRI-STAR INDUSTRIES PTE LTD) | 131236-WSW46-VI-I-0002 | 2 | Ricky | 2026-08-25 | 14 | 2026-09-08 | 2026-09-01 | 7 | -7 | RTR | AWC | YES
55 | 00038 | 0038-1 | Vendor Information For Pressure Transmitter (EMERSON ASIA PACIFIC PTE. LTD.) | 131236-WSW46-VI-I-0004 | 1 | Ricky | 2026-06-12 | 14 | 2026-06-26 | 2026-06-22 | 10 | -4 | NTS | APP | NO
56 | 00040 | 0040-1 | Vendor Information For Level Transmitter Radar (Non-Contacting) (ENDRESS + HAUSER S.E.A. PTE LTD) | 131236-WSW46-VI-I-0005 | 1 | Ricky | 2026-06-03 | 14 | 2026-06-17 | 2026-06-11 | 8 | -6 | NTS | APP | NO
57 | 00041 | 0041-1 | Vendor Information For Pressure Switch(WIKA INSTRUMENTATION PTE. LTD.) | 131236-WSW46-VI-I-0006 | 1 | Ricky | 2026-07-10 | 14 | 2026-07-24 | 2026-08-06 | 27 | 13 | NTS | APP | NO
58 | 00046 | 0046-1 | Vendor Information For Level Transmitter – RF Admittance(ENDRESS + HAUSER S.E.A. PTE LTD) | 131236-WSW46-VI-I-0007 | 1 | Ricky | 2026-05-18 | 14 | 2026-06-01 | 2026-05-31 | 13 | -1 | NTS | APP | NO
59 | 00048 | 0048-1 | Vendor Information For Auto Sampler (ENDRESS + HAUSER S.E.A. PTE LTD) | 131236-WSW46-VI-I-0008 | 1 | Ricky | 2026-06-12 | 14 | 2026-06-26 | 2026-06-22 | 10 | -4 | NTS | APP | NO
60 | 00050 | 0050-1 | Vendor Information For Low Point Leak Detector (IFM ELECTRONIC PTE LTD) | 131236-WSW46-VI-I-0009 | 1 | Ricky | 2026-06-12 | 14 | 2026-06-26 | 2026-07-01 | 19 | 5 | NTS | APP | NO
61 | 00051 | 0051-1 | Vendor Information For Thermal Mass Flowmeter (ENDRESS + HAUSER S.E.A. PTE LTD) | 131236-WSW46-VI-I-0010 | 1 | Ricky | 2026-06-09 | 14 | 2026-06-23 | 2026-07-01 | 22 | 8 | NTS | APP | NO
62 | 00067 | 0067-1 | Vendor Information For pH Analyser (EMERSON ASIA PACIFIC PTE. LTD.) | 131236-WSW46-VI-I-0014 | 1 | Ricky | 2026-07-08 | 14 | 2026-07-22 | 2026-07-17 | 9 | -5 | RTR | AWC | YES
63 | 00067 | 0067-2 | Vendor Information For pH Analyser (EMERSON ASIA PACIFIC PTE. LTD.) | 131236-WSW46-VI-I-0014 | 2 | Ricky | 2026-08-14 | 14 | 2026-08-28 | 2026-08-28 | 14 | 0 | NTS | APP | NO
64 | 00033 | 0033-1 | Vendor Information For Hydrogen Sulfide Gas Detector (DRAEGER SINGAPORE PTE LTD) | 131236-WIL21-VI-I-0001 | 1 | Ricky | 2026-05-29 | 14 | 2026-06-12 | 2026-06-11 | 13 | -1 | NTS | APP | NO
65 | 00034 | 0034-1 | Vendor Information For Carbon Monoxide Gas Detector (DRAEGER SINGAPORE PTE LTD) | 131236-WIL21-VI-I-0002 | 1 | Ricky | 2026-05-29 | 14 | 2026-06-12 | 2026-06-22 | 24 | 10 | NTS | APP | NO
66 | 00035 | 0035-1 | Vendor Information For Flammable (LEL) Gas Detector (DRAEGER SINGAPORE PTE LTD) | 131236-WIL21-VI-I-0003 | 1 | Ricky | 2026-05-29 | 14 | 2026-06-12 | 2026-06-22 | 24 | 10 | NTS | APP | NO
67 | 00036 | 0036-1 | Vendor Information For Weight Transmitter (METTLER – TOLEDO (S) PTE LTD) | 131236-WIL21-VI-I-0004 | 1 | Ricky | 2026-06-22 | 14 | 2026-07-06 | 2026-07-07 | 15 | 1 | RTR | AWC | YES
68 | 00036 | 0036-2 | Vendor Information For Weight Transmitter (METTLER – TOLEDO (S) PTE LTD) | 131236-WIL21-VI-I-0004 | 2 | Ricky | 2026-07-10 | 14 | 2026-07-24 | 2026-07-27 | 17 | 3 | NTS | APP | NO
69 | 00061 | 0061-1 | Vendor Information For Toxicity Analyser (AI ANALYTICAL PTE LTD) | 131236-WIL21-VI-I-0005 | 1 | Ricky | 2026-07-10 | 14 | 2026-07-24 | 2026-07-27 | 17 | 3 | NTS | APP | NO
70 | 00072 | 0072-1 | Vendor Information For Volatile Organic Compound (VOC) Gas Analyser (HONEYWELL RAE SYSTEMS) | 131236-WIL21-VI-I-0007 | 1 | Ricky | 2026-06-22 | 14 | 2026-07-06 | 2026-07-07 | 15 | 1 | NTS | APP | NO
71 | 00049 | 0049-1 | Vendor Information For Total Solid Analyser (VALMET - WETEC PTE LTD) | 131236-WIL22-VI-I-0001 | 1 | Ricky | 2026-06-03 | 14 | 2026-06-17 | 2026-06-11 | 8 | -6 | NTS | APP | NO
72 | 00042 | 0042-1 | Vendor Information For Level Switch – Tuning Fork (ENDRESS + HAUSER S.E.A. PTE LTD) | 131236-WIL23-VI-I-0001 | 1 | Ricky | 2026-07-10 | 14 | 2026-07-24 | 2026-07-27 | 17 | 3 | NTS | APP | NO
73 | 00043 | 0043-1 | Vendor Information For Orthophosphate Analyser(ENDRESS + HAUSER S.E.A. PTE LTD) | 131236-WIL23-VI-I-0002 | 1 | Ricky | 2026-06-03 | 14 | 2026-06-17 | 2026-06-11 | 8 | -6 | NTS | APP | NO
74 | 00045 | 0045-1 | Vendor Information For Conductivity Analyser(ENDRESS + HAUSER S.E.A. PTE LTD) | 131236-WIL23-VI-I-0003 | 1 | Ricky | 2026-06-03 | 14 | 2026-06-17 | 2026-06-11 | 8 | -6 | NTS | APP | NO
75 | 00047 | 0047-1 | Vendor Information For ORP Analyser(YOKOGAWA ENGINEERING ASIA PTE LTD) | 131236-WIL23-VI-I-0004 | 1 | Ricky | 2026-05-18 | 14 | 2026-06-01 | 2026-05-31 | 13 | -1 | NTS | APP | NO
76 | 00060 | 0060-1 | Vendor Information For Ammonia Analyser (HACH WATER QUALITY SINGAPORE PTE LTD) | 131236-WIL23-VI-I-0006 | 1 | Ricky | 2026-07-10 | 14 | 2026-07-24 | 2026-07-27 | 17 | 3 | NTS | APP | NO
77 | 00068 | 0068-1 | Vendor Information For Dissolved Oxygen Analyser (EMERSON ASIA PACIFIC PTE. LTD.) | 131236-WIL23-VI-I-0007 | 1 | Ricky | 2026-07-08 | 14 | 2026-07-22 | 2026-07-16 | 8 | -6 | RTR | AWC | YES
78 | 00068 | 0068-2 | Vendor Information For Dissolved Oxygen Analyser (EMERSON ASIA PACIFIC PTE. LTD.) | 131236-WIL23-VI-I-0007 | 2 | Ricky | 2026-08-14 | 14 | 2026-08-28 | 2026-08-28 | 14 | 0 | NTS | APP | NO
79 | 00069 | 0069-1 | Vendor Information For Nitrate / Nitrite Analyser (HACH WATER QUALITY SINGAPORE PTE LTD) | 131236-WIL23-VI-I-0008 | 1 | Ricky | 2026-07-09 | 14 | 2026-07-23 | 2026-08-06 | 28 | 14 | RTR | REJ | YES
80 | 00039 | 0039-1 | Vendor Information For Differential Pressure Transmitter (EMERSON ASIA PACIFIC PTE. LTD.) | 131236-WNS03-VI-I-0001 | 1 | Ricky | 2026-06-12 | 14 | 2026-06-26 | 2026-06-22 | 10 | -4 | NTS | APP | NO
Electrical
1 | 0094 |  | Vendor Information For Electrical Power Transformer & Distribution Transformer (TECO ELECTRIC & MACHINERY PTE LTD) | 131236-WSW46-VI-E-0001 | 0 | Ammar | 2026-07-08 | 20 | 2026-07-28 | 2026-07-27 | 19 | -1 | RTR | NAP | YES
2 | 0095 |  | Vendor Information For Electrical High Voltage Switchgear Panel (SCHNEIDER ELECTRIC PTE LTD) | 131236-WSW46-VI-E-0002 | 0 | Ammar | 2026-07-08 | 20 | 2026-07-28 | 2026-07-27 | 19 | -1 | RTR | NAP | YES
3 | 0101 |  | Vendor Information For Low Voltage Electrical Equipment Works (SUNLIGHT ELECTRICAL PTE LTD) | 131236-WSW46-VI-E-0003 | 0 | Ammar | 2026-07-15 | 20 | 2026-08-04 | 2026-07-27 | 12 | -8 | RTR | NAP | YES
4 | 0130 |  | Vendor Information For Cable Raceway (TRI-STAR INDUSTRIES PTE LTD) | 131236-WSW46-VI-E-0004 | 0 | Ammar | 2026-08-26 | 20 | 2026-09-15 | 2026-09-10 | 15 | -5 | RTR | AWC | YES
5 | 0133 |  | Vendor Information For Electrical High Voltage DOL Panel (SCHNEIDER ELECTRIC PTE LTD) | 131236-WSW46-VI-E-0005 | 0 | Ammar | 2026-08-26 | 20 | 2026-09-15 | 2026-09-10 | 15 | -5 | RTR | NAP | YES
6 | 0141 |  | Vendor Information For Emergency Generator (VIBROPOWER PTE LTD) | 131236-WSW46-VI-E-0006 | 0 | Ammar | 2026-09-04 | 20 | 2026-09-24 | 2026-09-22 | 18 | -2 | RTR | AWC | YES
7 | 00094 | 0094-1 | Vendor Information For Electrical Power Transformer & Distribution Transformer (TECO ELECTRIC & MACHINERY PTE LTD) | 131236-WSW46-VI-E-0001 | 1 | Ammar | 2026-09-25 | 14 | 2026-10-09 | 2026-10-14 | 19 | 5 | RTR | AWC | YES
8 | 00095 | 0095-1 | Vendor Information For Electrical High Voltage Switchgear Panel (SCHNEIDER ELECTRIC PTE LTD) | 131236-WSW46-VI-E-0002 | 1 | Ammar | 2026-08-26 | 14 | 2026-09-09 | 2026-09-10 | 15 | 1 | RTR | AWC | YES
9 | 00101 | 0101-1 | Vendor Information For Low Voltage Electrical Equipment Works (SUNLIGHT ELECTRICAL PTE LTD) | 131236-WSW46-VI-E-0003 | 1 | Ammar | 2026-08-28 | 14 | 2026-09-11 | 2026-09-22 | 25 | 11 | RTR | NAP | YES
Mechanical
1 | 0065 |  | Vendor Information For NDT Company Details & Procedure (Ace Quality Testing & Inspection Services Pte Ltd) | 131236-WIL00-VI-M-0001 | 0 | Dinesh | 2026-05-28 | 20 | 2026-06-17 | 2026-06-29 | 32 | 12 | RTR | AWC | YES
2 | 0076 |  | Preliminary Design Submission For Design, Supply, Manufacturing, FAT, and Delivery Of Stainless Steel (SS316L) Pipes & Fittings Vendor Information (RACCORTUBI SINGAPORE PTE LTD) | 131236-WIL00-VI-M-0002 | 0 | Fadhli Muiz | 2026-06-09 | 20 | 2026-06-29 | 2026-06-29 | 20 | 0 | RTR | AWC | YES
3 | 0064 |  | Vendor Information For Intermediate Screen And Its Associated Dewatering Press (WAM Singapore BHM Pte Ltd) | 131236-WIL21-VI-M-0001 | 0 | Alan Siah | 2026-05-26 | 20 | 2026-06-15 | 2026-06-28 | 33 | 13 | RTR | AWC | YES
4 | 0066 |  | Preliminary Design Submission For Design, Supply, Manufacturing, Factory Acceptance Test, Delivery, Supervision of Installation and Testing & Commissioning Of Grit Classifier (WAM Singapore BHM Pte Ltd) | 131236-WIL21-VI-M-0002 | 0 | Alan Siah | 2026-05-28 | 20 | 2026-06-17 | 2026-06-29 | 32 | 12 | RTR | AWC | YES
5 | 0077 |  | Preliminary Design Submission For Design, Supply, Manufacturing, Factory Acceptance Test, Delivery, Supervision of Installation and Testing & Commissioning Of Screenings And Grit Conveyors Including Associated Chute, Diverter Gates And Slide Gates (WAM Singapore BHM Pte Ltd) | 131236-WIL21-VI-M-0003 | 0 | Alan Siah | 2026-06-09 | 20 | 2026-06-29 | 2026-07-27 | 48 | 28 | RTR | AWC | YES
6 | 0112 |  | Vendor Information for Grit Tank Grease And Scum Removal Equipment (PROBIG GmbH) | 131236-WIL21-VI-M-0004 | 0 | Fadhli Muiz | 2026-08-06 | 20 | 2026-08-26 | 2026-08-27 | 21 | 1 | RTR | NAP | YES
7 | 0093 |  | Vendor Information For Lamella Settlement, Lamella support structure, PST Sludge Scraper and PST Scum Skimming and Removal System (Nova Industries International L.L.C-FZ) | 131236-WIL22-VI-M-0001 | 0 | Kenny Lim | 2026-07-08 | 20 | 2026-07-28 | 2026-08-17 | 40 | 20 | RTR | NAP | YES
8 | 0023 |  | Preliminary Design Submission For Design, Supply, Manufacturing, Factory Acceptance Test, Delivery, Supervision of Installation and Testing & Commissioning Of Hyperbolic Mixer(INVENT UMWELT- UND VERFAHRENSTECHNIK AG) | 131236-WIL23-VI-M-0001 | 0 | Wai Bin | 2026-03-26 | 20 | 2026-04-15 | 2026-04-30 | 35 | 15 | RTR | AWC | YES
9 | 0080 |  | Vendor Information For Design, Manufacturing, FAT, Supply & Delivery of MFS (Membrane) (Veolia Water Technologies & Solutions (Singapore) Pte Ltd) | 131236-WIL23-VI-M-0002 | 0 | Tan Si Hui | 2026-06-12 | 20 | 2026-07-02 | 2026-07-18 | 36 | 16 | RTR | AWC | YES
10 | 0088 |  | Vendor Information Submission For Design, Supply, Manufacturing, FAT, and Delivery Of Surge Vessel Including Instrument and Structure Support (SYNCHONG HOE ENGINEERING SDN. BHD.) | 131236-WNS03-VI-M-0001 | 0 | Fadhli Muiz | 2026-06-29 | 20 | 2026-07-19 | 2026-07-27 | 28 | 8 | RTR | NAP | YES
11 | 0103 |  | Vendor Information For Diffusers (Air Diffuser – Grit System and Bioreactors) (ENVIRONMENTAL DYNAMICS INTERNATIONAL, INC (EDI)) | 131236-WSW46-VI-M-0001 | 0 | Tan Si Hui | 2026-07-16 | 20 | 2026-08-05 | 2026-08-27 | 42 | 22 | RTR | NAP | YES
12 | 0119 |  | Datasheet For Bioreactor Tank Mixed Liquor Mixer | 131236-WIL23-DS-M-0001 | 0 | Wu Hongqing | 2026-08-14 | 20 | 2026-09-03 | 2026-09-11 | 28 | 8 | RTR | AWC | YES
13 | 0032 |  | Design Calculation For Existing RC Slab And Beam For Max.10 Tons Mini Spider Crane Parking And Access At SFL. 15.8m Industrial LM2 (WIL 21 AND 22) | 131236-WSW46-CL-M-0001 | 0 | Mark | 2026-04-16 | 20 | 2026-05-06 | 2026-06-22 | 67 | 47 | RTR | NAP | YES
14 | 0120 |  | Foul Air Pipeworks Pressure Drop Calculation For ILM2 OCF1 | 131236-WSW46-CL-M-0002 | 0 | Wang YiQian | 2026-08-17 | 20 | 2026-09-06 | 2026-09-29 | 43 | 23 | RTR | INF | YES
15 | 0138 |  | Foul Air Pipeworks Pressure Drop Calculation For ILM2 OCF2 | 131236-WSW46-CL-M-0003 | 0 | Wu Hongqing | 2026-09-01 | 20 | 2026-09-21 | 2026-09-29 | 28 | 8 | RTR | NAP | YES
| 0192 |  | SS316-PN10 Pipe & Flange Thickness Calculations Design Selection | 131236-WSW46-CL-M-0004 | 0 |  | 2026-10-21 | 20 | 2026-11-10 |  | 2 | -18 | SUR
16 | 0121 |  | DPS And Intake Chamber Pipe Size Calculation | 131236-WIL21-CL-M-0001 | 0 | Wang YiQian | 2026-08-18 | 20 | 2026-09-07 | 2026-09-29 | 42 | 22 | RTR | INF | YES
17 | 0122 |  | Intermediate Screen Area Pipe Size Calculation | 131236-WIL21-CL-M-0002 | 0 | Wang YiQian | 2026-08-18 | 20 | 2026-09-07 | 2026-09-30 | 43 | 23 | RTR | INF | YES
18 | 0123 |  | Fine Screen Area Pipe Size Calculation | 131236-WIL21-CL-M-0003 | 0 | Wang YiQian | 2026-08-19 | 20 | 2026-09-08 | 2026-09-29 | 41 | 21 | RTR | INF | YES
19 | 0124 |  | Aerated Grit Tank Area Pipe Size Calculation | 131236-WIL21-CL-M-0004 | 0 | Wang YiQian | 2026-08-24 | 20 | 2026-09-13 | 2026-09-30 | 37 | 17 | RTR | INF | YES
20 | 0125 |  | Grit Classifier & Hopper Area Pipe Size Calculation | 131236-WIL21-CL-M-0005 | 0 | Wang YiQian | 2026-08-24 | 20 | 2026-09-13 | 2026-09-29 | 36 | 16 | RTR | INF | YES
21 | 0126 |  | Headworks Grease and Scum Wet Well Area Pipe Size Calculation | 131236-WIL21-CL-M-0006 | 0 | Wang YiQian | 2026-08-24 | 20 | 2026-09-13 | 2026-09-30 | 37 | 17 | RTR | INF | YES
22 | 0161 |  | Influent Flowmeter Chamber Drainage Sump Pump Head Calculation | 131236-WIL21-CL-M-0007 | 0 | Wang YiQian | 2026-10-01 | 20 | 2026-10-21 |  | 22 | 2 | SUR
23 | 0162 |  | Plant Drainage PS Wet Well Compartment 2 Pump Head Calculation | 131236-WIL21-CL-M-0008 | 0 | Wang YiQian | 2026-10-01 | 20 | 2026-10-21 |  | 22 | 2 | SUR
24 | 0169 |  | Grease and Scum Wet Well Pump Head Calculation | 131236-WIL21-CL-M-0009 | 0 | Wang YiQian | 2026-10-05 | 20 | 2026-10-25 |  | 18 | -2 | SUR
| 0183 |  | Grit Tank Pump Head Calculation | 131236-WIL21-CL-M-0010 | 0 |  | 2026-10-16 | 20 | 2026-11-05 |  | 7 | -13 | SUR
25 | 0170 |  | Primary Scum Wet Well Pump Head Calculation | 131236-WIL21-CL-M-0001 | 0 | Wang YiQian | 2026-10-05 | 20 | 2026-10-25 |  | 18 | -2 | SUR
| 0184 |  | Primary Sludge Transfer Pump Head Calculation | 131236-WIL22-CL-M-0002 | 0 |  | 2026-10-16 | 20 | 2026-11-05 |  | 7 | -13 | SUR
26 | 0153 |  | MBR Fine Screen & Bioreactor Pipe Size Calculation | 131236-WIL23-CL-M-0001 | 0 | Wu Hongqing | 2026-09-22 | 20 | 2026-10-12 |  | 31 | 11 | SUR
27 | 0154 |  | Membrane Area Pipe Size Calculation | 131236-WIL23-CL-M-0002 | 0 | Wu Hongqing | 2026-09-22 | 20 | 2026-10-12 |  | 31 | 11 | SUR
28 | 0155 |  | MBR Filtrate Tank & Transfer Pump Pipe Size Calculation | 131236-WIL23-CL-M-0003 | 0 | Wu Hongqing | 2026-09-22 | 20 | 2026-10-12 |  | 31 | 11 | SUR
29 | 0156 |  | WAS, RAS & Mixed Liquor Wet Well Pipe Size Calculation | 131236-WIL23-CL-M-0004 | 0 | Wu Hongqing | 2026-09-22 | 20 | 2026-10-12 |  | 31 | 11 | SUR
30 | 0163 |  | Bioreactor Drainage Pump Head Calculation | 131236-WIL23-CL-M-0005 | 0 | Wang YiQian | 2026-10-03 | 20 | 2026-10-23 |  | 20 | 0 | SUR
31 | 0164 |  | DeOX&RAS Tank Drainage Pump Head Calculation | 131236-WIL23-CL-M-0006 | 0 | Wang YiQian | 2026-10-03 | 20 | 2026-10-23 |  | 20 | 0 | SUR
32 | 0165 |  | MBR Filtrate Tank Drainage Pump Head Calculation | 131236-WIL23-CL-M-0007 | 0 | Wang YiQian | 2026-10-03 | 20 | 2026-10-23 |  | 20 | 0 | SUR
33 | 0168 |  | Membrane Scum Wet Well Pump Head Calculation | 131236-WIL23-CL-M-0008 | 0 | Wang YiQian | 2026-10-05 | 20 | 2026-10-25 |  | 18 | -2 | SUR
| 0185 |  | MBR Filtrate Pump Head Calculation | 131236-WIL23-CL-M-0009 | 0 |  | 2026-10-16 | 20 | 2026-11-05 |  | 7 | -13 | SUR
| 0195 |  | Waste Activated Sludge Pump Head Calculation | 131236-WIL23-CL-M-0010 | 0 |  | 2026-10-23 | 20 | 2026-11-12 |  | 0 | -20 | SUR
34 | 0128 |  | GA Drawing for Bioreactor Mixed Liquor Mixer Sheet 1 of 2 | 131236-WIL23-DR-M-5500 | 0 | Wu Hongqing | 2026-08-25 | 20 | 2026-09-14 | 2026-09-21 | 27 | 7 | RTR | AWC | YES
35 | 0128 |  | GA Drawing for Bioreactor Mixed Liquor Mixer Sheet 2 of 2 | 131236-WIL23-DR-M-5501 | 0 | Wu Hongqing | 2026-08-25 | 20 | 2026-09-14 | 2026-09-21 | 27 | 7 | RTR | AWC | YES
36 | 0052 |  | ILM2 - HEAD WORKS BLOWER ROOM AREA DN300 - RISER PIPE Sheet 1 Of 2 | 131236-WIL21-DR-M-5000 | 0 | Rizal | 2026-05-13 | 20 | 2026-06-02 | 2026-06-03 | 21 | 1 | RTR | NAP | YES
37 | 0052 |  | ILM2 - HEAD WORKS BLOWER ROOM AREA DN300 - RISER PIPE Sheet 2 Of 2 | 131236-WIL21-DR-M-1000 | 0 | Rizal | 2026-05-13 | 20 | 2026-06-02 | 2026-06-03 | 21 | 1 | RTR | NAP | YES
38 | 0114 |  | P&ID-INTERMEDIATE SCREENS 1,2 & 3 | 131236-WIL21-DR-P-6000 | 0 | Wang YiQian | 2026-08-12 | 20 | 2026-09-01 |  | 72 | 52 | SUR
39 | 0114 |  | P&ID-INTERMEDIATE SCREENS 4,5 & 6 | 131236-WIL21-DR-P-6001 | 0 | Wang YiQian | 2026-08-12 | 20 | 2026-09-01 |  | 72 | 52 | SUR
40 | 0114 |  | P&ID-ODOUR HEADERS AND FLOWMETERS ILM OCF1 | 131236-WIL21-DR-P-6002 | 0 | Wang YiQian | 2026-08-12 | 20 | 2026-09-01 |  | 72 | 52 | SUR
41 | 0114 |  | P&ID-FINE SCREENS 1,2 & 3 | 131236-WIL21-DR-P-6003 | 0 | Wang YiQian | 2026-08-12 | 20 | 2026-09-01 |  | 72 | 52 | SUR
42 | 0114 |  | P&ID-FINE SCREENS 4,5 & 6 | 131236-WIL21-DR-P-6004 | 0 | Wang YiQian | 2026-08-12 | 20 | 2026-09-01 |  | 72 | 52 | SUR
43 | 0114 |  | P&ID-GRIT TANKS 1 & 2 | 131236-WIL21-DR-P-6005 | 0 | Wang YiQian | 2026-08-12 | 20 | 2026-09-01 |  | 72 | 52 | SUR
44 | 0114 |  | P&ID-GRIT TANKS 3 & 4 | 131236-WIL21-DR-P-6006 | 0 | Wang YiQian | 2026-08-12 | 20 | 2026-09-01 |  | 72 | 52 | SUR
45 | 0114 |  | P&ID-GRIT TANKS 5 & 6 | 131236-WIL21-DR-P-6007 | 0 | Wang YiQian | 2026-08-12 | 20 | 2026-09-01 |  | 72 | 52 | SUR
46 | 0114 |  | P&ID-GRIT AIR BLOWERS | 131236-WIL21-DR-P-6008 | 0 | Wang YiQian | 2026-08-12 | 20 | 2026-09-01 |  | 72 | 52 | SUR
47 | 0114 |  | P&ID-GRIT CLASSIFIER AND CONVEYANCE SYSTEM | 131236-WIL21-DR-P-6009 | 0 | Wang YiQian | 2026-08-12 | 20 | 2026-09-01 |  | 72 | 52 | SUR
48 | 0114 |  | P&ID-COMMON LOADOUT FACILITY | 131236-WIL21-DR-P-6010 | 0 | Wang YiQian | 2026-08-12 | 20 | 2026-09-01 |  | 72 | 52 | SUR
49 | 0114 |  | P&ID-GREASE AND SCUM REMOVAL SYSTEM | 131236-WIL21-DR-P-6011 | 0 | Wang YiQian | 2026-08-12 | 20 | 2026-09-01 |  | 72 | 52 | SUR
50 | 0114 |  | P&ID GREASE AND SCUM REMOVAL SYSTEM | 131236-WIL21-DR-P-6012 | 0 | Wang YiQian | 2026-08-12 | 20 | 2026-09-01 |  | 72 | 52 | SUR
51 | 0114 |  | P&ID-INDUSTRIAL LM2 PRIMARY TREATMENT & HEADWORKS PLANT DRAINAGE | 131236-WIL21-DR-P-6015 | 0 | Wang YiQian | 2026-08-12 | 20 | 2026-09-01 |  | 72 | 52 | SUR
52 | 0114 |  | P&ID-ILM2 PLANT DRAINAGE PUMPING STATION | 131236-WIL21-DR-P-6016 | 0 | Wang YiQian | 2026-08-12 | 20 | 2026-09-01 |  | 72 | 52 | SUR
0194
0194
0194
0194
0194
0194
0194
0194
0194
0194
0194
0194
0194
0194
0194
0194
0194
0194
0194
0194
0194
0194
0194
0194
0194
53 | 0137 |  | P&ID SURGE VESSELS | 131236-WNS03-DR-P-6050 | 0 | Fadhli Muiz | 2026-08-31 | 20 | 2026-09-20 |  | 53 | 33 | SUR
54 | 0054 |  | ITP, WPS & PQR For SS316L Pipe Fabrication Works | 131236-WIL00-QA-M-0001 | 0 | Dinesh | 2026-05-13 | 20 | 2026-06-02 | 2026-06-03 | 21 | 1 | RTR | AWC | YES
55 | 0056 |  | Welder Qualification for Carbon Steel & Stainless Steel Fabrication and Site Installation Works(UES Holdings Pte Ltd) | 131236-WIL00-QA-M-0002 | 0 | Dinesh | 2026-05-18 | 20 | 2026-06-07 | 2026-06-03 | 16 | -4 | RTR | AWC | YES
56 | 0070 |  | ITP, WPS & PQR For Pipe Support workshop Fabrication Works | 131236-WIL00-QA-M-0003 | 0 | Dinesh | 2026-05-28 | 20 | 2026-06-17 | 2026-06-29 | 32 | 12 | RTR | INF | YES
57 | 0157 |  | Inspection and Test Plan for SS316L Pipe, Fittings & Flanges (Raccortubi Singapore Pte. Ltd.) | 131236-WIL00-QA-M-0004 | 0 | Dinesh | 2026-09-23 | 20 | 2026-10-13 |  | 30 | 10 | SUR
58 | 0146 |  | ITP For Screen & Grit Conveyors System | 131236-WIL23-QA-M-0001 | 0 | Fadhli Muiz | 2026-09-15 | 20 | 2026-10-05 |  | 38 | 18 | SUR
59 | 0147 |  | ITP For Grit Classifier | 131236-WIL23-QA-M-0002 | 0 | Fadhli Muiz | 2026-09-15 | 20 | 2026-10-05 |  | 38 | 18 | SUR
60 | 0148 |  | ITP For Screen & Dewatering Press | 131236-WIL23-QA-M-0003 | 0 | Fadhli Muiz | 2026-09-15 | 20 | 2026-10-05 |  | 38 | 18 | SUR
61 | 0086 |  | ITP, FAT Procedure for ILM2 Bioreactor Mixed Liquor Mixer | 131236-WIL23-QA-M-0001 | 0 | Kenny | 2026-06-26 | 20 | 2026-07-16 | 2026-07-27 | 31 | 11 | RTR | AWC | YES
62 | 0113 |  | ITP For Modules MBR (Polymeric Membrane System) | 131236-WIL23-QA-M-0002 | 0 | Wu Hongqing | 2026-08-06 | 20 | 2026-08-26 | 2026-08-29 | 23 | 3 | RTR | NAP | YES
63 | 0176 |  | FAT For WIL21 DN300 Riser pipe Supports | 131236-WIL21-RT-M-0001 | 0 | Dinesh | 2026-10-08 | 20 | 2026-10-28 |  | 15 | -5 | SUR
64 | 0087 |  | CFD Report for Bioreactor Mixed Liquor Mixer | 131236-WIL23-RT-M-0001 | 0 | Kenny | 2026-06-26 | 20 | 2026-07-16 | 2026-07-27 | 31 | 11 | RTR | NAP | YES
65 | 0074 |  | Method Statement and Risk Assessment & Safe Work Procedure for Steel Pipe Fabrication, Welding and Site Installation | 131236-WIL21-MS-M-0001 | 0 |  | 2026-06-05 | 20 | 2026-06-25 | 2026-07-27 | 52 | 32 | RTR | INF | YES
66 | 0179 |  | MSRA & Safe Work Procedure for Erecting and Dismantling of Scaffold Access and Barricade | 131236-WIL21-MS-M-0002 | 0 | Rizal | 2026-10-14 | 20 | 2026-11-03 |  | 9 | -11 | SUR
67 | 00064 | 0064-1 | Vendor Information For Intermediate Screen And Its Associated Dewatering Press (WAM Singapore BHM Pte Ltd) | 131236-WIL21-VI-M-0001 | 1 | Fadhli Muiz | 2026-07-22 | 14 | 2026-08-05 | 2026-08-28 | 37 | 23 | RTR | AWC | YES
68 | 00093 | 0093-1 | Vendor Information For Lamella Settlement, Lamella support structure, PST Sludge Scraper and PST Scum Skimming and Removal System (Nova Industries International L.L.C-FZ) | 131236-WIL22-VI-M-0001 | 1 | Kenny | 2026-09-21 | 14 | 2026-10-05 | 2026-09-28 | 7 | -7 | RTR | NAP | YES
69 | 00093 | 0093-2 | Vendor Information For Lamella Settlement, Lamella support structure, PST Sludge Scraper and PST Scum Skimming and Removal System (Nova Industries International L.L.C-FZ) | 131236-WIL22-VI-M-0001 | 2 | Fadhli Muiz | 2026-10-09 | 14 | 2026-10-23 | 2026-10-15 | 6 | -8 | RTR | AWC | YES
70 | 00023 | 0023-1 | Preliminary Design Submission For Design, Supply, Manufacturing, Factory Acceptance Test, Delivery, Supervision of Installation and Testing & Commissioning Of Hyperbolic Mixer(INVENT UMWELT- UND VERFAHRENSTECHNIK AG) | 131236-WIL23-VI-M-0001 | 1 | Wai Bin | 2026-07-10 | 14 | 2026-07-24 | 2026-07-27 | 17 | 3 | RTR | AWC | YES
71 | 00023 | 0023-2 | Preliminary Design Submission For Design, Supply, Manufacturing, Factory Acceptance Test, Delivery, Supervision of Installation and Testing & Commissioning Of Hyperbolic Mixer(INVENT UMWELT- UND VERFAHRENSTECHNIK AG) | 131236-WIL23-VI-M-0001 | 2 | Wu Hongqing | 2026-10-01 | 14 | 2026-10-15 | 2026-10-15 | 14 | 0 | NTS | APP | NO
72 | 00088 | 0088-1 | Vendor Information Submission For Design, Supply, Manufacturing, FAT, and Delivery Of Surge Vessel Including Instrument and Structure Support (SYNCHONG HOE ENGINEERING SDN. BHD.) | 131236-WNS03-VI-M-0001 | 1 | Fadhli Muiz | 2026-08-13 | 14 | 2026-08-27 | 2026-09-11 | 29 | 15 | RTR | AWC | YES
73 | 00103 | 0103-1 | Vendor Information For Diffusers (Air Diffuser – Grit System and Bioreactors) (ENVIRONMENTAL DYNAMICS INTERNATIONAL, INC (EDI)) | 131236-WSW46-VI-M-0001 | 1 | Wu Hongqing | 2026-09-21 | 14 | 2026-10-05 | 2026-10-06 | 15 | 1 | RTR | AWC | YES
74 | 00119 | 0119-1 | Datasheet For Bioreactor Tank Mixed Liquor Mixer | 131236-WIL23-DS-M-0001 | 1 | Wu Hongqing | 2026-10-08 | 14 | 2026-10-22 |  | 15 | 1 | SUR
75 | 00120 | 0120-1 | Foul Air Pipeworks Pressure Drop Calculation For ILM2 OCF1 | 131236-WSw46-CL-M-0002 | 1 | Wang YiQian | 2026-10-01 | 14 | 2026-10-15 |  | 22 | 8 | SUR
76 | 00138 | 0138-1 | Foul Air Pipeworks Pressure Drop Calculation For ILM2 OCF2 | 131236-WSW46-CL-M-0003 | 1 | Wu Hongqing | 2026-10-01 | 14 | 2026-10-15 |  | 22 | 8 | SUR
77 | 00128 | 0128-1 | GA Drawing for Bioreactor Mixed Liquor Mixer Sheet 1 of 2 | 131236-WIL23-DR-M-5500 | 1 | Wu Hongqing | 2026-10-08 | 14 | 2026-10-22 |  | 15 | 1 | SUR
78 | 00128 | 0128-1 | GA Drawing for Bioreactor Mixed Liquor Mixer Sheet 2 of 2 | 131236-WIL23-DR-M-5501 | 1 | Wu Hongqing | 2026-10-08 | 14 | 2026-10-22 |  | 15 | 1 | SUR
79 | 00052 | 0052-1 | ILM2 - HEAD WORKS BLOWER ROOM AREA DN300 - RISER PIPE Sheet 1 Of 2 | 131236-WIL21-DR-M-5000 | 1 | Rizal | 2026-08-13 | 14 | 2026-08-27 | 2026-08-28 | 15 | 1 | NTS | APP | NO
80 | 00052 | 0052-1 | ILM2 - HEAD WORKS BLOWER ROOM AREA DN300 - RISER PIPE Sheet 2 Of 2 | 131236-WIL21-DR-M-1000 | 1 | Rizal | 2026-08-13 | 14 | 2026-08-27 | 2026-08-28 | 15 | 1 | NTS | APP | NO
81 | 00086 | 0086-1 | ITP, FAT Procedure for ILM2 Bioreactor Mixed Liquor Mixer | 131236-WIL23-QA-M-0001 | 1 | Wu Hongqing | 2026-10-08 | 14 | 2026-10-22 |  | 15 | 1 | SUR
Building Services
1 | 0127 |  | Vendor Information For Licensed Plumber for Site Office (M-Stars Engineering & Construction Pte Ltd) | 131236-WIL00-VI-B-0001 | 0 | Fadhli Muiz | 2026-08-25 | 20 | 2026-09-14 | 2026-08-29 | 4 | -16 | NTS | APP | NO
2 | 0096 |  | Vendor Information For Electric Lift Works (XJ Elevator Private Limited) | 131236-WIL22-VI-B-0001 | 0 | Aizuddin Rahman | 2026-07-10 | 20 | 2026-07-30 | 2026-07-30 | 20 | 0 | RTR | REJ | YES
3 | 0109 |  | Vendor Information for Addressable Fire Alarm System (Acclaim System Private Limited) | 131236-WSW46-VI-B-0001 | 0 | Alif Aizuddin | 2026-07-31 | 20 | 2026-08-20 | 2026-08-28 | 28 | 8 | RTR | REJ | YES
4 | 0110 |  | Vendor Information for Two-Way Emergency Voice Communication System (Acclaim System Private Limited) | 131236-WSW46-VI-B-0002 | 0 | Alif Aizuddin | 2026-07-31 | 20 | 2026-08-20 | 2026-08-28 | 28 | 8 | RTR | REJ | YES
5 | 0111 |  | Vendor Information for Gas Suppression System (Federal Fire Engineering Pte Ltd) | 131236-WSW46-VI-B-0003 | 0 | Alif Aizuddin | 2026-08-06 | 20 | 2026-08-26 | 2026-08-28 | 22 | 2 | RTR | REJ | YES
6 | 0160 |  | Vendor Information for Water-cooled Chiller (Midea (Singapore) Product Pte. Ltd.) | 131236-WSW46-VI-B-0004 | 0 | Alif Aizuddin | 2026-10-01 | 20 | 2026-10-21 | 2026-10-07 | 6 | -14 | RTR | NAP | YES
7 | 0175 |  | Vendor Information for Fire Protection, Detection and Alarm System Contractor (Decarb Engineering & Construction Pte. Ltd.) | 131236-WSW46-VI-B-0005 | 0 |  | 2026-10-08 | 20 | 2026-10-28 |  | 15 | -5 | SUR
8 | 00096 | 0096-1 | Vendor Information For Electric Lift Works (XJ Elevator Private Limited) | 131236-WIL22-VI-B-0001 | 1 | Aizuddin Rahman | 2026-09-15 | 14 | 2026-09-29 | 2026-09-23 | 8 | -6 | RTR | REJ | YES
Formulas:
Target Return Date = [Submission Date]+[Review Period]
Review Turnaround Days = IF(NOT(ISBLANK([Actual Return Date])),[Actual Return Date]-[Submission Date],TODAY()-[Submission Date])

## Code
Project Metadata Title | Project Metadata Values | Project Metadata Data Type | Submission Status Code | Submission Status | Approval Code | Approval Status | Error Code | Group | Rule | Severity
Project Title | TWRP C3B2 | Text | SUR | Submitted Under SO Review | REJ | Rejected | V-01 | A | Document No. (M) blank on an otherwise populated row | Warning
Project Code | C3B2 | Text | RTR | SO Reviewed Pending Resubmission | NAP | Not Approved | V-02 | A | Stage (B) not in Code!E list | Error
Client | PUB | Text | NTS | Resubmission Not Required | APP | Approved without Comments | V-03 | A | UESH Discipline (C) not in Code!H list | Error
Consultant | Jacobs | Text |  |  | AWC | Approved with Comments | V-04 | A | Discipline Code (J) not in Code!T list (client discipline code) | Warning
Project Start Date | 2026-03-15 | Date |  |  | INF | For Information Only | V-05 | A | Doc Type (I) not in Code!Q list | Warning
Header Row | 1 | Int |  |  |  |  | V-06 | A | Authority (Q) not in Code!Z list | Warning
List End Row | 20000 | Int |  |  |  |  | V-07 | A | Prolog Submission Status (W) not in Code!AC list | Warning
First Client Review | 20 | Int |  |  |  |  | V-08 | A | Latest Approval Status (Y) not in the Approval Code block (Code!AF, read at runtime) and not blank | Error
Subsequent Client Review | 14 | Int |  |  |  |  | V-09 | D | Date order: Planned (S) ≤ Forecast (T) ≤ Actual (U) | Warning
Resubmission Duration | 14 | Int |  |  |  |  | V-10 | A | As-Built (P) = YES but Actual 1st Issue Date (U) blank | Warning
SNo. | Column-A | Int |  |  |  |  | V-11 | C | Approval Status = APP but Latest Approval Date (X) blank | Warning
Prolog No. | Column-B | Text |  |  |  |  | V-12 | A | Stage = Deleted/Void/Superseded but still counted as active (should be excluded) | Info
Prolog Rev | Column-C | Text |  |  |  |  | V-13 | A | Empty lookup code column while description column has values (mirrors PPP V-22) | Warning
Prolog Subject | Column-D | Text |  |  |  |  | V-14 | A | Project Code (G) not in Code!K list (WBS Contract Code) | Warning
Document No. | Column-E | Text |  |  |  |  | V-15 | A | Document No. (M) contains a placeholder/xxxx (on-hold number) — the row record is still valid; Warning only (applies to active rows, §3.7; does not fail V-17 since composition uses the actual K value) | Warning
Revision | Column-F | Text |  |  |  |  | V-16 | C | Prolog Submission Status (W) = RTR but Latest Approval Status (Y) blank/VOID (approval expected) | Warning
Submitted By | Column-G | Text |  |  |  |  | V-17 | B | Document No. (M) must equal ProjectCode-Prefix-DocType-DisciplineCode-Number = G-H-I-J-K joined by - (universal project rule; the Discipline segment is the client Discipline Code = col J, validated against Code!T — not UESH Discipline col C) | Error
Submission Date | Column-H | Date |  |  |  |  | V-18 | C | Actual 1st Issue Date (U = 1st submission date) non-blank ⇒ Prolog Number (V) and Prolog Submission Status (W) must be non-blank (submitted ⇒ transmittal session exists) | Error
Review Period | Column-I | Int |  |  |  |  | V-19 | B | Prolog Submission Status (W) non-blank ⇔ Prolog Number (V) non-blank (two-way) | Warning
Target Return Date | Column-J | Date |  |  |  |  | V-20 | C | Approval Status (Y) has a conclusion (APP/AWC/REJ/NAP) ⇒ Actual (U) non-blank and Latest Approval Date (X) non-blank | Error
Actual Return Date | Column-K | Date |  |  |  |  | V-21 | C | Latest Approval Date (X) non-blank ⇒ Y non-blank and X ≥ U | Warning
Review Turnaround Days | Column-L | Int |  |  |  |  | V-22 | D | Actual (U) non-blank ⇒ Planned (S) & Forecast (T) non-blank | Warning
Delay Days | Column-M | Int |  |  |  |  | V-23 | D | Future-date check — only Actual 1st Issue Date (U) and Latest Approval Date (X) must not be later than the current system date (a document's actual submission / approval must already have occurred — data lag / impossible future actual). Planned (S) and Forecast (T) are forward-looking and MAY legitimately be later than today — they are NOT flagged. | Warning
Approval Status | Column-N | Text |  |  |  |  | V-24 | E | BQ Number (E) non-blank ⇒ must exist in BQ sheet BQ No. column (blank E is allowed) | Warning
Resubmission Required | Column-O | Boolen |  |  |  |  | V-25 | F | Valid record (M non-blank) missing any required field: Document Title(N)/UESH Discipline(C)/Stage(B)/Doc Type(I)/Discipline Code(J)/Project Code(G)/Project Prefix(H)/Number(K) | Warning
Notes | Column-P | Text |  |  |  |  | V-26 | G | Document No. (M) duplicated within the consolidated table | Error
[7 empty] | V-27 | G | As-Built (P) / Vendor Data (R) must be YES/NO/blank; other values | Warning
[7 empty] | V-28 | D | Any Planned/Forecast/Actual 1st-issue date (S/T/U) earlier than the project start date (Code!B6) — document still counted/plotted on the Issue-Progress curve; flag for review | Warning
[7 empty] | V-29 | Referential | Submittal Log Document No. must exist in MDL scope; otherwise the row is an orphan | Warning
[7 empty] | V-30 | Timeline | Actual Return / Target Return must not precede Submission Date | Warning
[7 empty] | V-31 | Cross-field | Approval Status present while Submission Status = NFS; or Resubmission Required = Yes while Submission Status ? {RTR,REJ} | Warning