## MonthlySubmissions
Record Type | Month | Discipline | Stage | Doc Type | System | Project Prefix | Vendor Data | Document No. | Document Title | Submission Date | Target Return Date | Actual Return Date | Submitted By | Revision | Review Period Days | Review Turnaround Days | Review Delay Days | Submission Status | Approval Status | Resubmission Required | Timeliness | Prolog No. | Count Submitted | Count Planned | Flag Approved | Flag On Time | Flag Delayed | Flag Resubmission
Submitted | 2026-04-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0001 | Vendor Information For Pressure Gauge (BAUMER SINGAPORE PTE LTD) | 2026-04-13 | 2026-05-03 | 2026-05-15 | Ricky | 0 | 20 | 32 | 12 | NTS - No Resubmission Required | APP - Approved | NO | Delayed | 0028 | 1 | 0 | 1 | 0 | 1 | 0
Submitted | 2026-04-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0002 | Vendor Information For Cable Raceway (TRI-STAR INDUSTRIES PTE LTD) | 2026-04-15 | 2026-05-05 | 2026-05-25 | Ricky | 0 | 20 | 40 | 20 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | Delayed | 0031 | 1 | 0 | 1 | 0 | 1 | 1
Submitted | 2026-04-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0003 | Vendor Information For Temperature Transmitter c/w RTD (ENDRESS + HAUSER S.E.A. PTE LTD) | 2026-04-28 | 2026-05-18 | 2026-05-15 | Ricky | 0 | 20 | 17 | -3 | NTS - No Resubmission Required | APP - Approved | NO | On Time | 0037 | 1 | 0 | 1 | 1 | 0 | 0
Submitted | 2026-04-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0004 | Vendor Information For Pressure Transmitter (EMERSON ASIA PACIFIC PTE. LTD.) | 2026-04-29 | 2026-05-19 | 2026-05-15 | Ricky | 0 | 20 | 16 | -4 | RTR - Returned for Resubmission | APP - Approved | YES | On Time | 0038 | 1 | 0 | 1 | 1 | 0 | 1
Submitted | 2026-04-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0005 | Vendor Information For Level Transmitter Radar (Non-Contacting) (ENDRESS + HAUSER S.E.A. PTE LTD) | 2026-04-30 | 2026-05-20 | 2026-05-15 | Ricky | 0 | 20 | 15 | -5 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | On Time | 0040 | 1 | 0 | 1 | 1 | 0 | 1
Submitted | 2026-04-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0006 | Vendor Information For Pressure Switch(WIKA INSTRUMENTATION PTE. LTD.) | 2026-04-30 | 2026-05-20 | 2026-05-25 | Ricky | 0 | 20 | 25 | 5 | RTR - Returned for Resubmission | APP - Approved | YES | Delayed | 0041 | 1 | 0 | 1 | 0 | 1 | 1
Submitted | 2026-05-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0007 | Vendor Information For Level Transmitter – RF Admittance(ENDRESS + HAUSER S.E.A. PTE LTD) | 2026-05-08 | 2026-05-28 | 2026-05-15 | Ricky | 0 | 20 | 7 | -13 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | On Time | 0046 | 1 | 0 | 1 | 1 | 0 | 1
Submitted | 2026-05-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0008 | Vendor Information For Auto Sampler (ENDRESS + HAUSER S.E.A. PTE LTD) | 2026-05-11 | 2026-05-31 | 2026-05-25 | Ricky | 0 | 20 | 14 | -6 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | On Time | 0048 | 1 | 0 | 1 | 1 | 0 | 1
Submitted | 2026-05-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0009 | Vendor Information For Low Point Leak Detector (IFM ELECTRONIC PTE LTD) | 2026-05-12 | 2026-06-01 | 2026-05-25 | Ricky | 0 | 20 | 13 | -7 | RTR - Returned for Resubmission | APP - Approved | YES | On Time | 0050 | 1 | 0 | 1 | 1 | 0 | 1
Submitted | 2026-05-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0010 | Vendor Information For Thermal Mass Flowmeter (ENDRESS + HAUSER S.E.A. PTE LTD) | 2026-05-13 | 2026-06-02 | 2026-05-31 | Ricky | 0 | 20 | 18 | -2 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | On Time | 0051 | 1 | 0 | 1 | 1 | 0 | 1
Submitted | 2026-05-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0011 | Vendor Information For Thermal Flow Switch (ENDRESS + HAUSER S.E.A. PTE LTD) | 2026-05-14 | 2026-06-03 | 2026-05-31 | Ricky | 0 | 20 | 17 | -3 | NTS - No Resubmission Required | AWC - Approved with Comments | NO | On Time | 0055 | 1 | 0 | 1 | 1 | 0 | 0
Submitted | 2026-05-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0012 | Vendor Information For Turbidity Analyser (HACH WATER QUALITY SINGAPORE PTE LTD) | 2026-05-18 | 2026-06-07 | 2026-05-31 | Ricky | 0 | 20 | 13 | -7 | NTS - No Resubmission Required | AWC - Approved with Comments | NO | On Time | 0057 | 1 | 0 | 1 | 1 | 0 | 0
Submitted | 2026-05-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0013 | Vendor Information For Level Switch – Conductive Probe (ENDRESS + HAUSER S.E.A. PTE LTD) | 2026-05-26 | 2026-06-15 | 2026-06-03 | Ricky | 0 | 20 | 8 | -12 | NTS - No Resubmission Required | AWC - Approved with Comments | NO | On Time | 0063 | 1 | 0 | 1 | 1 | 0 | 0
Submitted | 2026-05-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0014 | Vendor Information For pH Analyser (EMERSON ASIA PACIFIC PTE. LTD.) | 2026-05-28 | 2026-06-17 | 2026-06-22 | Ricky | 0 | 20 | 25 | 5 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | Delayed | 0067 | 1 | 0 | 1 | 0 | 1 | 1
Submitted | 2026-07-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0015 | Vendor Information For Room Temperature Sensor (KELE & ASSOCIATES PTE LTD - VAISALA) | 2026-07-16 | 2026-08-05 | 2026-07-29 | Ricky | 0 | 20 | 13 | -7 | NTS - No Resubmission Required | AWC - Approved with Comments | NO | On Time | 0102 | 1 | 0 | 1 | 1 | 0 | 0
Submitted | 2026-08-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0016 | Vendor Information For Local Display (ENDRESS + HAUSER S.E.A. PTE LTD) | 2026-08-13 | 2026-09-02 | 2026-08-28 | Ricky | 0 | 20 | 15 | -5 | NTS - No Resubmission Required | AWC - Approved with Comments | NO | On Time | 0115 | 1 | 0 | 1 | 1 | 0 | 0
Submitted | 2026-09-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0017 | Vendor Information For Cable (LV Power, Signal & Control) (C-KINGDOM CABLE TECHNOLOGY CO., LTD.) | 2026-09-21 | 2026-10-11 |  | Ricky | 0 | 20 | 23 | 3 | SUR - Under SO Review | Pending Review | Pending | Delayed | 0151 | 1 | 0 |  | 0 | 1
Submitted | 2026-09-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0018 | Vendor Information For SS316 Tube Fittings (YANGZHONG SINYA AUTO-CONTROL ENGINEERING CO.,LTD.) | 2026-09-21 | 2026-10-11 |  | Ricky | 0 | 20 | 23 | 3 | SUR - Under SO Review | Pending Review | Pending | Delayed | 0152 | 1 | 0 |  | 0 | 1
Submitted | 2026-09-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0019 | Vendor Information For Cable (LV Power, Signal & Control)(KEI INDUSTRIES LTD) | 2026-09-29 | 2026-10-19 |  | Ricky | 0 | 20 | 15 | -5 | SUR - Under SO Review | Pending Review | Pending | On Time | 0159 | 1 | 0 |  | 1 | 0
Submitted | 2026-10-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0020 | Vendor Information For Flowmeter - Electromagnetic (ENDRESS + HAUSER S.E.A. PTE LTD) | 2026-10-03 | 2026-10-23 |  | Ricky | 0 | 20 | 11 | -9 | SUR - Under SO Review | Pending Review | Pending | On Time | 166 | 1 | 0 |  | 1 | 0
Submitted | 2026-04-01 | ICA | Stage 1 | VI |  | WIL21 | YES | 131236-WIL21-VI-I-0001 | Vendor Information For Hydrogen Sulfide Gas Detector (DRAEGER SINGAPORE PTE LTD) | 2026-04-17 | 2026-05-07 | 2026-05-15 | Ricky | 0 | 20 | 28 | 8 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | Delayed | 0033 | 1 | 0 | 1 | 0 | 1 | 1
Submitted | 2026-04-01 | ICA | Stage 1 | VI |  | WIL21 | YES | 131236-WIL21-VI-I-0002 | Vendor Information For Carbon Monoxide Gas Detector (DRAEGER SINGAPORE PTE LTD) | 2026-04-17 | 2026-05-07 | 2026-05-15 | Ricky | 0 | 20 | 28 | 8 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | Delayed | 0034 | 1 | 0 | 1 | 0 | 1 | 1
Submitted | 2026-04-01 | ICA | Stage 1 | VI |  | WIL21 | YES | 131236-WIL21-VI-I-0003 | Vendor Information For Flammable (LEL) Gas Detector (DRAEGER SINGAPORE PTE LTD) | 2026-04-17 | 2026-05-07 | 2026-05-15 | Ricky | 0 | 20 | 28 | 8 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | Delayed | 0035 | 1 | 0 | 1 | 0 | 1 | 1
Submitted | 2026-04-01 | ICA | Stage 1 | VI |  | WIL21 | YES | 131236-WIL21-VI-I-0004 | Vendor Information For Weight Transmitter (METTLER – TOLEDO (S) PTE LTD) | 2026-04-28 | 2026-05-18 | 2026-05-31 | Ricky | 0 | 20 | 33 | 13 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | Delayed | 0036 | 1 | 0 | 1 | 0 | 1 | 1
Submitted | 2026-05-01 | ICA | Stage 1 | VI |  | WIL21 | YES | 131236-WIL21-VI-I-0005 | Vendor Information For Toxicity Analyser (AI ANALYTICAL PTE LTD) | 2026-05-26 | 2026-06-15 | 2026-06-03 | Ricky | 0 | 20 | 8 | -12 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | On Time | 0061 | 1 | 0 | 1 | 1 | 0 | 1
Submitted | 2026-05-01 | ICA | Stage 1 | VI |  | WIL21 | YES | 131236-WIL21-VI-I-0006 | Vendor Information For Motion Switch (IFM ELECTRONIC PTE LTD) | 2026-05-26 | 2026-06-15 | 2026-06-04 | Ricky | 0 | 20 | 9 | -11 | RTR - Returned for Resubmission | APP - Approved | YES | On Time | 0062 | 1 | 0 | 1 | 1 | 0 | 1
Submitted | 2026-06-01 | ICA | Stage 1 | VI |  | WIL21 | YES | 131236-WIL21-VI-I-0007 | Vendor Information For Volatile Organic Compound (VOC) Gas Analyser (HONEYWELL RAE SYSTEMS) | 2026-06-03 | 2026-06-23 | 2026-06-11 | Ricky | 0 | 20 | 8 | -12 | RTR - Returned for Resubmission | APP - Approved | YES | On Time | 0072 | 1 | 0 | 1 | 1 | 0 | 1
Submitted | 2026-05-01 | ICA | Stage 1 | VI |  | WIL22 | YES | 131236-WIL22-VI-I-0001 | Vendor Information For Total Solid Analyser (VALMET - WETEC PTE LTD) | 2026-05-12 | 2026-06-01 | 2026-05-15 | Ricky | 0 | 20 | 3 | -17 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | On Time | 0049 | 1 | 0 | 1 | 1 | 0 | 1
Submitted | 2026-06-01 | ICA | Stage 1 | VI |  | WIL22 | YES | 131236-WIL22-VI-I-0002 | Vendor Information For Level Switch Sludge Blanket – Ultrasonic (PULSAR – MAESTRO ASIA) | 2026-06-09 | 2026-06-29 | 2026-06-28 | Ricky | 0 | 20 | 19 | -1 | RTR - Returned for Resubmission | APP - Approved | YES | On Time | 0078 | 1 | 0 | 1 | 1 | 0 | 1
Submitted | 2026-05-01 | ICA | Stage 1 | VI |  | WIL23 | YES | 131236-WIL23-VI-I-0001 | Vendor Information For Level Switch – Tuning Fork (ENDRESS + HAUSER S.E.A. PTE LTD) | 2026-05-04 | 2026-05-24 | 2026-06-19 | Ricky | 0 | 20 | 46 | 26 | RTR - Returned for Resubmission | APP - Approved | YES | Delayed | 0042 | 1 | 0 | 1 | 0 | 1 | 1
Submitted | 2026-05-01 | ICA | Stage 1 | VI |  | WIL23 | YES | 131236-WIL23-VI-I-0002 | Vendor Information For Orthophosphate Analyser(ENDRESS + HAUSER S.E.A. PTE LTD) | 2026-05-06 | 2026-05-26 | 2026-05-15 | Ricky | 0 | 20 | 9 | -11 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | On Time | 0043 | 1 | 0 | 1 | 1 | 0 | 1
Submitted | 2026-05-01 | ICA | Stage 1 | VI |  | WIL23 | YES | 131236-WIL23-VI-I-0003 | Vendor Information For Conductivity Analyser(ENDRESS + HAUSER S.E.A. PTE LTD) | 2026-05-08 | 2026-05-28 | 2026-05-15 | Ricky | 0 | 20 | 7 | -13 | RTR - Returned for Resubmission | APP - Approved | YES | On Time | 0045 | 1 | 0 | 1 | 1 | 0 | 1
Submitted | 2026-05-01 | ICA | Stage 1 | VI |  | WIL23 | YES | 131236-WIL23-VI-I-0004 | Vendor Information For ORP Analyser(YOKOGAWA ENGINEERING ASIA PTE LTD) | 2026-05-11 | 2026-05-31 | 2026-05-15 | Ricky | 0 | 20 | 4 | -16 | RTR - Returned for Resubmission | APP - Approved | YES | On Time | 0047 | 1 | 0 | 1 | 1 | 0 | 1
Submitted | 2026-05-01 | ICA | Stage 1 | VI |  | WIL23 | YES | 131236-WIL23-VI-I-0005 | Vendor Information For Total Suspended Solid (MLSS) Analyser (HACH WATER QUALITY SINGAPORE PTE LTD) | 2026-05-26 | 2026-06-15 | 2026-06-03 | Ricky | 0 | 20 | 8 | -12 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | On Time | 0059 | 1 | 0 | 1 | 1 | 0 | 1
Submitted | 2026-05-01 | ICA | Stage 1 | VI |  | WIL23 | YES | 131236-WIL23-VI-I-0006 | Vendor Information For Ammonia Analyser (HACH WATER QUALITY SINGAPORE PTE LTD) | 2026-05-26 | 2026-06-15 | 2026-06-03 | Ricky | 0 | 20 | 8 | -12 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | On Time | 0060 | 1 | 0 | 1 | 1 | 0 | 1
Submitted | 2026-05-01 | ICA | Stage 1 | VI |  | WIL23 | YES | 131236-WIL23-VI-I-0007 | Vendor Information For Dissolved Oxygen Analyser (EMERSON ASIA PACIFIC PTE. LTD.) | 2026-05-28 | 2026-06-17 | 2026-06-22 | Ricky | 0 | 20 | 25 | 5 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | Delayed | 0068 | 1 | 0 | 1 | 0 | 1 | 1
Submitted | 2026-05-01 | ICA | Stage 1 | VI |  | WIL23 | YES | 131236-WIL23-VI-I-0008 | Vendor Information For Nitrate / Nitrite Analyser (HACH WATER QUALITY SINGAPORE PTE LTD) | 2026-05-28 | 2026-06-17 | 2026-06-28 | Ricky | 0 | 20 | 31 | 11 | RTR - Returned for Resubmission | REJ - Rejected | YES | Delayed | 0069 | 1 | 0 | 0 | 0 | 1 | 1
Submitted | 2026-04-01 | ICA | Stage 1 | VI |  | WNS03 | YES | 131236-WNS03-VI-I-0001 | Vendor Information For Differential Pressure Transmitter (EMERSON ASIA PACIFIC PTE. LTD.) | 2026-04-29 | 2026-05-19 | 2026-05-15 | Ricky | 0 | 20 | 16 | -4 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | On Time | 0039 | 1 | 0 | 1 | 1 | 0 | 1
Submitted | 2026-07-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0002 | Vendor Information For Cable Raceway (TRI-STAR INDUSTRIES PTE LTD) | 2026-07-08 | 2026-07-22 | 2026-07-17 | Ricky | 1 | 14 | 9 | -5 | NTS - No Resubmission Required | APP - Approved | NO | On Time | 00031 | 1 | 0 | 1 | 1 | 0 | 0
Submitted | 2026-08-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0002 | Vendor Information For Cable Raceway (TRI-STAR INDUSTRIES PTE LTD) | 2026-08-25 | 2026-09-08 | 2026-09-01 | Ricky | 2 | 14 | 7 | -7 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | On Time | 00031 | 1 | 0 | 1 | 1 | 0 | 1
Submitted | 2026-06-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0004 | Vendor Information For Pressure Transmitter (EMERSON ASIA PACIFIC PTE. LTD.) | 2026-06-12 | 2026-06-26 | 2026-06-22 | Ricky | 1 | 14 | 10 | -4 | NTS - No Resubmission Required | APP - Approved | NO | On Time | 00038 | 1 | 0 | 1 | 1 | 0 | 0
Submitted | 2026-06-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0005 | Vendor Information For Level Transmitter Radar (Non-Contacting) (ENDRESS + HAUSER S.E.A. PTE LTD) | 2026-06-03 | 2026-06-17 | 2026-06-11 | Ricky | 1 | 14 | 8 | -6 | NTS - No Resubmission Required | APP - Approved | NO | On Time | 00040 | 1 | 0 | 1 | 1 | 0 | 0
Submitted | 2026-07-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0006 | Vendor Information For Pressure Switch(WIKA INSTRUMENTATION PTE. LTD.) | 2026-07-10 | 2026-07-24 | 2026-08-06 | Ricky | 1 | 14 | 27 | 13 | NTS - No Resubmission Required | APP - Approved | NO | Delayed | 00041 | 1 | 0 | 1 | 0 | 1 | 0
Submitted | 2026-05-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0007 | Vendor Information For Level Transmitter – RF Admittance(ENDRESS + HAUSER S.E.A. PTE LTD) | 2026-05-18 | 2026-06-01 | 2026-05-31 | Ricky | 1 | 14 | 13 | -1 | NTS - No Resubmission Required | APP - Approved | NO | On Time | 00046 | 1 | 0 | 1 | 1 | 0 | 0
Submitted | 2026-06-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0008 | Vendor Information For Auto Sampler (ENDRESS + HAUSER S.E.A. PTE LTD) | 2026-06-12 | 2026-06-26 | 2026-06-22 | Ricky | 1 | 14 | 10 | -4 | NTS - No Resubmission Required | APP - Approved | NO | On Time | 00048 | 1 | 0 | 1 | 1 | 0 | 0
Submitted | 2026-06-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0009 | Vendor Information For Low Point Leak Detector (IFM ELECTRONIC PTE LTD) | 2026-06-12 | 2026-06-26 | 2026-07-01 | Ricky | 1 | 14 | 19 | 5 | NTS - No Resubmission Required | APP - Approved | NO | Delayed | 00050 | 1 | 0 | 1 | 0 | 1 | 0
Submitted | 2026-06-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0010 | Vendor Information For Thermal Mass Flowmeter (ENDRESS + HAUSER S.E.A. PTE LTD) | 2026-06-09 | 2026-06-23 | 2026-07-01 | Ricky | 1 | 14 | 22 | 8 | NTS - No Resubmission Required | APP - Approved | NO | Delayed | 00051 | 1 | 0 | 1 | 0 | 1 | 0
Submitted | 2026-07-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0014 | Vendor Information For pH Analyser (EMERSON ASIA PACIFIC PTE. LTD.) | 2026-07-08 | 2026-07-22 | 2026-07-17 | Ricky | 1 | 14 | 9 | -5 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | On Time | 00067 | 1 | 0 | 1 | 1 | 0 | 1
Submitted | 2026-08-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0014 | Vendor Information For pH Analyser (EMERSON ASIA PACIFIC PTE. LTD.) | 2026-08-14 | 2026-08-28 | 2026-08-28 | Ricky | 2 | 14 | 14 | 0 | NTS - No Resubmission Required | APP - Approved | NO | On Time | 00067 | 1 | 0 | 1 | 1 | 0 | 0
Submitted | 2026-05-01 | ICA | Stage 1 | VI |  | WIL21 | YES | 131236-WIL21-VI-I-0001 | Vendor Information For Hydrogen Sulfide Gas Detector (DRAEGER SINGAPORE PTE LTD) | 2026-05-29 | 2026-06-12 | 2026-06-11 | Ricky | 1 | 14 | 13 | -1 | NTS - No Resubmission Required | APP - Approved | NO | On Time | 00033 | 1 | 0 | 1 | 1 | 0 | 0
Submitted | 2026-05-01 | ICA | Stage 1 | VI |  | WIL21 | YES | 131236-WIL21-VI-I-0002 | Vendor Information For Carbon Monoxide Gas Detector (DRAEGER SINGAPORE PTE LTD) | 2026-05-29 | 2026-06-12 | 2026-06-22 | Ricky | 1 | 14 | 24 | 10 | NTS - No Resubmission Required | APP - Approved | NO | Delayed | 00034 | 1 | 0 | 1 | 0 | 1 | 0
Submitted | 2026-05-01 | ICA | Stage 1 | VI |  | WIL21 | YES | 131236-WIL21-VI-I-0003 | Vendor Information For Flammable (LEL) Gas Detector (DRAEGER SINGAPORE PTE LTD) | 2026-05-29 | 2026-06-12 | 2026-06-22 | Ricky | 1 | 14 | 24 | 10 | NTS - No Resubmission Required | APP - Approved | NO | Delayed | 00035 | 1 | 0 | 1 | 0 | 1 | 0
Submitted | 2026-06-01 | ICA | Stage 1 | VI |  | WIL21 | YES | 131236-WIL21-VI-I-0004 | Vendor Information For Weight Transmitter (METTLER – TOLEDO (S) PTE LTD) | 2026-06-22 | 2026-07-06 | 2026-07-07 | Ricky | 1 | 14 | 15 | 1 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | Delayed | 00036 | 1 | 0 | 1 | 0 | 1 | 1
Submitted | 2026-07-01 | ICA | Stage 1 | VI |  | WIL21 | YES | 131236-WIL21-VI-I-0005 | Vendor Information For Toxicity Analyser (AI ANALYTICAL PTE LTD) | 2026-07-10 | 2026-07-24 | 2026-07-27 | Ricky | 1 | 14 | 17 | 3 | NTS - No Resubmission Required | APP - Approved | NO | Delayed | 00061 | 1 | 0 | 1 | 0 | 1 | 0
Submitted | 2026-06-01 | ICA | Stage 1 | VI |  | WIL21 | YES | 131236-WIL21-VI-I-0007 | Vendor Information For Volatile Organic Compound (VOC) Gas Analyser (HONEYWELL RAE SYSTEMS) | 2026-06-22 | 2026-07-06 | 2026-07-07 | Ricky | 1 | 14 | 15 | 1 | NTS - No Resubmission Required | APP - Approved | NO | Delayed | 00072 | 1 | 0 | 1 | 0 | 1 | 0
Submitted | 2026-06-01 | ICA | Stage 1 | VI |  | WIL22 | YES | 131236-WIL22-VI-I-0001 | Vendor Information For Total Solid Analyser (VALMET - WETEC PTE LTD) | 2026-06-03 | 2026-06-17 | 2026-06-11 | Ricky | 1 | 14 | 8 | -6 | NTS - No Resubmission Required | APP - Approved | NO | On Time | 00049 | 1 | 0 | 1 | 1 | 0 | 0
Submitted | 2026-07-01 | ICA | Stage 1 | VI |  | WIL23 | YES | 131236-WIL23-VI-I-0001 | Vendor Information For Level Switch – Tuning Fork (ENDRESS + HAUSER S.E.A. PTE LTD) | 2026-07-10 | 2026-07-24 | 2026-07-27 | Ricky | 1 | 14 | 17 | 3 | NTS - No Resubmission Required | APP - Approved | NO | Delayed | 00042 | 1 | 0 | 1 | 0 | 1 | 0
Submitted | 2026-06-01 | ICA | Stage 1 | VI |  | WIL23 | YES | 131236-WIL23-VI-I-0002 | Vendor Information For Orthophosphate Analyser(ENDRESS + HAUSER S.E.A. PTE LTD) | 2026-06-03 | 2026-06-17 | 2026-06-11 | Ricky | 1 | 14 | 8 | -6 | NTS - No Resubmission Required | APP - Approved | NO | On Time | 00043 | 1 | 0 | 1 | 1 | 0 | 0
Submitted | 2026-06-01 | ICA | Stage 1 | VI |  | WIL23 | YES | 131236-WIL23-VI-I-0003 | Vendor Information For Conductivity Analyser(ENDRESS + HAUSER S.E.A. PTE LTD) | 2026-06-03 | 2026-06-17 | 2026-06-11 | Ricky | 1 | 14 | 8 | -6 | NTS - No Resubmission Required | APP - Approved | NO | On Time | 00045 | 1 | 0 | 1 | 1 | 0 | 0
Submitted | 2026-05-01 | ICA | Stage 1 | VI |  | WIL23 | YES | 131236-WIL23-VI-I-0004 | Vendor Information For ORP Analyser(YOKOGAWA ENGINEERING ASIA PTE LTD) | 2026-05-18 | 2026-06-01 | 2026-05-31 | Ricky | 1 | 14 | 13 | -1 | NTS - No Resubmission Required | APP - Approved | NO | On Time | 00047 | 1 | 0 | 1 | 1 | 0 | 0
Submitted | 2026-07-01 | ICA | Stage 1 | VI |  | WIL23 | YES | 131236-WIL23-VI-I-0006 | Vendor Information For Ammonia Analyser (HACH WATER QUALITY SINGAPORE PTE LTD) | 2026-07-10 | 2026-07-24 | 2026-07-27 | Ricky | 1 | 14 | 17 | 3 | NTS - No Resubmission Required | APP - Approved | NO | Delayed | 00060 | 1 | 0 | 1 | 0 | 1 | 0
Submitted | 2026-07-01 | ICA | Stage 1 | VI |  | WIL23 | YES | 131236-WIL23-VI-I-0007 | Vendor Information For Dissolved Oxygen Analyser (EMERSON ASIA PACIFIC PTE. LTD.) | 2026-07-08 | 2026-07-22 | 2026-07-16 | Ricky | 1 | 14 | 8 | -6 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | On Time | 00068 | 1 | 0 | 1 | 1 | 0 | 1
Submitted | 2026-08-01 | ICA | Stage 1 | VI |  | WIL23 | YES | 131236-WIL23-VI-I-0007 | Vendor Information For Dissolved Oxygen Analyser (EMERSON ASIA PACIFIC PTE. LTD.) | 2026-08-14 | 2026-08-28 | 2026-08-28 | Ricky | 2 | 14 | 14 | 0 | NTS - No Resubmission Required | APP - Approved | NO | On Time | 00068 | 1 | 0 | 1 | 1 | 0 | 0
Submitted | 2026-07-01 | ICA | Stage 1 | VI |  | WIL23 | YES | 131236-WIL23-VI-I-0008 | Vendor Information For Nitrate / Nitrite Analyser (HACH WATER QUALITY SINGAPORE PTE LTD) | 2026-07-09 | 2026-07-23 | 2026-08-06 | Ricky | 1 | 14 | 28 | 14 | RTR - Returned for Resubmission | REJ - Rejected | YES | Delayed | 00069 | 1 | 0 | 0 | 0 | 1 | 1
Submitted | 2026-06-01 | ICA | Stage 1 | VI |  | WNS03 | YES | 131236-WNS03-VI-I-0001 | Vendor Information For Differential Pressure Transmitter (EMERSON ASIA PACIFIC PTE. LTD.) | 2026-06-12 | 2026-06-26 | 2026-06-22 | Ricky | 1 | 14 | 10 | -4 | NTS - No Resubmission Required | APP - Approved | NO | On Time | 00039 | 1 | 0 | 1 | 1 | 0 | 0
Submitted | 2026-09-01 | ICA | Stage 2 | SH |  | WSW46 | NO | 131236-WSW46-SH-I-0001 | Instrument Master List | 2026-09-23 | 2026-10-13 |  | Ricky | 0 | 20 | 21 | 1 | SUR - Under SO Review | Pending Review | Pending | Delayed | 0158 | 1 | 0 |  | 0 | 1
Submitted | 2026-10-01 | ICA | Stage 2 | SH |  | WSW46 | YES | 131236-WSW46-SH-I-0002 | Detailed Engineering FOIP (Fiber Optic Interface Panel) & FOBOT (Fiber Optic Break-Out Tray) Master List | 2026-10-06 | 2026-10-26 |  | Ricky | 0 | 20 | 8 | -12 | SUR - Under SO Review | Pending Review | Pending | On Time | 0171 | 1 | 0 |  | 1 | 0
Submitted | 2026-10-01 | ICA | Stage 2 | SH |  | WSW46 | YES | 131236-WSW46-SH-I-0003 | Detailed Engineering UPSDB Master List | 2026-10-06 | 2026-10-26 |  | Ricky | 0 | 20 | 8 | -12 | SUR - Under SO Review | Pending Review | Pending | On Time | 0172 | 1 | 0 |  | 1 | 0
Submitted | 2026-10-01 | ICA | Stage 2 | SH |  | WSW46 | NO | 131236-WSW46-SH-I-0004 | RIO Panel Master List | 2026-10-07 | 2026-10-27 |  | Ricky | 0 | 20 | 7 | -13 | SUR - Under SO Review | Pending Review | Pending | On Time | 174 | 1 | 0 |  | 1 | 0
Submitted | 2026-06-01 | ICA | Stage 2 | DS |  | WIL21 | YES | 131236-WIL21-DS-I-0001 | Datasheet For Flammable (LEL) Gas Detector (DRAEGER SINGAPORE PTE LTD) | 2026-06-25 | 2026-07-15 | 2026-07-17 | Ricky | 0 | 20 | 22 | 2 | NTS - No Resubmission Required | AWC - Approved with Comments | NO | Delayed | 0083 | 1 | 0 | 1 | 0 | 1 | 0
Submitted | 2026-06-01 | ICA | Stage 2 | DS |  | WIL21 | YES | 131236-WIL21-DS-I-0002 | Datasheet For CO Gas Detector (DRAEGER SINGAPORE PTE LTD) | 2026-06-25 | 2026-07-15 | 2026-07-28 | Ricky | 0 | 20 | 33 | 13 | NTS - No Resubmission Required | AWC - Approved with Comments | NO | Delayed | 0084 | 1 | 0 | 1 | 0 | 1 | 0
Submitted | 2026-07-01 | ICA | Stage 2 | DS |  | WIL21 | YES | 131236-WIL21-DS-I-0003 | Datasheet For H2S Gas Detector (DRAEGER SINGAPORE PTE LTD) | 2026-07-17 | 2026-08-06 | 2026-08-06 | Ricky | 0 | 20 | 20 | 0 | NTS - No Resubmission Required | AWC - Approved with Comments | NO | On Time | 0105 | 1 | 0 | 1 | 1 | 0 | 0
Submitted | 2026-07-01 | ICA | Stage 2 | DS |  | WIL21 | YES | 131236-WIL21-DS-I-0004 | Datasheet For Motion Switch (IFM ELECTRONIC PTE LTD) | 2026-07-17 | 2026-08-06 | 2026-08-06 | Ricky | 0 | 20 | 20 | 0 | RTR - Returned for Resubmission | NAP - Not Approved | YES | On Time | 0106 | 1 | 0 | 0 | 1 | 0 | 1
Submitted | 2026-08-01 | ICA | Stage 2 | DS |  | WIL21 | YES | 131236-WIL21-DS-I-0005 | Datasheet For Weight Transmitter with Load Cell (METTLER TOLEDO (S) PTE. LTD.) | 2026-08-13 | 2026-09-02 | 2026-08-28 | Ricky | 0 | 20 | 15 | -5 | RTR - Returned for Resubmission | NAP - Not Approved | YES | On Time | 0116 | 1 | 0 | 0 | 1 | 0 | 1
Submitted | 2026-08-01 | ICA | Stage 2 | DS |  | WIL23 | YES | 131236-WIL23-DS-I-0001 | Datasheet For ORP Analyser (YOKOGAWA ENGINEERING ASIA PTE LTD) | 2026-08-27 | 2026-09-16 | 2026-09-22 | Ricky | 0 | 20 | 26 | 6 | NTS - No Resubmission Required | APP - Approved | NO | Delayed | 0134 | 1 | 0 | 1 | 0 | 1 | 0
Submitted | 2026-07-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-0001 | Datasheet For Low Point Leak Detector (IFM ELECTRONIC PTE LTD) | 2026-07-17 | 2026-08-06 | 2026-07-29 | Ricky | 0 | 20 | 12 | -8 | NTS - No Resubmission Required | APP - Approved | NO | On Time | 0104 | 1 | 0 | 1 | 1 | 0 | 0
Submitted | 2026-08-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-0002 | Datasheet For pH Analyser (EMERSON ASIA PACIFIC PTE. LTD.) | 2026-08-28 | 2026-09-17 | 2026-09-22 | Ricky | 0 | 20 | 25 | 5 | RTR - Returned for Resubmission | NAP - Not Approved | YES | Delayed | 0135 | 1 | 0 | 0 | 0 | 1 | 1
Submitted | 2026-08-01 | ICA | Stage 2 | DR |  | WNS03 | NO | 131236-WNS03-DR-I-7000 | INSTRUMENT HOOKUP DRAWINGS FOR DIFFERENTIAL PRESSURE TRANSMITTER (SHEET 1 OF 1) | 2026-08-26 | 2026-09-15 | 2026-09-22 | Ricky | 0 | 20 | 27 | 7 | NTS - No Resubmission Required | AWC - Approved with Comments | NO | Delayed | 0131 | 1 | 0 | 1 | 0 | 1 | 0
Submitted | 2026-08-01 | ICA | Stage 2 | DS |  | WIL21 | YES | 131236-WIL21-DS-I-0006 | Datasheet For Weight Transmitter (METTLER – TOLEDO (S) PTE LTD) | 2026-08-13 | 2026-09-02 | 2026-08-06 | Ricky | 0 | 20 | -7 | -27 | RTR - Returned for Resubmission | NAP - Not Approved | YES | On Time | 116 | 1 | 0 | 0 | 1 | 0 | 1
Submitted | 2026-07-01 | Electrical | Stage 1 | VI |  | WSW46 | NO | 131236-WSW46-VI-E-0001 | Vendor Information For Electrical Power Transformer & Distribution Transformer (TECO ELECTRIC & MACHINERY PTE LTD) | 2026-07-08 | 2026-07-28 | 2026-07-27 | Ammar | 0 | 20 | 19 | -1 | RTR - Returned for Resubmission | NAP - Not Approved | YES | On Time | 0094 | 1 | 0 | 0 | 1 | 0 | 1
Submitted | 2026-07-01 | Electrical | Stage 1 | VI |  | WSW46 | NO | 131236-WSW46-VI-E-0002 | Vendor Information For Electrical High Voltage Switchgear Panel (SCHNEIDER ELECTRIC PTE LTD) | 2026-07-08 | 2026-07-28 | 2026-07-27 | Ammar | 0 | 20 | 19 | -1 | RTR - Returned for Resubmission | NAP - Not Approved | YES | On Time | 0095 | 1 | 0 | 0 | 1 | 0 | 1
Submitted | 2026-07-01 | Electrical | Stage 1 | VI |  | WSW46 | NO | 131236-WSW46-VI-E-0003 | Vendor Information For Low Voltage Electrical Equipment Works (SUNLIGHT ELECTRICAL PTE LTD) | 2026-07-15 | 2026-08-04 | 2026-07-27 | Ammar | 0 | 20 | 12 | -8 | RTR - Returned for Resubmission | NAP - Not Approved | YES | On Time | 0101 | 1 | 0 | 0 | 1 | 0 | 1
Submitted | 2026-08-01 | Electrical | Stage 1 | VI |  | WSW46 | NO | 131236-WSW46-VI-E-0004 | Vendor Information For Cable Raceway (TRI-STAR INDUSTRIES PTE LTD) | 2026-08-26 | 2026-09-15 | 2026-09-10 | Ammar | 0 | 20 | 15 | -5 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | On Time | 0130 | 1 | 0 | 1 | 1 | 0 | 1
Submitted | 2026-08-01 | Electrical | Stage 1 | VI |  | WSW46 | NO | 131236-WSW46-VI-E-0005 | Vendor Information For Electrical High Voltage DOL Panel (SCHNEIDER ELECTRIC PTE LTD) | 2026-08-26 | 2026-09-15 | 2026-09-10 | Ammar | 0 | 20 | 15 | -5 | RTR - Returned for Resubmission | NAP - Not Approved | YES | On Time | 0133 | 1 | 0 | 0 | 1 | 0 | 1
Submitted | 2026-09-01 | Electrical | Stage 1 | VI |  | WSW46 | NO | 131236-WSW46-VI-E-0006 | Vendor Information For Emergency Generator (VIBROPOWER PTE LTD) | 2026-09-04 | 2026-09-24 | 2026-09-22 | Ammar | 0 | 20 | 18 | -2 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | On Time | 0141 | 1 | 0 | 1 | 1 | 0 | 1
Submitted | 2026-09-01 | Electrical | Stage 1 | VI |  | WSW46 | NO | 131236-WSW46-VI-E-0001 | Vendor Information For Electrical Power Transformer & Distribution Transformer (TECO ELECTRIC & MACHINERY PTE LTD) | 2026-09-25 | 2026-10-09 |  | Ammar | 1 | 14 | 19 | 5 | SUR - Under SO Review | Pending Review | Pending | Delayed | 00094 | 1 | 0 |  | 0 | 1
Submitted | 2026-08-01 | Electrical | Stage 1 | VI |  | WSW46 | NO | 131236-WSW46-VI-E-0002 | Vendor Information For Electrical High Voltage Switchgear Panel (SCHNEIDER ELECTRIC PTE LTD) | 2026-08-26 | 2026-09-09 | 2026-09-10 | Ammar | 1 | 14 | 15 | 1 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | Delayed | 00095 | 1 | 0 | 1 | 0 | 1 | 1
Submitted | 2026-08-01 | Electrical | Stage 1 | VI |  | WSW46 | NO | 131236-WSW46-VI-E-0003 | Vendor Information For Low Voltage Electrical Equipment Works (SUNLIGHT ELECTRICAL PTE LTD) | 2026-08-28 | 2026-09-11 | 2026-09-22 | Ammar | 1 | 14 | 25 | 11 | RTR - Returned for Resubmission | NAP - Not Approved | YES | Delayed | 00101 | 1 | 0 | 0 | 0 | 1 | 1
Submitted | 2026-05-01 | Mech | Unassigned | VI |  |  |  | 131236-WIL00-VI-M-0001 | Vendor Information For NDT Company Details & Procedure (Ace Quality Testing & Inspection Services Pte Ltd) | 2026-05-28 | 2026-06-17 | 2026-06-29 | Dinesh | 0 | 20 | 32 | 12 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | Delayed | 0065 | 1 | 0 | 1 | 0 | 1 | 1
Submitted | 2026-06-01 | Mech | Stage 1 | VI |  | WIL00 | NO | 131236-WIL00-VI-M-0002 | Vendor Information For Stainless Steel Pipes and Fittigngs | 2026-06-09 | 2026-06-29 | 2026-06-29 | Fadhli Muiz | 0 | 20 | 20 | 0 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | On Time | 0076 | 1 | 0 | 1 | 1 | 0 | 1
Submitted | 2026-05-01 | Mech | Stage 1 | VI | Intermediate Screen, Dewatering Press | WIL21 |  | 131236-WIL21-VI-M-0001 | Vendor Information For Intermediate Screen And Its Associated Dewatering Press (WAM Singapore BHM Pte Ltd) | 2026-05-26 | 2026-06-15 | 2026-06-28 | Alan Siah | 0 | 20 | 33 | 13 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | Delayed | 0064 | 1 | 0 | 1 | 0 | 1 | 1
Submitted | 2026-05-01 | Mech | Stage 1 | VI | Grit Classifier | WIL21 |  | 131236-WIL21-VI-M-0002 | Vendor Information For Grit Classifier (WAM Singapore BHM Pte Ltd) | 2026-05-28 | 2026-06-17 | 2026-06-29 | Alan Siah | 0 | 20 | 32 | 12 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | Delayed | 0066 | 1 | 0 | 1 | 0 | 1 | 1
Submitted | 2026-06-01 | Mech | Stage 1 | VI | Conveyor | WIL21 |  | 131236-WIL21-VI-M-0003 | Vendor Information For Conveyor (WAM Singapore BHM Pte Ltd) | 2026-06-09 | 2026-06-29 | 2026-07-27 | Alan Siah | 0 | 20 | 48 | 28 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | Delayed | 0077 | 1 | 0 | 1 | 0 | 1 | 1
Submitted | 2026-08-01 | Mech | Stage 1 | VI | Scum and Grease Removal Equipment | WIL21 |  | 131236-WIL21-VI-M-0004 | Vendor Information for Grit Tank Grease And Scum Removal Equipment (PROBIG GmbH) | 2026-08-06 | 2026-08-26 | 2026-08-27 | Fadhli Muiz | 0 | 20 | 21 | 1 | RTR - Returned for Resubmission | NAP - Not Approved | YES | Delayed | 0112 | 1 | 0 | 0 | 0 | 1 | 1
Submitted | 2026-07-01 | Mech | Stage 1 | VI | PST Lamella/Scraper/Scum Collector | WIL22 |  | 131236-WIL22-VI-M-0001 | Vendor Information For Lamella Settlement, Lamella support structure, PST Sludge Scraper and PST Scum Skimming and Removal System (Nova Industries International L.L.C-FZ) | 2026-07-08 | 2026-07-28 | 2026-08-17 | Kenny Lim | 0 | 20 | 40 | 20 | RTR - Returned for Resubmission | NAP - Not Approved | YES | Delayed | 0093 | 1 | 0 | 0 | 0 | 1 | 1
Submitted | 2026-03-01 | Mech | Stage 1 | VI | Hyperboloid Mixer | WIL23 |  | 131236-WIL23-VI-M-0001 | Vendor Information - Hyperbolic Mixer (INVENT UMWELT- UND VERFAHRENSTECHNIK AG) | 2026-03-26 | 2026-04-15 | 2026-04-30 | Wai Bin | 0 | 20 | 35 | 15 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | Delayed | 0023 | 1 | 0 | 1 | 0 | 1 | 1
Submitted | 2026-06-01 | Mech | Stage 1 | VI | MFS (Polymeric Membrane) | WIL23 |  | 131236-WIL23-VI-M-0002 | Vendor Information For Design, Manufacturing, FAT, Supply & Delivery of MFS (Membrane) (Veolia Water Technologies & Solutions (Singapore) Pte Ltd) | 2026-06-12 | 2026-07-02 | 2026-07-18 | Tan Si Hui | 0 | 20 | 36 | 16 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | Delayed | 0080 | 1 | 0 | 1 | 0 | 1 | 1
Submitted | 2026-06-01 | Mech | Stage 1 | VI | Surge Vessel | WNS03 |  | 131236-WNS03-VI-M-0001 | Vendor Information Submission For Design, Supply, Manufacturing, FAT, and Delivery Of Surge Vessel Including Instrument and Structure Support (SYNCHONG HOE ENGINEERING SDN. BHD.) | 2026-06-29 | 2026-07-19 | 2026-07-27 | Fadhli Muiz | 0 | 20 | 28 | 8 | RTR - Returned for Resubmission | NAP - Not Approved | YES | Delayed | 0088 | 1 | 0 | 0 | 0 | 1 | 1
Submitted | 2026-07-01 | Mech | Stage 1 | VI | Diffuser | WSW46 |  | 131236-WSW46-VI-M-0001 | Vendor Information For Diffusers (Air Diffuser – Grit System and Bioreactors) (ENVIRONMENTAL DYNAMICS INTERNATIONAL, INC (EDI)) | 2026-07-16 | 2026-08-05 | 2026-08-27 | Tan Si Hui | 0 | 20 | 42 | 22 | RTR - Returned for Resubmission | NAP - Not Approved | YES | Delayed | 0103 | 1 | 0 | 0 | 0 | 1 | 1
Submitted | 2026-08-01 | Mech | Stage 2 | DS | Hyperboloid Mixer | WIL23 |  | 131236-WIL23-DS-M-0001 | Datasheet - ILM2 Bioreactor Mixed Liquor Mixer | 2026-08-14 | 2026-09-03 | 2026-09-11 | Wu Hongqing | 0 | 20 | 28 | 8 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | Delayed | 0119 | 1 | 0 | 1 | 0 | 1 | 1
Submitted | 2026-04-01 | Mech | Stage 2 | CL | Lifting Equipment | WSW46 |  | 131236-WSW46-CL-M-0001 | Design Calculation For Existing RC Slab And Beam For Max.10 Tons Mini Spider Crane Parking And Access At SFL. 15.8m Industrial LM2 (WIL 21 AND 22) | 2026-04-16 | 2026-05-06 | 2026-06-22 | Mark | 0 | 20 | 67 | 47 | RTR - Returned for Resubmission | NAP - Not Approved | YES | Delayed | 0032 | 1 | 0 | 0 | 0 | 1 | 1
Submitted | 2026-08-01 | Mech | Stage 2 | CL | Foul Air Pipeworks | WSW46 |  | 131236-WSW46-CL-M-0002 | Calculation For Foul Air Pipeworks Pressure Drop Calculation For ILM2 OCF1 | 2026-08-17 | 2026-09-06 | 2026-09-29 | Wang YiQian | 0 | 20 | 43 | 23 | RTR - Returned for Resubmission | INF - For Information | YES | Delayed | 0120 | 1 | 0 |  | 0 | 1 | 1
Submitted | 2026-09-01 | Mech | Stage 2 | CL | Foul Air Pipeworks | WSW46 |  | 131236-WSW46-CL-M-0003 | Calculation For Foul Air Pipeworks Pressure Drop Calculation For ILM2 OCF2 | 2026-09-01 | 2026-09-21 | 2026-09-29 | Wu Hongqing | 0 | 20 | 28 | 8 | RTR - Returned for Resubmission | NAP - Not Approved | YES | Delayed | 0138 | 1 | 0 | 0 | 0 | 1 | 1
Submitted | 2026-08-01 | Mech | Stage 2 | CL |  | WIL21 |  | 131236-WIL21-CL-M-0001 | DPS And Intake Chamber Pipe Size Calculation | 2026-08-18 | 2026-09-07 | 2026-09-29 | Wang YiQian | 0 | 20 | 42 | 22 | RTR - Returned for Resubmission | INF - For Information | YES | Delayed | 0121 | 1 | 0 |  | 0 | 1 | 1
Submitted | 2026-08-01 | Mech | Stage 2 | CL |  | WIL21 |  | 131236-WIL21-CL-M-0002 | Intermediate Screen Area Pipe Size Calculation | 2026-08-18 | 2026-09-07 | 2026-09-30 | Wang YiQian | 0 | 20 | 43 | 23 | RTR - Returned for Resubmission | INF - For Information | YES | Delayed | 0122 | 1 | 0 |  | 0 | 1 | 1
Submitted | 2026-08-01 | Mech | Stage 2 | CL |  | WIL21 |  | 131236-WIL21-CL-M-0003 | Fine Screen Area Pipe Size Calculation | 2026-08-19 | 2026-09-08 | 2026-09-29 | Wang YiQian | 0 | 20 | 41 | 21 | RTR - Returned for Resubmission | INF - For Information | YES | Delayed | 0123 | 1 | 0 |  | 0 | 1 | 1
Submitted | 2026-08-01 | Mech | Stage 2 | CL |  | WIL21 |  | 131236-WIL21-CL-M-0004 | Aerated Grit Tank Area Pipe Size Calculation | 2026-08-24 | 2026-09-13 | 2026-09-30 | Wang YiQian | 0 | 20 | 37 | 17 | RTR - Returned for Resubmission | INF - For Information | YES | Delayed | 0124 | 1 | 0 |  | 0 | 1 | 1
Submitted | 2026-08-01 | Mech | Stage 2 | CL |  | WIL21 |  | 131236-WIL21-CL-M-0005 | Grit Classifier & Hopper Area Pipe Size Calculation | 2026-08-24 | 2026-09-13 | 2026-09-29 | Wang YiQian | 0 | 20 | 36 | 16 | RTR - Returned for Resubmission | INF - For Information | YES | Delayed | 0125 | 1 | 0 |  | 0 | 1 | 1
Submitted | 2026-08-01 | Mech | Stage 2 | CL |  | WIL21 |  | 131236-WIL21-CL-M-0006 | Headworks Grease and Scum Wet Well Area Pipe Size Calculation | 2026-08-24 | 2026-09-13 | 2026-09-30 | Wang YiQian | 0 | 20 | 37 | 17 | RTR - Returned for Resubmission | INF - For Information | YES | Delayed | 0126 | 1 | 0 |  | 0 | 1 | 1
Submitted | 2026-10-01 | Mech | Stage 1 | CL | Recessed Impeller Pump | WIL21 |  | 131236-WIL21-CL-M-0007 | Pump Head Calculation - ILM2 Influent Flowmeter Chamber Drainage Sump Pump | 2026-10-01 | 2026-10-21 |  | Wang YiQian | 0 | 20 | 13 | -7 | SUR - Under SO Review | Pending Review | Pending | On Time | 0161 | 1 | 0 |  | 1 | 0
Submitted | 2026-10-01 | Mech | Stage 2 | CL | Screw Induced Flow Pumps | WIL21 |  | 131236-WIL21-CL-M-0008 | Pump Head Calculation - ILM Plant Drainage PS Wet Well Compartment 2 Pump | 2026-10-01 | 2026-10-21 |  | Wang YiQian | 0 | 20 | 13 | -7 | SUR - Under SO Review | Pending Review | Pending | On Time | 0162 | 1 | 0 |  | 1 | 0
Submitted | 2026-10-01 | Mech | Stage 2 | CL | Double Disc Centrifugal Pumps | WIL21 |  | 131236-WIL21-CL-M-0009 | Pump Head Calculation - ILM2 Grease and Scum Wet Well Pump | 2026-10-05 | 2026-10-25 |  | Wang YiQian | 0 | 20 | 9 | -11 | SUR - Under SO Review | Pending Review | Pending | On Time | 0169 | 1 | 0 |  | 1 | 0
Submitted | 2026-10-01 | Mech | Stage 2 | CL |  | WIL21 |  | 131236-WIL21-CL-M-0001 | DPS And Intake Chamber Pipe Size Calculation | 2026-10-05 | 2026-10-25 |  | Wang YiQian | 0 | 20 | 9 | -11 | SUR - Under SO Review | Pending Review | Pending | On Time | 0170 | 1 | 0 |  | 1 | 0
Submitted | 2026-09-01 | Mech | Stage 2 | CL | Hyperboloid Mixer | WIL23 |  | 131236-WIL23-CL-M-0001 | Study Report - Anoxic Tank Mixing CFD Modelling | 2026-09-22 | 2026-10-12 |  | Wu Hongqing | 0 | 20 | 22 | 2 | SUR - Under SO Review | Pending Review | Pending | Delayed | 0153 | 1 | 0 |  | 0 | 1
Submitted | 2026-09-01 | Mech | Stage 2 | CL |  | WIL23 |  | 131236-WIL23-CL-M-0002 | Membrane Area Pipe Size Calculation | 2026-09-22 | 2026-10-12 |  | Wu Hongqing | 0 | 20 | 22 | 2 | SUR - Under SO Review | Pending Review | Pending | Delayed | 0154 | 1 | 0 |  | 0 | 1
Submitted | 2026-09-01 | Mech | Stage 2 | CL |  | WIL23 |  | 131236-WIL23-CL-M-0003 | MBR Filtrate Tank & Transfer Pump Pipe Size Calculation | 2026-09-22 | 2026-10-12 |  | Wu Hongqing | 0 | 20 | 22 | 2 | SUR - Under SO Review | Pending Review | Pending | Delayed | 0155 | 1 | 0 |  | 0 | 1
Submitted | 2026-09-01 | Mech | Stage 2 | CL |  | WIL23 |  | 131236-WIL23-CL-M-0004 | WAS, RAS & Mixed Liquor Wet Well Pipe Size Calculation | 2026-09-22 | 2026-10-12 |  | Wu Hongqing | 0 | 20 | 22 | 2 | SUR - Under SO Review | Pending Review | Pending | Delayed | 0156 | 1 | 0 |  | 0 | 1
Submitted | 2026-10-01 | Mech | Stage 2 | CL | Submersible Pumps | WIL23 |  | 131236-WIL23-CL-M-0005 | Pump Head Calculation - ILM2 Bioreactor Drainage Pump | 2026-10-03 | 2026-10-23 |  | Wang YiQian | 0 | 20 | 11 | -9 | SUR - Under SO Review | Pending Review | Pending | On Time | 0163 | 1 | 0 |  | 1 | 0
Submitted | 2026-10-01 | Mech | Stage 2 | CL | Submersible Pumps | WIL23 |  | 131236-WIL23-CL-M-0006 | Pump Head Calculation - ILM2 DEOX/RAS Tank Drainage Pump | 2026-10-03 | 2026-10-23 |  | Wang YiQian | 0 | 20 | 11 | -9 | SUR - Under SO Review | Pending Review | Pending | On Time | 0164 | 1 | 0 |  | 1 | 0
Submitted | 2026-10-01 | Mech | Stage 2 | CL | Submersible Pumps | WIL23 |  | 131236-WIL23-CL-M-0007 | Pump Head Calculation - ILM2 MBR Filtrate Tank Drainage Pump | 2026-10-03 | 2026-10-23 |  | Wang YiQian | 0 | 20 | 11 | -9 | SUR - Under SO Review | Pending Review | Pending | On Time | 0165 | 1 | 0 |  | 1 | 0
Submitted | 2026-10-01 | Mech | Stage 2 | CL | Double Disc Centrifugal Pumps | WIL23 |  | 131236-WIL23-CL-M-0008 | Pump Head Calculation - ILM2 Membrane Scum Wet Well Pump | 2026-10-05 | 2026-10-25 |  | Wang YiQian | 0 | 20 | 9 | -11 | SUR - Under SO Review | Pending Review | Pending | On Time | 0168 | 1 | 0 |  | 1 | 0
Submitted | 2026-08-01 | Mech | Stage 2 | DR | Hyperboloid Mixer | WIL23 |  | 131236-WIL23-DR-M-5500 | GA Drawing - ILM2 Bioreactor Mixed Liquor Mixer Sheet 1 of 2 | 2026-08-25 | 2026-09-14 | 2026-09-21 | Wu Hongqing | 0 | 20 | 27 | 7 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | Delayed | 0128 | 1 | 0 | 1 | 0 | 1 | 1
Submitted | 2026-08-01 | Mech | Stage 2 | DR | Hyperboloid Mixer | WIL23 |  | 131236-WIL23-DR-M-5501 | GA Drawing - ILM2 Bioreactor Mixed Liquor Mixer Sheet 2 of 2 | 2026-08-25 | 2026-09-14 | 2026-09-21 | Wu Hongqing | 0 | 20 | 27 | 7 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | Delayed | 0128 | 1 | 0 | 1 | 0 | 1 | 1
Submitted | 2026-05-01 | Mech | Stage 2 | DR | High Speed Turbo Blower | WIL21 |  | 131236-WIL21-DR-M-5000 | ILM2 - HEAD WORKS BLOWER ROOM AREA DN300 - RISER PIPE Sheet 1 Of 2 | 2026-05-13 | 2026-06-02 | 2026-06-03 | Rizal | 0 | 20 | 21 | 1 | RTR - Returned for Resubmission | NAP - Not Approved | YES | Delayed | 0052 | 1 | 0 | 0 | 0 | 1 | 1
Submitted | 2026-05-01 | Mech | Stage 2 | DR | High Speed Turbo Blower | WIL21 |  | 131236-WIL21-DR-M-1000 | ILM2 - HEAD WORKS BLOWER ROOM AREA DN300 - RISER PIPE Sheet 2 Of 2 | 2026-05-13 | 2026-06-02 | 2026-06-03 | Rizal | 0 | 20 | 21 | 1 | RTR - Returned for Resubmission | NAP - Not Approved | YES | Delayed | 0052 | 1 | 0 | 0 | 0 | 1 | 1
Submitted | 2026-08-01 | Mech | Stage 2 | DR |  | WIL21 |  | 131236-WIL21-DR-P-6000 | P&ID-INTERMEDIATE SCREENS 1,2 & 3 | 2026-08-12 | 2026-09-01 |  | Wang YiQian | 0 | 20 | 63 | 43 | SUR - Under SO Review | Pending Review | Pending | Delayed | 0114 | 1 | 0 |  | 0 | 1
Submitted | 2026-08-01 | Mech | Stage 2 | DR |  | WIL21 |  | 131236-WIL21-DR-P-6001 | P&ID-INTERMEDIATE SCREENS 4,5 & 6 | 2026-08-12 | 2026-09-01 |  | Wang YiQian | 0 | 20 | 63 | 43 | SUR - Under SO Review | Pending Review | Pending | Delayed | 0114 | 1 | 0 |  | 0 | 1
Submitted | 2026-08-01 | Mech | Stage 2 | DR |  | WIL21 |  | 131236-WIL21-DR-P-6002 | P&ID-ODOUR HEADERS AND FLOWMETERS ILM OCF1 | 2026-08-12 | 2026-09-01 |  | Wang YiQian | 0 | 20 | 63 | 43 | SUR - Under SO Review | Pending Review | Pending | Delayed | 0114 | 1 | 0 |  | 0 | 1
Submitted | 2026-08-01 | Mech | Stage 2 | DR |  | WIL21 |  | 131236-WIL21-DR-P-6003 | P&ID-FINE SCREENS 1,2 & 3 | 2026-08-12 | 2026-09-01 |  | Wang YiQian | 0 | 20 | 63 | 43 | SUR - Under SO Review | Pending Review | Pending | Delayed | 0114 | 1 | 0 |  | 0 | 1
Submitted | 2026-08-01 | Mech | Stage 2 | DR |  | WIL21 |  | 131236-WIL21-DR-P-6004 | P&ID-FINE SCREENS 4,5 & 6 | 2026-08-12 | 2026-09-01 |  | Wang YiQian | 0 | 20 | 63 | 43 | SUR - Under SO Review | Pending Review | Pending | Delayed | 0114 | 1 | 0 |  | 0 | 1
Submitted | 2026-08-01 | Mech | Unassigned | DR |  |  |  | 131236-WIL21-DR-P-6005 | P&ID-GRIT TANKS 1 & 2 | 2026-08-12 | 2026-09-01 |  | Wang YiQian | 0 | 20 | 63 | 43 | SUR - Under SO Review | Pending Review | Pending | Delayed | 0114 | 1 | 0 |  | 0 | 1
Submitted | 2026-08-01 | Mech | Stage 2 | DR |  | WIL21 |  | 131236-WIL21-DR-P-6006 | P&ID-GRIT TANKS 1 & 2 | 2026-08-12 | 2026-09-01 |  | Wang YiQian | 0 | 20 | 63 | 43 | SUR - Under SO Review | Pending Review | Pending | Delayed | 0114 | 1 | 0 |  | 0 | 1
Submitted | 2026-08-01 | Mech | Stage 2 | DR |  | WIL21 |  | 131236-WIL21-DR-P-6007 | P&ID-GRIT TANKS 3 & 4 | 2026-08-12 | 2026-09-01 |  | Wang YiQian | 0 | 20 | 63 | 43 | SUR - Under SO Review | Pending Review | Pending | Delayed | 0114 | 1 | 0 |  | 0 | 1
Submitted | 2026-08-01 | Mech | Stage 2 | DR |  | WIL21 |  | 131236-WIL21-DR-P-6008 | P&ID-GRIT TANKS 5 & 6 | 2026-08-12 | 2026-09-01 |  | Wang YiQian | 0 | 20 | 63 | 43 | SUR - Under SO Review | Pending Review | Pending | Delayed | 0114 | 1 | 0 |  | 0 | 1
Submitted | 2026-08-01 | Mech | Stage 2 | DR |  | WIL21 |  | 131236-WIL21-DR-P-6009 | P&ID-GRIT AIR BLOWERS | 2026-08-12 | 2026-09-01 |  | Wang YiQian | 0 | 20 | 63 | 43 | SUR - Under SO Review | Pending Review | Pending | Delayed | 0114 | 1 | 0 |  | 0 | 1
Submitted | 2026-08-01 | Mech | Stage 2 | DR |  | WIL21 |  | 131236-WIL21-DR-P-6010 | P&ID-GRIT CLASSIFIER AND CONVEYANCE SYSTEM | 2026-08-12 | 2026-09-01 |  | Wang YiQian | 0 | 20 | 63 | 43 | SUR - Under SO Review | Pending Review | Pending | Delayed | 0114 | 1 | 0 |  | 0 | 1
Submitted | 2026-08-01 | Mech | Stage 2 | DR |  | WIL21 |  | 131236-WIL21-DR-P-6011 | P&ID-COMMON LOADOUT FACILITY | 2026-08-12 | 2026-09-01 |  | Wang YiQian | 0 | 20 | 63 | 43 | SUR - Under SO Review | Pending Review | Pending | Delayed | 0114 | 1 | 0 |  | 0 | 1
Submitted | 2026-08-01 | Mech | Stage 2 | DR |  | WIL21 |  | 131236-WIL21-DR-P-6012 | P&ID-GREASE AND SCUM REMOVAL SYSTEM | 2026-08-12 | 2026-09-01 |  | Wang YiQian | 0 | 20 | 63 | 43 | SUR - Under SO Review | Pending Review | Pending | Delayed | 0114 | 1 | 0 |  | 0 | 1
Submitted | 2026-08-01 | Mech | Stage 2 | DR |  | WIL21 |  | 131236-WIL21-DR-P-6015 | P&ID-INDUSTRIAL LM2 PRIMARY TREATMENT & HEADWORKS PLANT DRAINAGE | 2026-08-12 | 2026-09-01 |  | Wang YiQian | 0 | 20 | 63 | 43 | SUR - Under SO Review | Pending Review | Pending | Delayed | 0114 | 1 | 0 |  | 0 | 1
Submitted | 2026-08-01 | Mech | Stage 2 | DR |  | WIL21 |  | 131236-WIL21-DR-P-6016 | P&ID-ILM2 PLANT DRAINAGE PUMPING STATION | 2026-08-12 | 2026-09-01 |  | Wang YiQian | 0 | 20 | 63 | 43 | SUR - Under SO Review | Pending Review | Pending | Delayed | 0114 | 1 | 0 |  | 0 | 1
Submitted | 2026-08-01 | Mech | Stage 2 | DR |  | WNS03 |  | 131236-WNS03-DR-P-6050 | P&ID SURGE VESSELS | 2026-08-31 | 2026-09-20 |  | Fadhli Muiz | 0 | 20 | 44 | 24 | SUR - Under SO Review | Pending Review | Pending | Delayed | 0137 | 1 | 0 |  | 0 | 1
Submitted | 2026-05-01 | Mech | Unassigned | QA |  |  |  | 131236-WIL00-QA-M-0001 | ITP, WPS & PQR For SS316L Pipe Fabrication Works | 2026-05-13 | 2026-06-02 | 2026-06-03 | Dinesh | 0 | 20 | 21 | 1 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | Delayed | 0054 | 1 | 0 | 1 | 0 | 1 | 1
Submitted | 2026-05-01 | Mech | Unassigned | QA |  |  |  | 131236-WIL00-QA-M-0002 | Welder Qualification for Carbon Steel & Stainless Steel Fabrication and Site Installation Works(UES Holdings Pte Ltd) | 2026-05-18 | 2026-06-07 | 2026-06-03 | Dinesh | 0 | 20 | 16 | -4 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | On Time | 0056 | 1 | 0 | 1 | 1 | 0 | 1
Submitted | 2026-05-01 | Mech | Unassigned | QA |  |  |  | 131236-WIL00-QA-M-0003 | ITP, WPS & PQR For Pipe Support workshop Fabrication Works | 2026-05-28 | 2026-06-17 | 2026-06-29 | Dinesh | 0 | 20 | 32 | 12 | RTR - Returned for Resubmission | INF - For Information | YES | Delayed | 0070 | 1 | 0 |  | 0 | 1 | 1
Submitted | 2026-09-01 | Mech | Unassigned | QA |  |  |  | 131236-WIL00-QA-M-0004 | Inspection and Test Plan for SS316L Pipe, Fittings & Flanges (Raccortubi Singapore Pte. Ltd.) | 2026-09-23 | 2026-10-13 |  | Dinesh | 0 | 20 | 21 | 1 | SUR - Under SO Review | Pending Review | Pending | Delayed | 0157 | 1 | 0 |  | 0 | 1
Submitted | 2026-09-01 | Mech | Stage 3 | QA | Hyperboloid Mixer | WIL23 |  | 131236-WIL23-QA-M-0001 | ITP & FAT - Hyperbolic Mixer | 2026-09-15 | 2026-10-05 |  | Fadhli Muiz | 0 | 20 | 29 | 9 | SUR - Under SO Review | Pending Review | Pending | Delayed | 0146 | 1 | 0 |  | 0 | 1
Submitted | 2026-09-01 | Mech | Stage 3 | QA | MFS (Polymeric Membrane) | WIL23 |  | 131236-WIL23-QA-M-0002 | ITP - MFS (Membrane) | 2026-09-15 | 2026-10-05 |  | Fadhli Muiz | 0 | 20 | 29 | 9 | SUR - Under SO Review | Pending Review | Pending | Delayed | 0147 | 1 | 0 |  | 0 | 1
Submitted | 2026-09-01 | Mech | Unassigned | QA |  |  |  | 131236-WIL23-QA-M-0003 | ITP For Screen & Dewatering Press | 2026-09-15 | 2026-10-05 |  | Fadhli Muiz | 0 | 20 | 29 | 9 | SUR - Under SO Review | Pending Review | Pending | Delayed | 0148 | 1 | 0 |  | 0 | 1
Submitted | 2026-06-01 | Mech | Stage 3 | QA | Hyperboloid Mixer | WIL23 |  | 131236-WIL23-QA-M-0001 | ITP & FAT - Hyperbolic Mixer | 2026-06-26 | 2026-07-16 | 2026-07-27 | Kenny | 0 | 20 | 31 | 11 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | Delayed | 0086 | 1 | 0 | 1 | 0 | 1 | 1
Submitted | 2026-08-01 | Mech | Stage 3 | QA | MFS (Polymeric Membrane) | WIL23 |  | 131236-WIL23-QA-M-0002 | ITP - MFS (Membrane) | 2026-08-06 | 2026-08-26 | 2026-08-29 | Wu Hongqing | 0 | 20 | 23 | 3 | RTR - Returned for Resubmission | NAP - Not Approved | YES | Delayed | 0113 | 1 | 0 | 0 | 0 | 1 | 1
Submitted | 2026-06-01 | Mech | Stage 3 | RT | Mixer | WIL23 |  | 131236-WIL23-RT-M-0001 | CFD Report for Bioreactor Mixed Liquor Mixer | 2026-06-26 | 2026-07-16 | 2026-07-27 | Kenny | 0 | 20 | 31 | 11 | RTR - Returned for Resubmission | NAP - Not Approved | YES | Delayed | 0087 | 1 | 0 | 0 | 0 | 1 | 1
Submitted | 2026-07-01 | Mech | Stage 1 | VI | Intermediate Screen, Dewatering Press | WIL21 |  | 131236-WIL21-VI-M-0001 | Vendor Information For Intermediate Screen And Its Associated Dewatering Press (WAM Singapore BHM Pte Ltd) | 2026-07-22 | 2026-08-05 | 2026-08-28 | Fadhli Muiz | 1 | 14 | 37 | 23 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | Delayed | 00064 | 1 | 0 | 1 | 0 | 1 | 1
Submitted | 2026-09-01 | Mech | Stage 1 | VI | PST Lamella/Scraper/Scum Collector | WIL22 |  | 131236-WIL22-VI-M-0001 | Vendor Information For Lamella Settlement, Lamella support structure, PST Sludge Scraper and PST Scum Skimming and Removal System (Nova Industries International L.L.C-FZ) | 2026-09-21 | 2026-10-05 | 2026-09-28 | Kenny | 1 | 14 | 7 | -7 | RTR - Returned for Resubmission | NAP - Not Approved | YES | On Time | 00093 | 1 | 0 | 0 | 1 | 0 | 1
Submitted | 2026-07-01 | Mech | Stage 1 | VI | Hyperboloid Mixer | WIL23 |  | 131236-WIL23-VI-M-0001 | Vendor Information - Hyperbolic Mixer (INVENT UMWELT- UND VERFAHRENSTECHNIK AG) | 2026-07-10 | 2026-07-24 | 2026-07-27 | Wai Bin | 1 | 14 | 17 | 3 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | Delayed | 00023 | 1 | 0 | 1 | 0 | 1 | 1
Submitted | 2026-08-01 | Mech | Stage 1 | VI | Surge Vessel | WNS03 |  | 131236-WNS03-VI-M-0001 | Vendor Information Submission For Design, Supply, Manufacturing, FAT, and Delivery Of Surge Vessel Including Instrument and Structure Support (SYNCHONG HOE ENGINEERING SDN. BHD.) | 2026-08-13 | 2026-08-27 | 2026-09-11 | Fadhli Muiz | 1 | 14 | 29 | 15 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | Delayed | 00088 | 1 | 0 | 1 | 0 | 1 | 1
Submitted | 2026-09-01 | Mech | Stage 1 | VI | Diffuser | WSW46 |  | 131236-WSW46-VI-M-0001 | Vendor Information For Diffusers (Air Diffuser – Grit System and Bioreactors) (ENVIRONMENTAL DYNAMICS INTERNATIONAL, INC (EDI)) | 2026-09-21 | 2026-10-05 | 2026-10-06 | Wu Hongqing | 1 | 14 | 15 | 1 | RTR - Returned for Resubmission | AWC - Approved with Comments | YES | Delayed | 00103 | 1 | 0 | 1 | 0 | 1 | 1
Submitted | 2026-10-01 | Mech | Unassigned | CL |  |  |  | 131236-WSw46-CL-M-0002 | Foul Air Pipeworks Pressure Drop Calculation For ILM2 OCF1 | 2026-10-01 | 2026-10-15 |  | Wang YiQian | 1 | 14 | 13 | -1 | SUR - Under SO Review | Pending Review | Pending | On Time | 00120 | 1 | 0 |  | 1 | 0
Submitted | 2026-10-01 | Mech | Stage 2 | CL | Foul Air Pipeworks | WSW46 |  | 131236-WSW46-CL-M-0003 | Calculation For Foul Air Pipeworks Pressure Drop Calculation For ILM2 OCF2 | 2026-10-01 | 2026-10-15 |  | Wu Hongqing | 1 | 14 | 13 | -1 | SUR - Under SO Review | Pending Review | Pending | On Time | 00138 | 1 | 0 |  | 1 | 0
Submitted | 2026-08-01 | Mech | Stage 2 | DR | High Speed Turbo Blower | WIL21 |  | 131236-WIL21-DR-M-5000 | ILM2 - HEAD WORKS BLOWER ROOM AREA DN300 - RISER PIPE Sheet 1 Of 2 | 2026-08-13 | 2026-08-27 | 2026-08-28 | Rizal | 1 | 14 | 15 | 1 | NTS - No Resubmission Required | APP - Approved | NO | Delayed | 00052 | 1 | 0 | 1 | 0 | 1 | 0
Submitted | 2026-08-01 | Mech | Stage 2 | DR | High Speed Turbo Blower | WIL21 |  | 131236-WIL21-DR-M-1000 | ILM2 - HEAD WORKS BLOWER ROOM AREA DN300 - RISER PIPE Sheet 2 Of 2 | 2026-08-13 | 2026-08-27 | 2026-08-28 | Rizal | 1 | 14 | 15 | 1 | NTS - No Resubmission Required | APP - Approved | NO | Delayed | 00052 | 1 | 0 | 1 | 0 | 1 | 0
Submitted | 2026-10-01 | Mech | Stage 1 | VI | Hyperboloid Mixer | WIL23 |  | 131236-WIL23-VI-M-0001 | Vendor Information - Hyperbolic Mixer (INVENT UMWELT- UND VERFAHRENSTECHNIK AG) | 2026-10-01 | 2026-10-15 |  | Wu Hongqing | 2 | 14 | 13 | -1 | SUR - Under SO Review | Pending Review | Pending | On Time | 00023 | 1 | 0 |  | 1 | 0
Submitted | 2026-08-01 | BS | Stage 1 | VI |  | WIL00 | NO | 131236-WIL00-VI-B-0001 | Vendor Information For Licensed Plumber for Site Office (M-Stars Engineering & Construction Pte Ltd) | 2026-08-25 | 2026-09-14 | 2026-08-29 | Fadhli Muiz | 0 | 20 | 4 | -16 | NTS - No Resubmission Required | APP - Approved | NO | On Time | 0127 | 1 | 0 | 1 | 1 | 0 | 0
Submitted | 2026-07-01 | BS | Stage 1 | VI | Lift | WIL22 | NO | 131236-WIL22-VI-B-0001 | Vendor Information For Electric Lift Works (XJ Elevator Private Limited) | 2026-07-10 | 2026-07-30 | 2026-07-30 | Aizuddin Rahman | 0 | 20 | 20 | 0 | RTR - Returned for Resubmission | REJ - Rejected | YES | On Time | 0096 | 1 | 0 | 0 | 1 | 0 | 1
Submitted | 2026-07-01 | BS | Stage 1 | VI | Fire Protection System | WSW46 | NO | 131236-WSW46-VI-B-0001 | Vendor Information for Addressable Fire Alarm System (Acclaim System Private Limited) | 2026-07-31 | 2026-08-20 | 2026-08-28 | Alif Aizuddin | 0 | 20 | 28 | 8 | RTR - Returned for Resubmission | REJ - Rejected | YES | Delayed | 0109 | 1 | 0 | 0 | 0 | 1 | 1
Submitted | 2026-07-01 | BS | Stage 1 | VI | Fire Protection System | WSW46 | NO | 131236-WSW46-VI-B-0002 | Vendor Information for Two-Way Emergency Voice Communication System (Acclaim System Private Limited) | 2026-07-31 | 2026-08-20 | 2026-08-28 | Alif Aizuddin | 0 | 20 | 28 | 8 | RTR - Returned for Resubmission | REJ - Rejected | YES | Delayed | 0110 | 1 | 0 | 0 | 0 | 1 | 1
Submitted | 2026-08-01 | BS | Stage 1 | VI | Fire Protection System | WSW46 | NO | 131236-WSW46-VI-B-0003 | Vendor Information for Gas Suppression System (Federal Fire Engineering Pte Ltd) | 2026-08-06 | 2026-08-26 | 2026-08-28 | Alif Aizuddin | 0 | 20 | 22 | 2 | RTR - Returned for Resubmission | REJ - Rejected | YES | Delayed | 0111 | 1 | 0 | 0 | 0 | 1 | 1
Submitted | 2026-10-01 | BS | Stage 1 | VI | ACMV | WSW46 | NO | 131236-WSW46-VI-B-0004 | Vendor Information for Water-cooled Chiller (Midea (Singapore) Product Pte. Ltd.) | 2026-10-01 | 2026-10-21 |  | Alif Aizuddin | 0 | 20 | 13 | -7 | SUR - Under SO Review | Pending Review | Pending | On Time | 0160 | 1 | 0 |  | 1 | 0
Submitted | 2026-09-01 | BS | Stage 1 | VI | Lift | WIL22 | NO | 131236-WIL22-VI-B-0001 | Vendor Information For Electric Lift Works (XJ Elevator Private Limited) | 2026-09-15 | 2026-09-29 | 2026-09-23 | Aizuddin Rahman | 1 | 14 | 8 | -6 | RTR - Returned for Resubmission | REJ - Rejected | YES | On Time | 00096 | 1 | 0 | 0 | 1 | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0001 | Vendor Information For Pressure Gauge (BAUMER SINGAPORE PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0002 | Vendor Information For Cable Raceway (TRI-STAR INDUSTRIES PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0003 | Vendor Information For Temperature Transmitter c/w RTD (ENDRESS + HAUSER S.E.A. PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0004 | Vendor Information For Pressure Transmitter (EMERSON ASIA PACIFIC PTE. LTD.) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0005 | Vendor Information For Level Transmitter Radar (Non-Contacting) (ENDRESS + HAUSER S.E.A. PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0006 | Vendor Information For Pressure Switch(WIKA INSTRUMENTATION PTE. LTD.) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0007 | Vendor Information For Level Transmitter – RF Admittance(ENDRESS + HAUSER S.E.A. PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0008 | Vendor Information For Auto Sampler (ENDRESS + HAUSER S.E.A. PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0009 | Vendor Information For Low Point Leak Detector (IFM ELECTRONIC PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0010 | Vendor Information For Thermal Mass Flowmeter (ENDRESS + HAUSER S.E.A. PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0011 | Vendor Information For Thermal Flow Switch (ENDRESS + HAUSER S.E.A. PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0012 | Vendor Information For Turbidity Analyser (HACH WATER QUALITY SINGAPORE PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0013 | Vendor Information For Level Switch – Conductive Probe (ENDRESS + HAUSER S.E.A. PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0014 | Vendor Information For pH Analyser (EMERSON ASIA PACIFIC PTE. LTD.) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0015 | Vendor Information For Room Temperature Sensor (KELE & ASSOCIATES PTE LTD - VAISALA) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0016 | Vendor Information For Local Display (ENDRESS + HAUSER S.E.A. PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0017 | Vendor Information For Cable (LV Power, Signal & Control) (C-KINGDOM CABLE TECHNOLOGY CO., LTD.) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0018 | Vendor Information For SS316 Tube Fittings (YANGZHONG SINYA AUTO-CONTROL ENGINEERING CO.,LTD.) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0019 | Vendor Information For Cable (LV Power, Signal & Control)(KEI INDUSTRIES LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-0020 | Vendor Information For Flowmeter - Electromagnetic (ENDRESS + HAUSER S.E.A. PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WIL21 | YES | 131236-WIL21-VI-I-0001 | Vendor Information For Hydrogen Sulfide Gas Detector (DRAEGER SINGAPORE PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WIL21 | YES | 131236-WIL21-VI-I-0002 | Vendor Information For Carbon Monoxide Gas Detector (DRAEGER SINGAPORE PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WIL21 | YES | 131236-WIL21-VI-I-0003 | Vendor Information For Flammable (LEL) Gas Detector (DRAEGER SINGAPORE PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WIL21 | YES | 131236-WIL21-VI-I-0004 | Vendor Information For Weight Transmitter (METTLER – TOLEDO (S) PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WIL21 | YES | 131236-WIL21-VI-I-0005 | Vendor Information For Toxicity Analyser (AI ANALYTICAL PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WIL21 | YES | 131236-WIL21-VI-I-0006 | Vendor Information For Motion Switch (IFM ELECTRONIC PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WIL21 | YES | 131236-WIL21-VI-I-0007 | Vendor Information For Volatile Organic Compound (VOC) Gas Analyser (HONEYWELL RAE SYSTEMS) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WIL22 | YES | 131236-WIL22-VI-I-0001 | Vendor Information For Total Solid Analyser (VALMET - WETEC PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WIL22 | YES | 131236-WIL22-VI-I-0002 | Vendor Information For Level Switch Sludge Blanket – Ultrasonic (PULSAR – MAESTRO ASIA) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WIL23 | YES | 131236-WIL23-VI-I-0001 | Vendor Information For Level Switch – Tuning Fork (ENDRESS + HAUSER S.E.A. PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WIL23 | YES | 131236-WIL23-VI-I-0002 | Vendor Information For Orthophosphate Analyser(ENDRESS + HAUSER S.E.A. PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WIL23 | YES | 131236-WIL23-VI-I-0003 | Vendor Information For Conductivity Analyser(ENDRESS + HAUSER S.E.A. PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WIL23 | YES | 131236-WIL23-VI-I-0004 | Vendor Information For ORP Analyser(YOKOGAWA ENGINEERING ASIA PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WIL23 | YES | 131236-WIL23-VI-I-0005 | Vendor Information For Total Suspended Solid (MLSS) Analyser (HACH WATER QUALITY SINGAPORE PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WIL23 | YES | 131236-WIL23-VI-I-0006 | Vendor Information For Ammonia Analyser (HACH WATER QUALITY SINGAPORE PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WIL23 | YES | 131236-WIL23-VI-I-0007 | Vendor Information For Dissolved Oxygen Analyser (EMERSON ASIA PACIFIC PTE. LTD.) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | ICA | Stage 1 | VI |  | WIL23 | YES | 131236-WIL23-VI-I-0008 | Vendor Information For Nitrate / Nitrite Analyser (HACH WATER QUALITY SINGAPORE PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-08-01 | ICA | Stage 1 | VI |  | WNS03 | YES | 131236-WNS03-VI-I-0001 | Vendor Information For Differential Pressure Transmitter (EMERSON ASIA PACIFIC PTE. LTD.) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-XXXX | Vendor Information For Data Cables | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-XXXX | Vendor Information For Fibre Optic Cables | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-XXXX | Vendor Information For Instrument Tubing | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-XXXX | Vendor Information For Rotameter c/w Flow (Reed) Switch | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-XXXX | Vendor Information For Flowmeter - Open Channel Ultrasonic | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-XXXX | Vendor Information For - RIO Panels & Racks | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 1 | VI |  | WIL21 | YES | 131236-WIL21-VI-I-XXXX | Vendor Information For Truck Position Sensor | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 1 | VI |  | WIL23 | YES | 131236-WIL23-VI-I-XXXX | Vendor Information For Limit Switch | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 1 | VI |  | WIL22 | YES | 131236-WIL22-VI-I-XXXX | Vendor Information For Level Switch - Ultrasonic | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-XXXX | Vendor Information For Cable Gland | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-XXXX | Vendor Information For ICA Installation Sub Contracting Works | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-XXXX | Vendor Information For ICA Control System Sub Contracting Works | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-XXXX | Vendor Information For ICA Junction Box | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-XXXX | Vendor Information For ICA Field UPS DB | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 1 | VI |  | WNS03 | YES | 131236-WNS03-VI-I-XXXX | Vendor Information For Surge Protection Device (for Outdoor Instrument) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-XXXX | Vendor Information For Nameplate & Label | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 1 | VI |  | WIL21 | YES | 131236-WIL21-VI-I-XXXX | Vendor Information For Grit Air Blower PLC | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 1 | VI |  | WIL23 | YES | 131236-WIL23-VI-I-XXXX | Vendor Information For Bio Aeration Blower PLC | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 1 | VI |  | WIL23 | YES | 131236-WIL23-VI-I-XXXX | Vendor Information For Membrane Blower PLC | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 1 | VI |  | WNS03 | YES | 131236-WNS03-VI-I-XXXX | Vendor Information For Level Gauge - Magnetic | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 1 | VI |  | WNS03 | YES | 131236-WNS03-VI-I-XXXX | Vendor Information For Solenoid Valve | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 1 | VI |  | WNS03 | YES | 131236-WNS03-VI-I-XXXX | Vendor Information For Level Switch for Magnetic Level Gauge | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-XXXX | Vendor Approval - Preliminary Design, Manufacturing FAT, Delivery, and T&C for ICA Panels | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-XXXX | Vendor Information for Hazardous Area, SIF Study and Verification | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-XXXX | Vendor Information For Portable pH/ORP Meters | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-XXXX | Vendor Information For Portable Conductivity Meters | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-XXXX | Vendor Information For Portable DO Meters | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-XXXX | Vendor Information For Portable Turbidity Meters | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-XXXX | Vendor Information For Portable Residual Chlorine Meters | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-XXXX | Vendor Information For Portable NOx Meters | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-XXXX | Vendor Information For Portable TSS Meters | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-XXXX | Vendor Information For Portable VOC Gas Meters | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-XXXX | Vendor Information For Portable H2S Gas Meters | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-XXXX | Vendor Information For Portable Ammonia (High Range) Meters | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-XXXX | Vendor Information For Portable Ammonia (Low Range) Meters | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 1 | VI |  | WIL21 | YES | 131236-WIL21-VI-I-XXXX | Vendor Information For Loadout Facility Control System | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 1 | VI |  | WIL23 | YES | 131236-WIL23-VI-I-XXXX | Vendor Information For Biosorption Blower PLC c/w HMI | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 1 | VI |  | WSW46 | YES | 131236-WSW46-VI-I-XXXX | Vendor Information For Vibration Monitoring System | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-08-01 | ICA | Stage 2 | SH |  | WSW46 | NO | 131236-WSW46-SH-I-0001 | Instrument Master List | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | ICA | Stage 2 | SH |  | WSW46 | YES | 131236-WSW46-SH-I-0002 | Detailed Engineering FOIP (Fiber Optic Interface Panel) & FOBOT (Fiber Optic Break-Out Tray) Master List | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | ICA | Stage 2 | SH |  | WSW46 | YES | 131236-WSW46-SH-I-0003 | Detailed Engineering UPSDB Master List | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | ICA | Stage 2 | SH |  | WSW46 | NO | 131236-WSW46-SH-I-0004 | RIO Panel Master List | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | SH |  | WSW46 | NO | 131236-WSW46-SH-I-XXXX | LCS / LCP Schedule | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | SH |  | WSW46 | NO | 131236-WSW46-SH-I-XXXX | Junction Box Schedule | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL06 | NO | 131236-WIL06-SH-I-XXXX | I/O List For RIO Panel WIL06-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL21 | NO | 131236-WIL21-SH-I-XXXX | I/O List For RIO Panel WIL06-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL21 | NO | 131236-WIL21-SH-I-XXXX | I/O List For RIO Panel WIL21-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL21 | NO | 131236-WIL21-SH-I-XXXX | I/O List For RIO Panel WIL21-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL21 | NO | 131236-WIL21-SH-I-XXXX | I/O List For RIO Panel WIL21-RIO-0301A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL21 | NO | 131236-WIL21-SH-I-XXXX | I/O List For RIO Panel WIL21-RIO-0301B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL21 | NO | 131236-WIL21-SH-I-XXXX | I/O List For RIO Panel WIL21-RIO-0302A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL21 | NO | 131236-WIL21-SH-I-XXXX | I/O List For RIO Panel WIL21-RIO-0302B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL21 | NO | 131236-WIL21-SH-I-XXXX | I/O List For RIO Panel WIL21-RIO-0303A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL21 | NO | 131236-WIL21-SH-I-XXXX | I/O List For RIO Panel WIL21-RIO-0303B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL21 | NO | 131236-WIL21-SH-I-XXXX | I/O List For RIO Panel WIL21-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL21 | NO | 131236-WIL21-SH-I-XXXX | I/O List For RIO Panel WIL21-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL22 | NO | 131236-WIL22-SH-I-XXXX | I/O List For RIO Panel WIL22-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL22 | NO | 131236-WIL22-SH-I-XXXX | I/O List For RIO Panel WIL22-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL22 | NO | 131236-WIL22-SH-I-XXXX | I/O List For RIO Panel WIL22-RIO-0103A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL22 | NO | 131236-WIL22-SH-I-XXXX | I/O List For RIO Panel WIL22-RIO-0103B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL22 | NO | 131236-WIL22-SH-I-XXXX | I/O List For RIO Panel WIL22-RIO-0104A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL22 | NO | 131236-WIL22-SH-I-XXXX | I/O List For RIO Panel WIL22-RIO-0104B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL22 | NO | 131236-WIL22-SH-I-XXXX | I/O List For RIO Panel WIL22-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL22 | NO | 131236-WIL22-SH-I-XXXX | I/O List For RIO Panel WIL22-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0201 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0202 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0203 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0204A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0204B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0401 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0402 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0403 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0404 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0405 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0406 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0407 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0408 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0409 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0410 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0301 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0302 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0303 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0304A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0304B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0501 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0502 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0503 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0504 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0505 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0506 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0507 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0508 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0601A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | I/O List For RIO Panel WIL23-RIO-0601B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL06 | NO | 131236-WIL06-SH-I-XXXX | Cable Schedule For RIO Panel WIL06-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL06 | NO | 131236-WIL06-SH-I-XXXX | Cable Schedule For RIO Panel WIL06-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL21 | NO | 131236-WIL21-SH-I-XXXX | Cable Schedule For RIO Panel WIL21-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL21 | NO | 131236-WIL21-SH-I-XXXX | Cable Schedule For RIO Panel WIL21-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL21 | NO | 131236-WIL21-SH-I-XXXX | Cable Schedule For RIO Panel WIL21-RIO-0301A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL21 | NO | 131236-WIL21-SH-I-XXXX | Cable Schedule For RIO Panel WIL21-RIO-0301B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL21 | NO | 131236-WIL21-SH-I-XXXX | Cable Schedule For RIO Panel WIL21-RIO-0302A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL21 | NO | 131236-WIL21-SH-I-XXXX | Cable Schedule For RIO Panel WIL21-RIO-0302B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL21 | NO | 131236-WIL21-SH-I-XXXX | Cable Schedule For RIO Panel WIL21-RIO-0303A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL21 | NO | 131236-WIL21-SH-I-XXXX | Cable Schedule For RIO Panel WIL21-RIO-0303B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL21 | NO | 131236-WIL21-SH-I-XXXX | Cable Schedule For RIO Panel WIL21-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL21 | NO | 131236-WIL21-SH-I-XXXX | Cable Schedule For RIO Panel WIL21-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL22 | NO | 131236-WIL22-SH-I-XXXX | Cable Schedule For RIO Panel WIL22-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL22 | NO | 131236-WIL22-SH-I-XXXX | Cable Schedule For RIO Panel WIL22-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL22 | NO | 131236-WIL22-SH-I-XXXX | Cable Schedule For RIO Panel WIL22-RIO-0103A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL22 | NO | 131236-WIL22-SH-I-XXXX | Cable Schedule For RIO Panel WIL22-RIO-0103B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL22 | NO | 131236-WIL22-SH-I-XXXX | Cable Schedule For RIO Panel WIL22-RIO-0104A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL22 | NO | 131236-WIL22-SH-I-XXXX | Cable Schedule For RIO Panel WIL22-RIO-0104B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL22 | NO | 131236-WIL22-SH-I-XXXX | Cable Schedule For RIO Panel WIL22-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL22 | NO | 131236-WIL22-SH-I-XXXX | Cable Schedule For RIO Panel WIL22-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0201 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0202 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0203 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0204A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0204B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0401 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0402 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0403 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0404 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0405 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0406 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0407 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0408 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0409 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0410 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0301 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0302 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0303 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0304A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0304B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0501 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0502 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0503 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0504 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0505 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0506 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0507 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0508 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WIL23 | NO | 131236-WIL23-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0601A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WSW46 | NO | 131236-WSW46-SH-I-XXXX | Cable Schedule For RIO Panel WIL23-RIO-0601B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WSW46 | NO | 131236-WSW46-SH-I-XXXX | Process Automation Network (PAN) Overall Cable Schedule | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | SH |  | WSW46 | NO | 131236-WSW46-SH-I-XXXX | Process Monitoring Network (PMN) Overall Cable Schedule | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-06-01 | ICA | Stage 2 | DS |  | WIL21 | YES | 131236-WIL21-DS-I-0001 | Datasheet For Flammable (LEL) Gas Detector (DRAEGER SINGAPORE PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-06-01 | ICA | Stage 2 | DS |  | WIL21 | YES | 131236-WIL21-DS-I-0002 | Datasheet For CO Gas Detector (DRAEGER SINGAPORE PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-07-01 | ICA | Stage 2 | DS |  | WIL21 | YES | 131236-WIL21-DS-I-0003 | Datasheet For H2S Gas Detector (DRAEGER SINGAPORE PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-07-01 | ICA | Stage 2 | DS |  | WIL21 | YES | 131236-WIL21-DS-I-0004 | Datasheet For Motion Switch (IFM ELECTRONIC PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-08-01 | ICA | Stage 2 | DS |  | WIL21 | YES | 131236-WIL21-DS-I-0005 | Datasheet For Weight Transmitter with Load Cell (METTLER TOLEDO (S) PTE. LTD.) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | DS |  | WIL21 | YES | 131236-WIL21-DS-I-0006 | Datasheet For Weight Transmitter (METTLER – TOLEDO (S) PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-08-01 | ICA | Stage 2 | DS |  | WIL23 | YES | 131236-WIL23-DS-I-0001 | Datasheet For ORP Analyser (YOKOGAWA ENGINEERING ASIA PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-07-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-0001 | Datasheet For Low Point Leak Detector (IFM ELECTRONIC PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-0002 | Datasheet For pH Analyser (EMERSON ASIA PACIFIC PTE. LTD.) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Datasheet For Pressure Gauge (BAUMER SINGAPORE PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Datasheet For Temperature Transmitter c/w RTD (ENDRESS + HAUSER S.E.A. PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Datasheet For Pressure Transmitter (EMERSON ASIA PACIFIC PTE. LTD.) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Datasheet For Level Transmitter Radar (Non-Contacting) (ENDRESS + HAUSER S.E.A. PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Datasheet For Pressure Switch(WIKA INSTRUMENTATION PTE. LTD.) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Datasheet For Level Transmitter – RF Admittance(ENDRESS + HAUSER S.E.A. PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Datasheet For Auto Sampler (ENDRESS + HAUSER S.E.A. PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Datasheet For Thermal Mass Flowmeter (ENDRESS + HAUSER S.E.A. PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Datasheet For Thermal Flow Switch (ENDRESS + HAUSER S.E.A. PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Datasheet For Turbidity Analyser (HACH WATER QUALITY SINGAPORE PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Datasheet For Level Switch – Conductive Probe (ENDRESS + HAUSER S.E.A. PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Datasheet For Room Temperature Sensor (KELE & ASSOCIATES PTE LTD - VAISALA) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | DS |  | WIL21 | YES | 131236-WIL21-DS-I-XXXX | Datasheet For Toxicity Analyser (AI ANALYTICAL PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | DS |  | WIL21 | YES | 131236-WIL21-DS-I-XXXX | Datasheet For Volatile Organic Compound (VOC) Gas Analyser (HONEYWELL RAE SYSTEMS) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | DS |  | WIL22 | YES | 131236-WIL22-DS-I-XXXX | Datasheet For Total Solid Analyser (VALMET - WETEC PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | ICA | Stage 2 | DS |  | WIL22 | YES | 131236-WIL22-DS-I-XXXX | Datasheet For Level Switch Sludge Blanket – Ultrasonic (PULSAR – MAESTRO ASIA) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | DS |  | WIL23 | YES | 131236-WIL23-DS-I-XXXX | Datasheet For Level Switch – Tuning Fork (ENDRESS + HAUSER S.E.A. PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | DS |  | WIL23 | YES | 131236-WIL23-DS-I-XXXX | Datasheet For Orthophosphate Analyser(ENDRESS + HAUSER S.E.A. PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | ICA | Stage 2 | DS |  | WIL23 | YES | 131236-WIL23-DS-I-XXXX | Datasheet For Conductivity Analyser(ENDRESS + HAUSER S.E.A. PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | DS |  | WIL23 | YES | 131236-WIL23-DS-I-XXXX | Datasheet For Total Suspended Solid (MLSS) Analyser (HACH WATER QUALITY SINGAPORE PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | DS |  | WIL23 | YES | 131236-WIL23-DS-I-XXXX | Datasheet For Ammonia Analyser (HACH WATER QUALITY SINGAPORE PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | DS |  | WIL23 | YES | 131236-WIL23-DS-I-XXXX | Datasheet For Dissolved Oxygen Analyser (EMERSON ASIA PACIFIC PTE. LTD.) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | DS |  | WIL23 | YES | 131236-WIL23-DS-I-XXXX | Datasheet For Nitrate / Nitrite Analyser (HACH WATER QUALITY SINGAPORE PTE LTD) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | ICA | Stage 2 | DS |  | WNS03 | YES | 131236-WNS03-DS-I-XXXX | Datasheet For Differential Pressure Transmitter (EMERSON ASIA PACIFIC PTE. LTD.) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Datasheetn For Local Display (ENDRESS HAUSER) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Datasheet For Rotameter c/w Flow (Reed) Switch | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Datasheet For Flowmeter - Electromagnetic | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Datasheet For Flowmeter - Open Channel Ultrasonic | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | DS |  | WIL21 | YES | 131236-WIL21-DS-I-XXXX | Datasheet For Truck Position Sensor | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | DS |  | WIL23 | YES | 131236-WIL23-DS-I-XXXX | Datasheet For Limit Switch | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | DS |  | WIL22 | YES | 131236-WIL22-DS-I-XXXX | Datasheet For Level Switch - Ultrasonic | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Datasheet For Portable Analyser | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | DS |  | WNS03 | YES | 131236-WNS03-DS-I-XXXX | Datasheet For Level Gauge - Magnetic with Level Swich & Solenoid Valve | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Data Sheet & Details - RIO Panel | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Datasheet for Vehicle Entry and Exit Sensor | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Datasheet for Loop Powered Process Indicator - Local Indicator | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DS |  | WIL23 | YES | 131236-WIL23-DS-I-XXXX | Datasheet For Biosorption Blower LCP Design | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DS |  | WIL23 | YES | 131236-WIL23-DS-I-XXXX | Datasheet For Biosorption Blower MCP Design | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Data Sheet & Details - PLC Panel | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Data Sheet & Details - LCP Panel | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Data Sheet & Details - PLC Panel | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Data Sheet & Details - Junction Box | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Data Sheet & Details - Network Panels & Fobot | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DS |  | WIL23 | YES | 131236-WIL23-DS-I-XXXX | Datasheet For Bioreactor Blower LCP Design | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DS |  | WIL23 | YES | 131236-WIL23-DS-I-XXXX | Datasheet for Membrane Air Scour Blower LCP Design | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DS |  | WIL23 | YES | 131236-WIL23-DS-I-XXXX | Datasheet for Bioreactor Blower MCP Design | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DS |  | WIL23 | YES | 131236-WIL23-DS-I-XXXX | Datasheet for Membrane Air Scour Blower MCP Design | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DS |  | WIL21 | YES | 131236-WIL21-DS-I-XXXX | VMS Design for IGV Blowers | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Datasheet For Network Architecture and Signal List for IGV Blowers | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DS |  | WIL21 | YES | 131236-WIL21-DS-I-XXXX | Instrument Datasheets for IGV Blowers | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Data Sheet & Details - Cables | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Data Sheet & Details - Bench Testing Equipment | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Intrinsic Safety Cable Calculations | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | SIL level Design Calculations | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Fibre Optic Power Loss Calculations | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Data Sheet - Surge Arrestors | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Data Sheet - Vibration Monitoring System | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DS |  | WSW46 | YES | 131236-WSW46-DS-I-XXXX | Cable Size Calculation | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | ILM2 – Plant Drainage Pumping Station Process Control Narrative | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | PCN-Screenings and Grit Hopper Loadout Facility | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | PCN-Headworks Screening (Screens and Associated Equipment) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | PCN-Grit and Grease Removal (Grit Classifier and Associated Equipment) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | ILM2 – MBR Filtrate System Process Control Narrative | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | PCN-High Pressure Plant Water (G2HP) Pumping | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | PCN-Chemical Storage & Dosing | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | PCN-Grit Aeration Blower | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | ILM2 – Primary Treatment Process Control Narrative | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | PCN-Primary Sludge Domestic (PSD) Storage and Pumping | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | PCN-MBR Screening (Screens and Associated Equipment) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | PCN-Process Air Blowers | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | PCN-Bioreactor Sludge Wasting | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | PCN-Biosorption Air Blower | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | PCN-Membrance Air Blower | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | PCN-RAS Flow Division Control | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | PCN-Membrane Filtration System | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | PCN-Membrane Feed Channel Scum Removal | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | PCN-IWMF Process Water Pumping | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | PCN-IW Transfer Pumping | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | PCN-Membrane Filtrate Tank Drainage | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | FDS-High Pressure Plant Water (G2HP) Pumping | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | FDS-Chemical Storage & Dosing | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | FDS-Plant Drainage Pumping Station | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | FDS-Screenings and Grit Hopper Loadout Facility | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | FDS-Headworks Screening (Screens and Associated Equipment) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | FDS-Grit and Grease Removal (Grit Classifier and Associated Equipment) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | FDS-Grit Aeration Blower | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | FDS-Biosorption Tank (Mixer, Diffuser and Associated Equipment) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | FDS-Biosorption Aeration System | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | FDS-Primary Sludge Domestic (PSD) Storage and Pumping | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | FDS-Primary Sedimentation Tanks (Lamella System and Associated Equipment) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | FDS - ILM MBR Filtrate Tank Overview & Plant Water (G2D) Pumping | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | FDS-IWMF Process Water Pumping | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | FDS-ILM2 IW Transfer Pumping | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | FDS-ILM2 High Pressure Plant Water (G2HP) Pumping | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | FDS-MBR Screening (Screens and Associated Equipment) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | FDS-Process Air Blowers | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | FDS-Bioreactor Sludge Wasting | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | FDS-RAS Flow Division Control | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | FDS-Membrane Filtration System | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | FDS-Membrane Feed Channel Scum Removal | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | FDS-IW Transfer Pumping | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 2 | SP |  |  | NO | 131236-SP-PR-XXXX | FDS-Membrane Filtrate Tank Drainage | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WNS03 | NO | 131236-WNS03-DR-I-7000 | INSTRUMENT HOOKUP DRAWINGS FOR DIFFERENTIAL PRESSURE TRANSMITTER (SHEET 1 OF 1) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Hook-Up Drawing For Flammable (LEL) Gas Detector | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Hook-Up Drawing For CO Gas Detector | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Hook-Up Drawing For H2S Gas Detector | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Hook-Up Drawing For Motion Switch | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WSW46 | NO | 131236-WSW46-DR-I-XXXX | Hook-Up Drawing For Low Point Leak Detector | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WSW46 | NO | 131236-WSW46-DR-I-XXXX | Hook-Up Drawing For Pressure Gauge | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WSW46 | NO | 131236-WSW46-DR-I-XXXX | Hook-Up Drawing For Temperature Transmitter c/w RTD | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WSW46 | NO | 131236-WSW46-DR-I-XXXX | Hook-Up Drawing For Pressure Transmitter | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WSW46 | NO | 131236-WSW46-DR-I-XXXX | Hook-Up Drawing For Level Transmitter Radar (Non-Contacting) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WSW46 | NO | 131236-WSW46-DR-I-XXXX | Hook-Up Drawing For Pressure Switch | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WSW46 | NO | 131236-WSW46-DR-I-XXXX | Hook-Up Drawing For Level Transmitter – RF Admittance | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WSW46 | NO | 131236-WSW46-DR-I-XXXX | Hook-Up Drawing For Auto Sampler | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WSW46 | NO | 131236-WSW46-DR-I-XXXX | Hook-Up Drawing For Thermal Mass Flowmeter | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WSW46 | NO | 131236-WSW46-DR-I-XXXX | Hook-Up Drawing For Thermal Flow Switch | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WSW46 | NO | 131236-WSW46-DR-I-XXXX | Hook-Up Drawing For Turbidity Analyser | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WSW46 | NO | 131236-WSW46-DR-I-XXXX | Hook-Up Drawing For Level Switch – Conductive Probe | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WSW46 | NO | 131236-WSW46-DR-I-XXXX | Hook-Up Drawing For pH Analyser | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WSW46 | NO | 131236-WSW46-DR-I-XXXX | Hook-Up Drawing For Room Temperature Sensor | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Hook-Up Drawing For Weight Transmitter | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Hook-Up Drawing For Toxicity Analyser | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Hook-Up Drawing For Volatile Organic Compound (VOC) Gas Analyser | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Hook-Up Drawing For Total Solid Analyser | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Hook-Up Drawing For Level Switch Sludge Blanket – Ultrasonic | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Hook-Up Drawing For Level Switch – Tuning Fork | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Hook-Up Drawing For Orthophosphate Analyser | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Hook-Up Drawing For Conductivity Analyser | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Hook-Up Drawing For ORP Analyser | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Hook-Up Drawing For Total Suspended Solid (MLSS) Analyser | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Hook-Up Drawing For Ammonia Analyser | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Hook-Up Drawing For Dissolved Oxygen Analyser | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Hook-Up Drawing For Nitrate / Nitrite Analyser | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WSW46 | NO | 131236-WSW46-DR-I-XXXX | Hook-Up Drawing For Local Display | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WSW46 | NO | 131236-WSW46-DR-I-XXXX | Hook-Up Drawing For Rotameter c/w Flow (Reed) Switch | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WSW46 | NO | 131236-WSW46-DR-I-XXXX | Hook-Up Drawing For Flowmeter - Electromagnetic | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WSW46 | NO | 131236-WSW46-DR-I-XXXX | Hook-Up Drawing For Flowmeter - Open Channel Ultrasonic | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Hook-Up Drawing For Truck Position Sensor | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Hook-Up Drawing For Limit Switch | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Hook-Up Drawing For Level Switch - Ultrasonic | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 2 | DR |  | WNS03 | NO | 131236-WNS03-DR-I-XXXX | Hook Up Drawing For Level Gauge - Magnetic with Level Swich & Solenoid Valve | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL06 | NO | 131236-WIL06-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL06-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL06 | NO | 131236-WIL06-DR-I-XXXX | Cover Sheet For RIO Panel WIL06-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL06 | NO | 131236-WIL06-DR-I-XXXX | Revision Index For RIO Panel WIL06-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL06 | NO | 131236-WIL06-DR-I-XXXX | Bill Of Materials For RIO Panel WIL06-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL06 | NO | 131236-WIL06-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL06-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL06 | NO | 131236-WIL06-DR-I-XXXX | Nameplate Details For RIO Panel WIL06-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL06 | NO | 131236-WIL06-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL06-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL06 | NO | 131236-WIL06-DR-I-XXXX | Legend For RIO Panel WIL06-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL06 | NO | 131236-WIL06-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL06-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL06 | NO | 131236-WIL06-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL06-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL06 | NO | 131236-WIL06-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL06-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL06 | NO | 131236-WIL06-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL06-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL06 | NO | 131236-WIL06-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL06-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL06 | NO | 131236-WIL06-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL06-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL06 | NO | 131236-WIL06-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL06-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL06 | NO | 131236-WIL06-DR-I-XXXX | Cover Sheet For RIO Panel WIL06-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL06 | NO | 131236-WIL06-DR-I-XXXX | Revision Index For RIO Panel WIL06-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL06 | NO | 131236-WIL06-DR-I-XXXX | Bill Of Materials For RIO Panel WIL06-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL06 | NO | 131236-WIL06-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL06-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL06 | NO | 131236-WIL06-DR-I-XXXX | Nameplate Details For RIO Panel WIL06-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL06 | NO | 131236-WIL06-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL06-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL06 | NO | 131236-WIL06-DR-I-XXXX | Legend For RIO Panel WIL06-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL06 | NO | 131236-WIL06-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL06-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL06 | NO | 131236-WIL06-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL06-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL06 | NO | 131236-WIL06-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL06-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL06 | NO | 131236-WIL06-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL06-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL06 | NO | 131236-WIL06-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL06-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL06 | NO | 131236-WIL06-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL06-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL21-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Cover Sheet For RIO Panel WIL21-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Revision Index For RIO Panel WIL21-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Bill Of Materials For RIO Panel WIL21-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL21-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Nameplate Details For RIO Panel WIL21-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL21-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Legend For RIO Panel WIL21-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL21-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL21-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL21-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL21-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL21-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL21-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL21-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Cover Sheet For RIO Panel WIL21-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Revision Index For RIO Panel WIL21-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Bill Of Materials For RIO Panel WIL21-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL21-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Nameplate Details For RIO Panel WIL21-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL21-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Legend For RIO Panel WIL21-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL21-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL21-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL21-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL21-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL21-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL21-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL21-RIO-0301A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Cover Sheet For RIO Panel WIL21-RIO-0301A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Revision Index For RIO Panel WIL21-RIO-0301A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Bill Of Materials For RIO Panel WIL21-RIO-0301A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL21-RIO-0301A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Nameplate Details For RIO Panel WIL21-RIO-0301A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL21-RIO-0301A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Legend For RIO Panel WIL21-RIO-0301A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL21-RIO-0301A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL21-RIO-0301A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL21-RIO-0301A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL21-RIO-0301A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL21-RIO-0301A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL21-RIO-0301A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL21-RIO-0301B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Cover Sheet For RIO Panel WIL21-RIO-0301B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Revision Index For RIO Panel WIL21-RIO-0301B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Bill Of Materials For RIO Panel WIL21-RIO-0301B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL21-RIO-0301B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Nameplate Details For RIO Panel WIL21-RIO-0301B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL21-RIO-0301B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Legend For RIO Panel WIL21-RIO-0301B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL21-RIO-0301B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL21-RIO-0301B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL21-RIO-0301B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL21-RIO-0301B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL21-RIO-0301B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL21-RIO-0301B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL21-RIO-0302A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Cover Sheet For RIO Panel WIL21-RIO-0302A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Revision Index For RIO Panel WIL21-RIO-0302A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Bill Of Materials For RIO Panel WIL21-RIO-0302A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL21-RIO-0302A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Nameplate Details For RIO Panel WIL21-RIO-0302A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL21-RIO-0302A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Legend For RIO Panel WIL21-RIO-0302A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL21-RIO-0302A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL21-RIO-0302A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL21-RIO-0302A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL21-RIO-0302A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL21-RIO-0302A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL21-RIO-0302A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL21-RIO-0302B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Cover Sheet For RIO Panel WIL21-RIO-0302B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Revision Index For RIO Panel WIL21-RIO-0302B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Bill Of Materials For RIO Panel WIL21-RIO-0302B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL21-RIO-0302B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Nameplate Details For RIO Panel WIL21-RIO-0302B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL21-RIO-0302B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Legend For RIO Panel WIL21-RIO-0302B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL21-RIO-0302B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL21-RIO-0302B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL21-RIO-0302B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL21-RIO-0302B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL21-RIO-0302B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL21-RIO-0302B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL21-RIO-0303A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Cover Sheet For RIO Panel WIL21-RIO-0303A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Revision Index For RIO Panel WIL21-RIO-0303A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Bill Of Materials For RIO Panel WIL21-RIO-0303A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL21-RIO-0303A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Nameplate Details For RIO Panel WIL21-RIO-0303A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL21-RIO-0303A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Legend For RIO Panel WIL21-RIO-0303A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL21-RIO-0303A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL21-RIO-0303A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL21-RIO-0303A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL21-RIO-0303A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL21-RIO-0303A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL21-RIO-0303A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL21-RIO-0303B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Cover Sheet For RIO Panel WIL21-RIO-0303B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Revision Index For RIO Panel WIL21-RIO-0303B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Bill Of Materials For RIO Panel WIL21-RIO-0303B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL21-RIO-0303B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Nameplate Details For RIO Panel WIL21-RIO-0303B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL21-RIO-0303B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Legend For RIO Panel WIL21-RIO-0303B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL21-RIO-0303B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL21-RIO-0303B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL21-RIO-0303B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL21-RIO-0303B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL21-RIO-0303B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL21-RIO-0303B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL21-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Cover Sheet For RIO Panel WIL21-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Revision Index For RIO Panel WIL21-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Bill Of Materials For RIO Panel WIL21-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL21-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Nameplate Details For RIO Panel WIL21-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL21-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Legend For RIO Panel WIL21-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL21-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL21-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL21-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL21-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL21-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL21-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL21-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Cover Sheet For RIO Panel WIL21-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Revision Index For RIO Panel WIL21-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Bill Of Materials For RIO Panel WIL21-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL21-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Nameplate Details For RIO Panel WIL21-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL21-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Legend For RIO Panel WIL21-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL21-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL21-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL21-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL21-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL21-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL21-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL22-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Cover Sheet For RIO Panel WIL22-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Revision Index For RIO Panel WIL22-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Bill Of Materials For RIO Panel WIL22-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL22-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Nameplate Details For RIO Panel WIL22-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL22-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Legend For RIO Panel WIL22-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL22-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL22-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL22-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL22-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL22-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL22-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL22-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Cover Sheet For RIO Panel WIL22-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Revision Index For RIO Panel WIL22-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Bill Of Materials For RIO Panel WIL22-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL22-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Nameplate Details For RIO Panel WIL22-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL22-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Legend For RIO Panel WIL22-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL22-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL22-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL22-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL22-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL22-RIO-0103A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Cover Sheet For RIO Panel WIL22-RIO-0103A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Revision Index For RIO Panel WIL22-RIO-0103A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Bill Of Materials For RIO Panel WIL22-RIO-0103A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL22-RIO-0103A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Nameplate Details For RIO Panel WIL22-RIO-0103A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL22-RIO-0103A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Legend For RIO Panel WIL22-RIO-0103A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL22-RIO-0103A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL22-RIO-0103A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL22-RIO-0103A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL22-RIO-0103A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL22-RIO-0103A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL22-RIO-0103A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL22-RIO-0103B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Cover Sheet For RIO Panel WIL22-RIO-0103B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Revision Index For RIO Panel WIL22-RIO-0103B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Bill Of Materials For RIO Panel WIL22-RIO-0103B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL22-RIO-0103B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Nameplate Details For RIO Panel WIL22-RIO-0103B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL22-RIO-0103B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Legend For RIO Panel WIL22-RIO-0103B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL22-RIO-0103B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL22-RIO-0103B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL22-RIO-0103B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL22-RIO-0103B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL22-RIO-0103B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL22-RIO-0103B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL22-RIO-0104A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Cover Sheet For RIO Panel WIL22-RIO-0104A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Revision Index For RIO Panel WIL22-RIO-0104A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Bill Of Materials For RIO Panel WIL22-RIO-0104A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL22-RIO-0104A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Nameplate Details For RIO Panel WIL22-RIO-0104A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL22-RIO-0104A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Legend For RIO Panel WIL22-RIO-0104A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL22-RIO-0104A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL22-RIO-0104A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL22-RIO-0104A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL22-RIO-0104A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL22-RIO-0104A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL22-RIO-0104A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL22-RIO-0104B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Cover Sheet For RIO Panel WIL22-RIO-0104B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Revision Index For RIO Panel WIL22-RIO-0104B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Bill Of Materials For RIO Panel WIL22-RIO-0104B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL22-RIO-0104B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Nameplate Details For RIO Panel WIL22-RIO-0104B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL22-RIO-0104B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Legend For RIO Panel WIL22-RIO-0104B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL22-RIO-0104B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL22-RIO-0104B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL22-RIO-0104B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL22-RIO-0104B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL22-RIO-0104B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL22-RIO-0104B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL22-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Cover Sheet For RIO Panel WIL22-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Revision Index For RIO Panel WIL22-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Bill Of Materials For RIO Panel WIL22-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL22-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Nameplate Details For RIO Panel WIL22-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL22-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Legend For RIO Panel WIL22-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL22-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL22-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL22-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL22-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL22-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL22-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL22-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Cover Sheet For RIO Panel WIL22-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Revision Index For RIO Panel WIL22-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Bill Of Materials For RIO Panel WIL22-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL22-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Nameplate Details For RIO Panel WIL22-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL22-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Legend For RIO Panel WIL22-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL22-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL22-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL22-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL22-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL22-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL22-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0201 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0201 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0201 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0201 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0201 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0201 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0201 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0201 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0201 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0201 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0201 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0201 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0201 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0201 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0202 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0202 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0202 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0202 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0202 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0202 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0202 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0202 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0202 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0202 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0202 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0202 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0202 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0202 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0203 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0203 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0203 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0203 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0203 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0203 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0203 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0203 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0203 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0203 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0203 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0203 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0203 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0203 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0204A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0204A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0204A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0204A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0204A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0204A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0204A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0204A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0204A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0204A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0204A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0204A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0204A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0204A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0204B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0204B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0204B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0204B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0204B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0204B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0204B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0204B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0204B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0204B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0204B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0204B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0204B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0204B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0401 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0401 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0401 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0401 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0401 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0401 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0401 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0401 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0401 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0401 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0401 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0401 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0401 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0401 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0402 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0402 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0402 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0402 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0402 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0402 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0402 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0402 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0402 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0402 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0402 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0402 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0402 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0402 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0403 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0403 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0403 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0403 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0403 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0403 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0403 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0403 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0403 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0403 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0403 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0403 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0403 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0403 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0404 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0404 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0404 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0404 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0404 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0404 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0404 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0404 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0404 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0404 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0404 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0404 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0404 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0404 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0405 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0405 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0405 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0405 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0405 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0405 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0405 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0405 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0405 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0405 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0405 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0405 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0405 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0405 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0406 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0406 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0406 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0406 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0406 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0406 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0406 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0406 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0406 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0406 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0406 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0406 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0406 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0406 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0407 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0407 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0407 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0407 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0407 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0407 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0407 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0407 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0407 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0407 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0407 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0407 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0407 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0407 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0408 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0408 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0408 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0408 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0408 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0408 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0408 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0408 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0408 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0408 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0408 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0408 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0408 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0408 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0409 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0409 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0409 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0409 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0409 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0409 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0409 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0409 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0409 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0409 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0409 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0409 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0409 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0409 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0410 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0410 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0410 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0410 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0410 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0410 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0410 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0410 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0410 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0410 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0410 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0410 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0410 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0410 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0301 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0301 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0301 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0301 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0301 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0301 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0301 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0301 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0301 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0301 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0301 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0301 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0301 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0301 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0302 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0302 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0302 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0302 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0302 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0302 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0302 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0302 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0302 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0302 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0302 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0302 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0302 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0302 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0303 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0303 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0303 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0303 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0303 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0303 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0303 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0303 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0303 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0303 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0303 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0303 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0303 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0303 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0304A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0304A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0304A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0304A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0304A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0304A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0304A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0304A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0304A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0304A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0304A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0304A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0304A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0304A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0304B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0304B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0304B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0304B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0304B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0304B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0304B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0304B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0304B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0304B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0304B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0304B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0304B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0304B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0501 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0501 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0501 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0501 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0501 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0501 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0501 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0501 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0501 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0501 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0501 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0501 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0501 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0501 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0502 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0502 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0502 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0502 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0502 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0502 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0502 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0502 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0502 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0502 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0502 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0502 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0502 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0502 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0503 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0503 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0503 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0503 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0503 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0503 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0503 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0503 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0503 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0503 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0503 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0503 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0503 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0503 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0504 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0504 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0504 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0504 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0504 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0504 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0504 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0504 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0504 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0504 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0504 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0504 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0504 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0504 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0505 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0505 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0505 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0505 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0505 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0505 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0505 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0505 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0505 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0505 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0505 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0505 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0505 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0505 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0506 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0506 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0506 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0506 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0506 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0506 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0506 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0506 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0506 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0506 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0506 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0506 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0506 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0506 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0507 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0507 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0507 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0507 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0507 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0507 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0507 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0507 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0507 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0507 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0507 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0507 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0507 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0507 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0508 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0508 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0508 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0508 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0508 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0508 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0508 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0508 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0508 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0508 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0508 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0508 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0508 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0508 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0601A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0601A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0601A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0601A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0601A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0601A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0601A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0601A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0601A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0601A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0601A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0601A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0601A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0601A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 3 | DR |  | WIL23 | NO | 131237-WIL23-DR-I-XXXX | General Arrangement and Wiring Diagram For RIO Panel WIL23-RIO-0601B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Cover Sheet For RIO Panel WIL23-RIO-0601B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Revision Index For RIO Panel WIL23-RIO-0601B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Bill Of Materials For RIO Panel WIL23-RIO-0601B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Control Cabinet - External View For RIO Panel WIL23-RIO-0601B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Nameplate Details For RIO Panel WIL23-RIO-0601B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Wiring Color Coding Scheme For RIO Panel WIL23-RIO-0601B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Legend For RIO Panel WIL23-RIO-0601B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 230VAC Power Distribution For RIO Panel WIL23-RIO-0601B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | 24VDC Supply Distribution For RIO Panel WIL23-RIO-0601B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | I/O Cluster Interconnection For RIO Panel WIL23-RIO-0601B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Rack Wiring Diagram For RIO Panel WIL23-RIO-0601B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Earth Bar Connection Diagram For RIO Panel WIL23-RIO-0601B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | Safety Barrier Wiring Digram For RIO Panel WIL23-RIO-0601B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-04-01 | ICA | Stage 2 | DR |  | WSW46 | NO | 131236-WSW46-DR-I-XXXX | FO Termination Drawing | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | DR |  | WSW46 | NO | 131236-WSW46-DR-I-XXXX | Cable Routing Drawing - Signal & Control | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | DR |  | WSW46 | NO | 131236-WSW46-DR-I-XXXX | Cable Routing Drawing - Power | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | DR |  | WSW46 | NO | 131236-WSW46-DR-I-XXXX | Cable Routing Drawing - FO | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | DR |  | WIL00 | NO | 131236-WIL00-DR-I-XXXX | WIL00 Instrument Location Layout | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | DR |  | WIL06 | NO | 131236-WIL06-DR-I-XXXX | WIL06 Instrument Location Layout | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | WIL21 Instrument Location Layout | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | WIL22 Instrument Location Layout | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | WIL23 Instrument Location Layout | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | DR |  | WNS03 | NO | 131236-WNS03-DR-I-XXXX | WNS03 Instrument Location Layout | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | DR |  | WIL00 | NO | 131236-WIL00-DR-I-XXXX | WIL00 Panel Location Layout | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | DR |  | WIL06 | NO | 131236-WIL06-DR-I-XXXX | WIL06 Panel Location Layout | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | DR |  | WIL21 | NO | 131236-WIL21-DR-I-XXXX | WIL21 Panel Location Layout | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | DR |  | WIL22 | NO | 131236-WIL22-DR-I-XXXX | WIL22 Panel Location Layout | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | DR |  | WIL23 | NO | 131236-WIL23-DR-I-XXXX | WIL23 Panel Location Layout | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | ICA | Stage 2 | DR |  | WNS03 | NO | 131236-WNS03-DR-I-XXXX | WNS03 Panel Location Layout | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WSW46 | YES | 131236-WSW46-QA-I-XXXX | Inspection Test Plan (ITP) For RIO Panel | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WSW46 | YES | 131236-WSW46-QA-I-XXXX | Factory Acceptance Test Procedures for RIO Panels | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL21 | YES | 131236-WIL21-QA-I-XXXX | Vendor Manufacturing Inspection and Toxicity Analyzer | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131236-WIL23-QA-I-XXXX | Vendor Manufacturing Inspection and ORP Analyzer | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WSW46 | YES | 131236-WSW46-QA-I-XXXX | Vendor Manufacturing Inspection and Test Procedure For Pressure Gauge | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL21 | YES | 131236-WIL21-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For H2S Gas Detector | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL21 | YES | 131236-WIL21-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Carbon Monoxide Gas Detector | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL21 | YES | 131236-WIL21-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For VOC Analyses | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL21 | YES | 131236-WIL21-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For LEL Gas Detectors | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WSW46 | YES | 131236-WSW46-QA-I-XXXX | Factory Acceptance Test Procedure for VMS for IGV Blowers | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WNS03 | YES | 131236-WNS03-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Magnetic Level Indicator | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WSW46 | YES | 131236-WSW46-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Fiber Optic and CAT 6A Cables | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL22 | YES | 131236-WIL22-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Total Solid Meter | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WSW46 | YES | 131236-WSW46-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Room Temperature Transmitter | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WSW46 | YES | 131236-WSW46-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For FFOTP Panels | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WSW46 | YES | 131236-WSW46-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For FOIP Panels | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131236-WIL23-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Ammonium Analyser | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131236-WIL23-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Nitrate Analyser | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WSW46 | YES | 131236-WSW46-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For ICA Cable Raceway | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WSW46 | YES | 131236-WSW46-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For ICA Power and Control Cable | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL22 | YES | 131236-WIL22-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Sludge Blanket Level Switch | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WSW46 | YES | 131236-WSW46-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Leak Detector Sensor | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL21 | YES | 131236-WIL21-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Truck Position Sensor | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL21 | YES | 131236-WIL21-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Motion Sensor | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WSW46 | YES | 131236-WSW46-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Conductive Probe Level Switch | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131236-WIL23-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Turning Fork Level Switch | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WSW46 | YES | 131236-WSW46-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Local Display | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL21 | YES | 131236-WIL21-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Flammable (LEL) Gas Detector | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL21 | YES | 131236-WIL21-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For CO Gas Detector | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL21 | YES | 131237-WIL21-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For H2S Gas Detector | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL21 | YES | 131238-WIL21-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Motion Switch | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WSW46 | YES | 131239-WSW46-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Low Point Leak Detector | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WSW46 | YES | 131240-WSW46-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Pressure Gauge | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WSW46 | YES | 131241-WSW46-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Temperature Transmitter c/w RTD | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WSW46 | YES | 131242-WSW46-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Pressure Transmitter | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WSW46 | YES | 131243-WSW46-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Level Transmitter Radar (Non-Contacting) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WSW46 | YES | 131244-WSW46-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Pressure Switch | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WSW46 | YES | 131245-WSW46-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Level Transmitter – RF Admittance | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WSW46 | YES | 131246-WSW46-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Auto Sampler | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WSW46 | YES | 131247-WSW46-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Thermal Mass Flowmeter | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WSW46 | YES | 131248-WSW46-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Thermal Flow Switch | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WSW46 | YES | 131249-WSW46-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Turbidity Analyser | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WSW46 | YES | 131251-WSW46-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For pH Analyser | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL21 | YES | 131253-WIL21-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Weight Transmitter | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL21 | YES | 131254-WIL21-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Toxicity Analyser | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL21 | YES | 131255-WIL21-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Volatile Organic Compound (VOC) Gas Analyser | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL22 | YES | 131256-WIL22-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Total Solid Analyser | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL22 | YES | 131257-WIL22-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Level Switch Sludge Blanket – Ultrasonic | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131258-WIL23-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Level Switch – Tuning Fork | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131259-WIL23-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Orthophosphate Analyser | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131260-WIL23-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Conductivity Analyser | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131261-WIL23-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For ORP Analyser | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131262-WIL23-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Total Suspended Solid (MLSS) Analyser | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131263-WIL23-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Ammonia Analyser | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131264-WIL23-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Dissolved Oxygen Analyser | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131265-WIL23-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Nitrate / Nitrite Analyser | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WNS03 | YES | 131266-WNS03-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Differential Pressure Transmitter | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WSW46 | YES | 131267-WSW46-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Local Display | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WSW46 | YES | 131268-WSW46-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Rotameter c/w Flow (Reed) Switch | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WSW46 | YES | 131269-WSW46-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Flowmeter - Electromagnetic | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WSW46 | YES | 131270-WSW46-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Flowmeter - Open Channel Ultrasonic | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL21 | YES | 131271-WIL21-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Truck Position Sensor | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131272-WIL23-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Limit Switch | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL22 | YES | 131273-WIL22-QA-I-XXXX | Vendor Manufacturing Inspection and Test Plan For Level Switch - Ultrasonic | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL06 | YES | 131273-WIL06-QA-I-XXXX | FAT Report For RIO Panel WIL06-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL06 | YES | 131273-WIL06-QA-I-XXXX | FAT Report For RIO Panel WIL06-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL21 | YES | 131273-WIL21-QA-I-XXXX | FAT Report For RIO Panel WIL21-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL21 | YES | 131273-WIL21-QA-I-XXXX | FAT Report For RIO Panel WIL21-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL21 | YES | 131273-WIL21-QA-I-XXXX | FAT Report For RIO Panel WIL21-RIO-0301A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL21 | YES | 131273-WIL21-QA-I-XXXX | FAT Report For RIO Panel WIL21-RIO-0301B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL21 | YES | 131273-WIL21-QA-I-XXXX | FAT Report For RIO Panel WIL21-RIO-0302A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL21 | YES | 131273-WIL21-QA-I-XXXX | FAT Report For RIO Panel WIL21-RIO-0302B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL21 | YES | 131273-WIL21-QA-I-XXXX | FAT Report For RIO Panel WIL21-RIO-0303A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL21 | YES | 131273-WIL21-QA-I-XXXX | FAT Report For RIO Panel WIL21-RIO-0303B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL21 | YES | 131273-WIL21-QA-I-XXXX | FAT Report For RIO Panel WIL21-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL21 | YES | 131273-WIL21-QA-I-XXXX | FAT Report For RIO Panel WIL21-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL22 | YES | 131273-WIL22-QA-I-XXXX | FAT Report For RIO Panel WIL22-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL22 | YES | 131273-WIL22-QA-I-XXXX | FAT Report For RIO Panel WIL22-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL22 | YES | 131273-WIL22-QA-I-XXXX | FAT Report For RIO Panel WIL22-RIO-0103A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL22 | YES | 131273-WIL22-QA-I-XXXX | FAT Report For RIO Panel WIL22-RIO-0103B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL22 | YES | 131273-WIL22-QA-I-XXXX | FAT Report For RIO Panel WIL22-RIO-0104A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL22 | YES | 131273-WIL22-QA-I-XXXX | FAT Report For RIO Panel WIL22-RIO-0104B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL22 | YES | 131273-WIL22-QA-I-XXXX | FAT Report For RIO Panel WIL22-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL22 | YES | 131273-WIL22-QA-I-XXXX | FAT Report For RIO Panel WIL22-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0101A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0101B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0102A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0102B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0201 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0202 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0203 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0204A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0204B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0401 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0402 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0403 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0404 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0405 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0406 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0407 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0408 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0409 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0410 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0001A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0001B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0301 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0302 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0303 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0304A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0304B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0501 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0502 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0503 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0504 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0505 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0506 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0507 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0508 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0002A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0002B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0601A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | ICA | Stage 3 | QA |  | WIL23 | YES | 131273-WIL23-QA-I-XXXX | FAT Report For RIO Panel WIL23-RIO-0601B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 5 | MS |  | WSW46 | NO | 131273-WSW46-MS-I-XXXX | MSRA For Installation, Testing & Commissioning of ICA Works | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 5 | MS |  | WSW46 | NO | 131273-WSW46-MS-I-XXXX | MSRA For Installation of cable raceways and cables, panels and instruments for ICA Works | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 5 | MS |  | WSW46 | NO | 131273-WSW46-MS-I-XXXX | MSRA For Loading and Unloading the Cable Raceway Materials from Container | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 5 | MS |  | WSW46 | NO | 131273-WSW46-MS-I-XXXX | MSRA For Erection, Modification and Dismantling of Scaffold | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | ICA | Stage 5 | MS |  | WSW46 | NO | 131273-WSW46-MS-I-XXXX | MSRA For Installation, Testing & Commissioning Of ICA Panel Works | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | ICA | Stage 6 | PQ |  |  |  | 131236-PQ-I | [9 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 1 | VI | Centrifugal Pump | WSW46 |  | 131236-WSW46-VI-M-XXXX | Vendor Approval - Centrifugal Pumps | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 1 | VI | Vertical Turbine Pumps | WIL23 |  | 131236-WIL23-VI-M-XXXX | Vendor Approval - Vertical Turbine Pumps | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 1 | VI | Concentric Tubular Casing Submersible Pump | WIL23 |  | 131236-WIL23-VI-M-XXXX | Vendor Approval - Concentric Tubular Casing Submersible Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 1 | VI | Screw Induced Flow Pumps | WSW46 |  | 131236-WSW46-VI-M-XXXX | Vendor Approval - Screw Induced Flow Pumps | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 1 | VI | Submersible Pumps | WIL23 |  | 131236-WIL23-VI-M-XXXX | Vendor Approval - Submersible Pumps | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 1 | VI | Double Disc Centrifugal Pumps | WSW46 |  | 131236-WSW46-VI-M-XXXX | Vendor Approval - Double Disc Centrifugal Pumps | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 1 | VI | Sump Dewatering Pumps | WIL21 |  | 131236-WIL21-VI-M-XXXX | Vendor Approval - Sump Dewatering Pumps | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 1 | VI | Recessed Impellel Pump | WIL21 |  | 131236-WIL21-VI-M-XXXX | Vendor Approval - Recessed Impellel Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Process | Stage 1 | VI | Progressive Cavity Pump | WIL21 |  | 131236-WIL21-VI-M-XXXX | Vendor Approval - Progressive Cavity Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Process | Stage 1 | VI | Chemical Dosing Pump | WIL06 |  | 131236-WIL06-VI-M-XXXX | Vendor Approval - Chemical Dosing Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Process | Stage 1 | VI | Compressed Air System | WIL23 |  | 131236-WIL23-VI-M-XXXX | Vendor Approval - Compressed Air System Including Compressors, Air Dryers and Air Receiver Tanks | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-03-01 | Process | Stage 1 | VI | Hyperboloid Mixer | WIL23 |  | 131236-WIL23-VI-M-0001 | Vendor Information - Hyperbolic Mixer (INVENT UMWELT- UND VERFAHRENSTECHNIK AG) | [8 empty] | NTS - No Resubmission Required | APP - Approved |  |  |  | 0 | 1
Planned | 2026-07-01 | Process | Stage 1 | VI | Diffuser | WSW46 |  | 131236-WSW46-VI-M-0001 | Vendor Information For Diffusers (Air Diffuser – Grit System and Bioreactors) (ENVIRONMENTAL DYNAMICS INTERNATIONAL, INC (EDI)) | [8 empty] | RTR - Returned for Resubmission | AWC - Approved with Comments |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 1 | VI | High Speed Turbo Blower | WIL21 |  | 131236-WIL21-VI-M-XXXX | Vendor Approval - High Speed Turbo Blower (Grit Aeration Blower) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 1 | VI | Integrally Geared Blowers | WIL23 |  | 131236-WIL23-VI-M-XXXX | Vendor Approval-Integrally Single Stage Centrifugal Geared Air Blower Sub System Works IGV Blower | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-07-01 | Process | Stage 1 | VI | PST Lamella/Scraper/Scum Collector | WIL22 |  | 131236-WIL22-VI-M-0001 | Vendor Information For Lamella Settlement, Lamella support structure, PST Sludge Scraper and PST Scum Skimming and Removal System (Nova Industries International L.L.C-FZ) | [8 empty] | RTR - Returned for Resubmission | AWC - Approved with Comments |  |  |  | 0 | 1
Planned | 2026-06-01 | Process | Stage 1 | VI | MFS (Polymeric Membrane) | WIL23 |  | 131236-WIL23-VI-M-0002 | Vendor Information For Design, Manufacturing, FAT, Supply & Delivery of MFS (Membrane) (Veolia Water Technologies & Solutions (Singapore) Pte Ltd) | [8 empty] | RTR - Returned for Resubmission | AWC - Approved with Comments |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 1 | VI | Valve | WSW46 |  | 131236-WSW46-VI-M-XXXX | Vendor Approval - Air Flow Control Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | Process | Stage 1 | VI | Valve | WSW46 |  | 131236-WSW46-VI-M-XXXX | Vendor Approval - Liquid Flow Control Valves And Actuators | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | Process | Stage 1 | VI | Valve | WSW46 |  | 131236-WSW46-VI-M-XXXX | Preliminary Design Submission For Design, Supply, Manufacturing, Factory Acceptance Test, Delivery Of Accumulators | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | Process | Stage 1 | VI | Ejector | WIL23 |  | 131236-WIL23-VI-M-XXXX | Vendor Approval - MFS Air Ejector | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DS | Centrifugal Pump | WIL00 |  | 131236-WIL00-DS-M-XXXX | Datasheet - ILM2 Plant Water High Pressure Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DS | Centrifugal Pump | WIL23 |  | 131236-WIL23-DS-M-XXXX | Datasheet - ILM2 Membrane Cleaning Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DS | Centrifugal Pump | WIL23 |  | 131236-WIL23-DS-M-XXXX | Datasheet - ILM2 MBR Filtrate Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DS | Vertical Turbine Pumps | WIL23 |  | 131236-WIL23-DS-M-XXXX | Datasheet - ILM2 G2I Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DS | Concentric Tubular Casing Submersible Pump | WIL23 |  | 131236-WIL23-DS-M-XXXX | Datasheet - ILM2 DEOX/RAS Tank RAS Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DS | Concentric Tubular Casing Submersible Pump | WIL23 |  | 131236-WIL23-DS-M-XXXX | Datasheet - ILM2 Mixed Liquor Return Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DS | Screw Induced Flow Pumps | WIL21 |  | 131236-WIL21-DS-M-XXXX | Datasheet - ILM Plant Drainage PS Wet Well Compartment 2 Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DS | Screw Induced Flow Pumps | WIL22 |  | 131236-WIL22-DS-M-XXXX | Datasheet - ILM2 PST Primary Sludge Transfer Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DS | Screw Induced Flow Pumps | WIL23 |  | 131236-WIL23-DS-M-XXXX | Datasheet - ILM2 WAS Wet Well WAS Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DS | Submersible Pumps | WIL23 |  | 131236-WIL23-DS-M-XXXX | Datasheet - ILM2 Bioreactor Drainage Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DS | Submersible Pumps | WIL23 |  | 131236-WIL23-DS-M-XXXX | Datasheet - ILM2 DEOX/RAS Tank Drainage Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DS | Submersible Pumps | WIL23 |  | 131236-WIL23-DS-M-XXXX | Datasheet - ILM2 MBR Filtrate Tank Drainage Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DS | Double Disc Centrifugal Pumps | WIL21 |  | 131236-WIL21-DS-M-XXXX | Datasheet - ILM2 Grease and Scum Wet Well Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DS | Double Disc Centrifugal Pumps | WIL22 |  | 131236-WIL22-DS-M-XXXX | Datasheet - ILM2 Primary Scum Wet Well Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DS | Double Disc Centrifugal Pumps | WIL23 |  | 131236-WIL23-DS-M-XXXX | Datasheet - ILM2 Membrane Scum Wet Well Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DS | Recessed Impeller Pump | WIL21 |  | 131236-WIL21-DS-M-XXXX | Datasheet - ILM2 Influent Flowmeter Chamber Drainage Sump Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DS | Recessed Impeller Pump | WIL21 |  | 131236-WIL21-DS-M-XXXX | Datasheet - ILM2 Grit Tank Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Process | Stage 2 | DS | Progressive Cavity Pump | WIL21 |  | 131236-WIL21-DS-M-XXXX | Datasheet - ILM2 Grit Tanks Inlet Sampling Point Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Process | Stage 2 | DS | Progressive Cavity Pump | WIL22 |  | 131236-WIL22-DS-M-XXXX | Datasheet - ILM2 PSI Transfer Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Process | Stage 2 | DS | Progressive Cavity Pump | WIL23 |  | 131236-WIL23-DS-M-XXXX | Datasheet - ILM2 Bioreactor Sampling Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Process | Stage 2 | DS | Progressive Cavity Pump | WIL23 |  | 131236-WIL23-DS-M-XXXX | Datasheet - ILM2 MBR Filtrate Tank Membrane Filtrate Sampling Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Process | Stage 2 | DS | Chemical Dosing Pump | WIL06 |  | 131236-WIL06-DS-M-XXXX | Datasheet - ILM2 MFS Citric Acid Dosing Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Process | Stage 2 | DS | Chemical Dosing Pump | WIL06 |  | 131236-WIL06-DS-M-XXXX | Datasheet - ILM2 MFS Sodium Hypochlorite Dosing Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Process | Stage 2 | DS | Compressed Air System | WIL23 |  | 131236-WIL23-DS-M-XXXX | Datasheet - ILM2 Air Compressor | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Process | Stage 2 | DS | Compressed Air System | WIL23 |  | 131236-WIL23-DS-M-XXXX | Datasheet - ILM2 Air Dryer | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Process | Stage 2 | DS | Compressed Air System | WIL23 |  | 131236-WIL23-DS-M-XXXX | Datasheet - ILM2 Air Receiver Tank | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 2 | DS | Compressed Air System | WNS03 |  | 131236-WNS03-DS-M-XXXX | Datasheet - Portable Compressure for Surge Tank | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-08-01 | Process | Stage 2 | DS | Hyperboloid Mixer | WIL23 |  | 131236-WIL23-DS-M-0001 | Datasheet - ILM2 Bioreactor Mixed Liquor Mixer | [8 empty] | SUR - Under SO Review | AWC - Approved with Comments |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DS | Diffuser | WIL21 |  | 131236-WIL21-DS-M-XXXX | Datasheet - ILM2 Coarse Bubble Diffusers (Common Grit Tank Inlet Channel, Aeration Grit Tanks, Common Grit Tank Effluent Channel) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DS | Diffuser | WIL23 |  | 131236-WIL23-DS-M-XXXX | Datasheet - ILM2 Bioreactor Tank Fine Bubble Diffuser | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | DS | High Speed Turbo Blower | WIL21 |  | 131236-WIL21-DS-M-XXXX | Datasheet - ILM2 Grit Air Blower | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | DS | Integrally Geared Blowers | WIL23 |  | 131236-WIL23-DS-M-XXXX | Datasheet - ILM2 Bioreactor Process Aeration Blowers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | DS | Integrally Geared Blowers | WIL23 |  | 131236-WIL23-DS-M-XXXX | Datasheet - ILM2 Membrane Air Scour Blowers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 2 | DS | PST Lamella/Scraper/Scum Collector | WIL22 |  | 131236-WIL22-DS-M-XXXX | Datasheet - ILM2 Primary Sedimentation Tank Lamella Settlement System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DS | MFS (Polymeric Membrane) | WIL23 |  | 131236-WIL23-DS-M-XXXX | Datasheet - MFS (Membrane) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DS | Valve | WIL21 |  | 131236-WIL21-DS-M-XXXX | Datasheet - ILM2 Grit Tank Aeration Flow Control Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Process | Stage 2 | DS | Valve | WIL23 |  | 131236-WIL23-DS-M-XXXX | Datasheet - ILM2 Bioreactor Tank Aeration Flow Control Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Process | Stage 2 | DS | Valve | WSW46 |  | 131236-WSW46-DS-M-XXXX | Datasheet - Accumulators | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Process | Stage 2 | DS | Ejector | WIL23 |  | 131236-WIL23-DS-M-XXXX | Datasheet - ILM2 MBR Filtrate Air Ejector | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 2 | DS | Penstock | WIL23 |  | 131236-WIL23-DS-M-XXXX | Datasheet - ILM2 Membrane Scum Wet Well Penstock | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 2 | DS | Penstock | WIL23 |  | 131236-WIL23-DS-M-XXXX | Datasheet - ILM2 MBR Fine Screens Common Outlet Penstock | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | CL | Centrifugal Pump | WIL00 |  | 131236-WIL00-CL-M-XXXX | Pump Head Calculation - ILM2 Plant Water High Pressure Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | CL | Centrifugal Pump | WIL23 |  | 131236-WIL23-CL-M-XXXX | Pump Head Calculation - ILM2 Membrane Cleaning Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | CL | Centrifugal Pump | WIL23 |  | 131236-WIL23-CL-M-XXXX | Pump Head Calculation - ILM2 MBR Filtrate Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | CL | Centrifugal Pump | WIL23 |  | 131236-WIL23-CL-M-XXXX | Study Report - Membrane Filtrate Pumping System Surge Analysis | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Process | Stage 2 | CL | MBR Filtrate Tank | WIL23 |  | 131236-WIL23-CL-M-XXXX | Study Report - Membrane Filtrate Tank CFD Modelling | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | CL | Vertical Turbine Pumps | WIL23 |  | 131236-WIL23-CL-M-XXXX | Pump Head Calculation - ILM2 G2I Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-04-01 | Process | Stage 2 | CL | Vertical Turbine Pumps | WIL23 |  | 131236-WIL23-CL-M-XXXX | Study Report - G2I Pumping System Surge Analysis | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | CL | Concentric Tubular Casing Submersible Pump | WIL23 |  | 131236-WIL23-CL-M-XXXX | Pump Head Calculation - ILM2 DEOX/RAS Tank RAS Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | CL | Concentric Tubular Casing Submersible Pump | WIL23 |  | 131236-WIL23-CL-M-XXXX | Study Report - RAS Pumping System Surge Analysis | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | CL | Concentric Tubular Casing Submersible Pump | WIL23 |  | 131236-WIL23-CL-M-XXXX | Pump Head Calculation - ILM2 Mixed Liquor Return Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | CL | Screw Induced Flow Pumps | WIL21 |  | 131236-WIL21-CL-M-0008 | Pump Head Calculation - ILM Plant Drainage PS Wet Well Compartment 2 Pump | [8 empty] | SUR - Under SO Review | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | CL | Screw Induced Flow Pumps | WIL22 |  | 131236-WIL22-CL-M-XXXX | Pump Head Calculation - ILM2 PST Primary Sludge Transfer Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | CL | Screw Induced Flow Pumps | WIL23 |  | 131236-WIL23-CL-M-XXXX | Pump Head Calculation - ILM2 WAS Wet Well WAS Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-04-01 | Process | Stage 2 | CL | Screw Induced Flow Pumps | WIL23 |  | 131236-WIL23-CL-M-XXXX | Study Report - WAS Pumping System Surge Analysis | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | CL | Submersible Pumps | WIL23 |  | 131236-WIL23-CL-M-0005 | Pump Head Calculation - ILM2 Bioreactor Drainage Pump | [8 empty] | SUR - Under SO Review | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | CL | Submersible Pumps | WIL23 |  | 131236-WIL23-CL-M-0006 | Pump Head Calculation - ILM2 DEOX/RAS Tank Drainage Pump | [8 empty] | SUR - Under SO Review | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | CL | Submersible Pumps | WIL23 |  | 131236-WIL23-CL-M-0007 | Pump Head Calculation - ILM2 MBR Filtrate Tank Drainage Pump | [8 empty] | SUR - Under SO Review | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | CL | Double Disc Centrifugal Pumps | WIL21 |  | 131236-WIL21-CL-M-0009 | Pump Head Calculation - ILM2 Grease and Scum Wet Well Pump | [8 empty] | SUR - Under SO Review | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | CL | Double Disc Centrifugal Pumps | WIL22 |  | 131236-WIL22-CL-M-0001 | Pump Head Calculation - ILM2 Primary Scum Wet Well Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | CL | Double Disc Centrifugal Pumps | WIL23 |  | 131236-WIL23-CL-M-0008 | Pump Head Calculation - ILM2 Membrane Scum Wet Well Pump | [8 empty] | SUR - Under SO Review | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 1 | CL | Recessed Impeller Pump | WIL21 |  | 131236-WIL21-CL-M-0007 | Pump Head Calculation - ILM2 Influent Flowmeter Chamber Drainage Sump Pump | [8 empty] | SUR - Under SO Review | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 1 | CL | Recessed Impeller Pump | WIL21 |  | 131236-WIL21-CL-M-XXXX | Pump Head Calculation - ILM2 Grit Tank Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | CL | Progressive Cavity Pump | WIL21 |  | 131236-WIL21-CL-M-XXXX | Pump Head Calculation - ILM2 Grit Tanks Inlet Sampling Point Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | CL | Progressive Cavity Pump | WIL22 |  | 131236-WIL22-CL-M-XXXX | Pump Head Calculation - ILM2 PSI Transfer Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Process | Stage 2 | CL | Progressive Cavity Pump | WIL22 |  | 131236-WIL22-CL-M-XXXX | Study Report - PSI Transfer Pumping System Surge Analysis | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | CL | Progressive Cavity Pump | WIL23 |  | 131236-WIL23-CL-M-XXXX | Pump Head Calculation - ILM2 Bioreactor Sampling Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | CL | Progressive Cavity Pump | WIL23 |  | 131236-WIL23-CL-M-XXXX | Pump Head Calculation - ILM2 MBR Filtrate Tank Membrane Filtrate Sampling Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-10-01 | Process | Stage 2 | CL | Chemical Dosing Pump | WIL06 |  | 131236-WIL06-CL-M-XXXX | Pump Head Calculation - ILM2 MFS Citric Acid Dosing Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Process | Stage 2 | CL | Chemical Dosing Pump | WIL06 |  | 131236-WIL06-CL-M-XXXX | Pump Head Calculation - ILM2 MFS Sodium Hypochlorite Dosing Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Process | Stage 2 | CL | Compressed Air System | WIL23 |  | 131236-WIL23-CL-M-XXXX | ILM2 Air Compressor Sizing Calculation | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-06-01 | Process | Stage 2 | CL | Hyperboloid Mixer | WIL23 |  | 131236-WIL23-CL-M-0001 | Study Report - Anoxic Tank Mixing CFD Modelling | [8 empty] | SUR - Under SO Review | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | CL | High Speed Turbo Blower | WIL21 |  | 131236-WIL21-CL-M-XXXX | Blower Head Calculation - ILM2 Grit Air Blower | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | CL | High Speed Turbo Blower | WIL21 |  | 131236-WIL21-CL-M-XXXX | Grit Blower Intake Lourve Size Calculation | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | CL | Integrally Geared Blowers | WIL23 |  | 131236-WIL23-CL-M-XXXX | Blower Head Calculation - ILM2 Bioreactor Process Aeration Blowers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | CL | Integrally Geared Blowers | WIL23 |  | 131236-WIL23-CL-M-XXXX | Blower Head Calculation - ILM2 Membrane Air Scour Blowers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | CL | MFS (Polymeric Membrane) | WIL23 |  | 131236-WIL23-CL-M-XXXX | Calculation Report For Membrane Cassettes (Polymeric Membrane) Steel Structure | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | CL | MFS (Polymeric Membrane) | WIL23 |  | 131236-WIL23-CL-M-XXXX | MBR Tank Grating Cover Design Calculation | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-08-01 | Process | Stage 2 | CL | Foul Air Pipeworks | WSW46 |  | 131236-WSW46-CL-M-0002 | Calculation For Foul Air Pipeworks Pressure Drop Calculation For ILM2 OCF1 | [8 empty] | SUR - Under SO Review | INF - For Information |  |  |  | 0 | 1
Planned | 2026-09-01 | Process | Stage 2 | CL | Foul Air Pipeworks | WSW46 |  | 131236-WSW46-CL-M-0003 | Calculation For Foul Air Pipeworks Pressure Drop Calculation For ILM2 OCF2 | [8 empty] | SUR - Under SO Review | NAP - Not Approved |  |  |  | 0 | 1
Planned | 2026-08-01 | Process | Stage 2 | CL |  | WIL21 |  | 131236-WIL21-CL-M-0001 | DPS And Intake Chamber Pipe Size Calculation | [8 empty] | SUR - Under SO Review | INF - For Information |  |  |  | 0 | 1
Planned | 2026-08-01 | Process | Stage 2 | CL |  | WIL21 |  | 131236-WIL21-CL-M-0002 | Intermediate Screen Area Pipe Size Calculation | [8 empty] | RTR - Returned for Resubmission | INF - For Information |  |  |  | 0 | 1
Planned | 2026-08-01 | Process | Stage 2 | CL |  | WIL21 |  | 131236-WIL21-CL-M-0003 | Fine Screen Area Pipe Size Calculation | [8 empty] | RTR - Returned for Resubmission | INF - For Information |  |  |  | 0 | 1
Planned | 2026-08-01 | Process | Stage 2 | CL |  | WIL21 |  | 131236-WIL21-CL-M-0004 | Aerated Grit Tank Area Pipe Size Calculation | [8 empty] | RTR - Returned for Resubmission | INF - For Information |  |  |  | 0 | 1
Planned | 2026-08-01 | Process | Stage 2 | CL |  | WIL21 |  | 131236-WIL21-CL-M-0005 | Grit Classifier & Hopper Area Pipe Size Calculation | [8 empty] | RTR - Returned for Resubmission | INF - For Information |  |  |  | 0 | 1
Planned | 2026-08-01 | Process | Stage 2 | CL |  | WIL21 |  | 131236-WIL21-CL-M-0006 | Headworks Grease and Scum Wet Well Area Pipe Size Calculation | [8 empty] | RTR - Returned for Resubmission | INF - For Information |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | CL |  | WIL22 |  | 131236-WIL22-CL-M-XXXX | PSI Tank&PSI Transfer Pump Pipe Size Calculation | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | Process | Stage 2 | CL |  | WIL23 |  | 131236-WIL23-CL-M-0001 | MBR Fine Screen & Bioreactor Pipe Size Calculation | [8 empty] | SUR - Under SO Review | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | Process | Stage 2 | CL |  | WIL23 |  | 131236-WIL23-CL-M-0002 | Membrane Area Pipe Size Calculation | [8 empty] | SUR - Under SO Review | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | Process | Stage 2 | CL |  | WIL23 |  | 131236-WIL23-CL-M-0003 | MBR Filtrate Tank & Transfer Pump Pipe Size Calculation | [8 empty] | SUR - Under SO Review | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | Process | Stage 2 | CL |  | WIL23 |  | 131236-WIL23-CL-M-0004 | WAS, RAS & Mixed Liquor Wet Well Pipe Size Calculation | [8 empty] | SUR - Under SO Review | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Process | Stage 2 | CL |  | WIL23 |  | 131236-WIL23-CL-M-XXXX | Compressed Air System Pipe Size Calculation | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | CL |  | WIL00 |  | 131236-WIL00-CL-M-XXXX | Plant Water Pipe Size Calculation | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | CL |  | WIL06 |  | 131236-WIL06-CL-M-XXXX | Chemical Dosing System Pipe Size Calculation | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Centrifugal Pump | WIL00 |  | 131236-WIL00-DR-M-XXXX | GA Drawing - ILM2 Plant Water High Pressure Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Centrifugal Pump | WIL00 |  | 131236-WIL00-DR-M-XXXX | GA Drawing - ILM2 Plant Water High Pressure Pump Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Centrifugal Pump | WIL00 |  | 131236-WIL00-DR-M-XXXX | High Pressure Pump Setting Out Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Centrifugal Pump | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 Membrane Cleaning Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Centrifugal Pump | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 Membrane Cleaning Pump Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Centrifugal Pump | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 MBR Filtrate Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Centrifugal Pump | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 MBR Filtrate Pump Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Vertical Turbine Pumps | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 G2I Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Vertical Turbine Pumps | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 G2I Pump Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Concentric Tubular Casing Submersible Pump | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 DEOX/RAS Tank RAS Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Concentric Tubular Casing Submersible Pump | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 DEOX/RAS Tank RAS Pump Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Concentric Tubular Casing Submersible Pump | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 Mixed Liquor Return Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Concentric Tubular Casing Submersible Pump | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 Mixed Liquor Return Pump Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Screw Induced Flow Pumps | WIL21 |  | 131236-WIL21-DR-M-XXXX | GA Drawing - ILM Plant Drainage PS Wet Well Compartment 2 Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Screw Induced Flow Pumps | WIL21 |  | 131236-WIL21-DR-M-XXXX | GA Drawing - ILM Plant Drainage PS Wet Well Compartment 2 Pump Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Screw Induced Flow Pumps | WIL22 |  | 131236-WIL22-DR-M-XXXX | GA Drawing - ILM2 PST Primary Sludge Transfer Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Screw Induced Flow Pumps | WIL22 |  | 131236-WIL22-DR-M-XXXX | GA Drawing - ILM2 PST Primary Sludge Transfer Pump Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Screw Induced Flow Pumps | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 WAS Wet Well WAS Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Screw Induced Flow Pumps | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 WAS Wet Well WAS Pump Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Submersible Pumps | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 Bioreactor Drainage Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Submersible Pumps | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 Bioreactor Drainage Pump Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Submersible Pumps | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 DEOX/RAS Tank Drainage Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Submersible Pumps | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 DEOX/RAS Tank Drainage Pump Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Submersible Pumps | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 MBR Filtrate Tank Drainage Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Submersible Pumps | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 MBR Filtrate Tank Drainage Pump Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Double Disc Centrifugal Pumps | WIL21 |  | 131236-WIL21-DR-M-XXXX | GA Drawing - ILM2 Grease and Scum Wet Well Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Double Disc Centrifugal Pumps | WIL21 |  | 131236-WIL21-DR-M-XXXX | GA Drawing - ILM2 Grease and Scum Wet Well Pump Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Double Disc Centrifugal Pumps | WIL22 |  | 131236-WIL22-DR-M-XXXX | GA Drawing - ILM2 Primary Scum Wet Well Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Double Disc Centrifugal Pumps | WIL22 |  | 131236-WIL22-DR-M-XXXX | GA Drawing - ILM2 Primary Scum Wet Well Pump Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Double Disc Centrifugal Pumps | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 Membrane Scum Wet Well Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Double Disc Centrifugal Pumps | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 Membrane Scum Wet Well Pump Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 1 | DR | Recessed Impeller Pump | WIL21 |  | 131236-WIL21-DR-M-XXXX | GA Drawing - ILM2 Influent Flowmeter Chamber Drainage Sump Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 1 | DR | Recessed Impeller Pump | WIL21 |  | 131236-WIL21-DR-M-XXXX | GA Drawing - ILM2 Influent Flowmeter Chamber Drainage Sump Pump Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 1 | DR | Recessed Impeller Pump | WIL21 |  | 131236-WIL21-DR-M-XXXX | GA Drawing - ILM2 Grit Tank Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 1 | DR | Recessed Impeller Pump | WIL21 |  | 131236-WIL21-DR-M-XXXX | GA Drawing - ILM2 Grit Tank Pump Sectional View | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 1 | DR | Recessed Impeller Pump | WIL21 |  | 131236-WIL21-DR-M-XXXX | GA Drawing - ILM2 Grit Tank Pump Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Process | Stage 2 | DR | Progressive Cavity Pump | WIL21 |  | 131236-WIL21-DR-M-XXXX | GA Drawing - ILM2 Grit Tanks Inlet Sampling Point Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Process | Stage 2 | DR | Progressive Cavity Pump | WIL21 |  | 131236-WIL21-DR-M-XXXX | GA Drawing - ILM2 Grit Tanks Inlet Sampling Point Pump Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Process | Stage 2 | DR | Progressive Cavity Pump | WIL22 |  | 131236-WIL22-DR-M-XXXX | GA Drawing - ILM2 PSI Transfer Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Process | Stage 2 | DR | Progressive Cavity Pump | WIL22 |  | 131236-WIL22-DR-M-XXXX | GA Drawing - ILM2 PSI Transfer Pump Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Process | Stage 2 | DR | Progressive Cavity Pump | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 Bioreactor Sampling Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Process | Stage 2 | DR | Progressive Cavity Pump | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 Bioreactor Sampling Pump Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Process | Stage 2 | DR | Progressive Cavity Pump | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 MBR Filtrate Tank Membrane Filtrate Sampling Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Process | Stage 2 | DR | Progressive Cavity Pump | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 MBR Filtrate Tank Membrane Filtrate Sampling Pump Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Process | Stage 2 | DR | Chemical Dosing Pump | WIL06 |  | 131236-WIL06-DR-M-XXXX | GA Drawing - ILM2 MFS Citric Acid Dosing Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Process | Stage 2 | DR | Chemical Dosing Pump | WIL06 |  | 131236-WIL06-DR-M-XXXX | GA Drawing - ILM2 MFS Citric Acid Dosing Pump Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Process | Stage 2 | DR | Chemical Dosing Pump | WIL06 |  | 131236-WIL06-DR-M-XXXX | GA Drawing - ILM2 Citric Acid Hypochlorite Dosing Pump Skid | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Process | Stage 2 | DR | Chemical Dosing Pump | WIL06 |  | 131236-WIL06-DR-M-XXXX | Detail Drawing - ILM2 Citric Acid Hypochlorite Dosing Pump Skid | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Process | Stage 2 | DR | Chemical Dosing Pump | WIL06 |  | 131236-WIL06-DR-M-XXXX | GA Drawing - ILM2 MFS Sodium Hypochlorite Dosing Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Process | Stage 2 | DR | Chemical Dosing Pump | WIL06 |  | 131236-WIL06-DR-M-XXXX | GA Drawing - ILM2 MFS Sodium Hypochlorite Dosing Pump Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Process | Stage 2 | DR | Chemical Dosing Pump | WIL06 |  | 131236-WIL06-DR-M-XXXX | GA Drawing - ILM2 Sodium Hypochlorite Dosing Pump Skid | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Process | Stage 2 | DR | Chemical Dosing Pump | WIL06 |  | 131236-WIL06-DR-M-XXXX | Detail Drawing - ILM2 Sodium Hypochlorite Dosing Pump Skid | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Process | Stage 2 | DR | Compressed Air System | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 Air Compressor | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Process | Stage 2 | DR | Compressed Air System | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 Air Dryer | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Process | Stage 2 | DR | Compressed Air System | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 Air Receiver Tank | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-08-01 | Process | Stage 2 | DR | Hyperboloid Mixer | WIL23 |  | 131236-WIL23-DR-M-5500 | GA Drawing - ILM2 Bioreactor Mixed Liquor Mixer Sheet 1 of 2 | [8 empty] | SUR - Under SO Review | AWC - Approved with Comments |  |  |  | 0 | 1
Planned | 2026-08-01 | Process | Stage 2 | DR | Hyperboloid Mixer | WIL23 |  | 131236-WIL23-DR-M-5501 | GA Drawing - ILM2 Bioreactor Mixed Liquor Mixer Sheet 2 of 2 | [8 empty] | SUR - Under SO Review | AWC - Approved with Comments |  |  |  | 0 | 1
Planned | 2027-03-01 | Process | Stage 2 | DR | Hyperboloid Mixer | WIL23 |  | 131236-WIL23-DR-M-XXXX | ILM2 Maintenance Space For Hyperbolic Mixer | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Process | Stage 2 | DR | Hyperboloid Mixer | WIL23 |  | 131236-WIL23-DR-M-XXXX | ILM2 Plan View For Bioreactor Tank Hyperbolic Mixer 1 Of 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Process | Stage 2 | DR | Hyperboloid Mixer | WIL23 |  | 131236-WIL23-DR-M-XXXX | ILM2 Plan View For Bioreactor Tank Hyperbolic Mixer 2 Of 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | Process | Stage 2 | DR | Hyperboloid Mixer | WIL23 |  | 131236-WIL23-DR-M-XXXX | ILM2 Bioreactor Tank Hyperbolic Mixer Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR | Diffuser | WIL21 |  | 131236-WIL21-DR-M-XXXX | GA Drawing - ILM2 Coarse Bubble Diffusers (Common Grit Tank Inlet Channel, Aeration Grit Tanks, Common Grit Tank Effluent Channel) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Process | Stage 2 | DR | Diffuser | WIL21 |  | 131236-WIL21-DR-M-XXXX | ILM2 Coarse Bubble Diffusers (Common Grit Tank Inlet Channel, Aeration Grit Tanks, Common Grit Tank Effluent Channel) Plan view | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR | Diffuser | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 Bioreactor Tank Fine Bubble Diffuser | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Process | Stage 2 | DR | Diffuser | WIL23 |  | 131236-WIL23-DR-M-XXXX | ILM2 Bioreactor Tank Fine Bubble Diffuser Plan View | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR | Diffuser | WIL23 |  | 131236-WIL23-DR-M-XXXX | FINE BUBBLE DIFFUSERS LIQUID CLEANING SYSTEM | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR | Diffuser | WIL23 |  | 131236-WIL23-DR-M-XXXX | DIFFUSER PRESSURE MONITORING INSTALLATION | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR | Diffuser | WIL23 |  | 131236-WIL23-DR-M-XXXX | DIFFUSER BAND DETAILS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | DR | High Speed Turbo Blower | WIL21 |  | 131236-WIL21-DR-M-XXXX | GA Drawing - ILM2 Grit Air Blower | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | DR | High Speed Turbo Blower | WIL21 |  | 131236-WIL21-DR-M-XXXX | GA Drawing - ILM2 Grit Air Blower Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | DR | Integrally Geared Blowers | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 Bioreactor Process Aeration Blowers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | DR | Integrally Geared Blowers | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 Bioreactor Process Aeration Blowers Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | DR | Integrally Geared Blowers | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 Membrane Air Scour Blowers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | DR | Integrally Geared Blowers | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 Membrane Air Scour Blowers Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Process | Stage 2 | DR |  | WSW46 |  | 131236-WSW46-DR-M-XXXX | Overall Blower Layout Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-05-01 | Process | Stage 2 | DR | High Speed Turbo Blower | WIL21 |  | 131236-WIL21-DR-M-5000 | ILM2 - HEAD WORKS BLOWER ROOM AREA DN300 - RISER PIPE Sheet 1 Of 2 | [8 empty] | NTS - No Resubmission Required | APP - Approved |  |  |  | 0 | 1
Planned | 2026-05-01 | Process | Stage 2 | DR | High Speed Turbo Blower | WIL21 |  | 131236-WIL21-DR-M-1000 | ILM2 - HEAD WORKS BLOWER ROOM AREA DN300 - RISER PIPE Sheet 2 Of 2 | [8 empty] | NTS - No Resubmission Required | APP - Approved |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR | MFS (Polymeric Membrane) | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing – Membrane Tank Cover Layout Plan View | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR | MFS (Polymeric Membrane) | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing – Membrane Tank Cover Layout Sectional View | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR | MFS (Polymeric Membrane) | WIL23 |  | 131236-WIL23-DR-M-XXXX | Detailed Drawing – Grating Cover Supports & Mounting Brackets | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR | MFS (Polymeric Membrane) | WIL23 |  | 131236-WIL23-DR-M-XXXX | Detailed Drawing – Grating Cover | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR | MFS (Polymeric Membrane) | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - Membrane Tank Section View | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR | MFS (Polymeric Membrane) | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - Support Brackets & Mounting Layout Plan View | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR | MFS (Polymeric Membrane) | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - Support Brackets & Mounting Layout Section View | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR | MFS (Polymeric Membrane) | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - Membrane Tank Section View | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR | MFS (Polymeric Membrane) | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - Membrane Tank Elevation View | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 2 | DR | Valve | WIL21 |  | 131236-WIL21-DR-M-XXXX | GA Drawing - ILM2 Grit Tank Aeration Flow Control Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Process | Stage 2 | DR | Valve | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 Bioreactor Tank Aeration Flow Control Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Process | Stage 2 | DR | Valve | WIL06 |  | 131236-WIL06-DR-M-XXXX | ACCUMULATOR WDL00 GENERAL ARRANGEMENT | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Process | Stage 2 | DR | Valve | WIL06 |  | 131236-WIL06-DR-M-XXXX | ACCUMULATOR WDL00 DETAILS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Process | Stage 2 | DR | Valve | WIL06 |  | 131236-WIL06-DR-M-XXXX | ACCUMULATOR WDL00 NAME PLATE DETAIL | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Process | Stage 2 | DR | Ejector | WIL23 |  | 131236-WIL23-DR-M-XXXX | GA Drawing - ILM2 MBR Filtrate Air Ejector | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | DR |  | WIL00 |  | 131236-WIL00-DR-P-6000 | P&ID PLANT WATER NETWORK INDUSTRIAL LIQUID MODULE 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | DR |  | WIL00 |  | 131236-WIL00-DR-P-6003 | P&ID PLANT WATER NETWORK INDUSTRIAL LIQUID MODULE 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | DR |  | WIL00 |  | 131236-WIL00-DR-P-6005 | P&ID PLANT WATER NETWORK INDUSTRIAL LIQUID MODULE 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | DR |  | WIL00 |  | 131236-WIL00-DR-P-6008 | P&ID PLANT WATER NETWORK INDUSTRIAL LIQUID MODULE 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | DR |  | WIL00 |  | 131236-WIL00-DR-P-7001 | PFD-INDUSTRIAL USED WATER TREATMENT PHASE 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | DR |  | WIL00 |  | 131236-WIL00-DR-P-7010 | HYDRAULIC PROFILE INDUSTRIAL LM | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | DR |  | WIL06 |  | 131236-WIL06-DR-P-6021 | P&ID ILM2 CITRIC ACID DOSING PUMPS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 2 | DR |  | WIL06 |  | 131236-WIL06-DR-P-6026 | P&ID ILM2 SODIUM HYPOCHLORITE DOSING PUMPS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 2 | DR |  | WIL11 |  | 131236-WIL11-DR-P-6000 | P&ID-INTERMEDIATE SCREENS 1,2 & 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-08-01 | Process | Stage 2 | DR |  | WIL21 |  | 131236-WIL21-DR-P-6000 | P&ID-INTERMEDIATE SCREENS 1,2 & 3 | [8 empty] | SUR - Under SO Review | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-08-01 | Process | Stage 2 | DR |  | WIL21 |  | 131236-WIL21-DR-P-6001 | P&ID-INTERMEDIATE SCREENS 4,5 & 6 | [8 empty] | SUR - Under SO Review | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-08-01 | Process | Stage 2 | DR |  | WIL21 |  | 131236-WIL21-DR-P-6002 | P&ID-ODOUR HEADERS AND FLOWMETERS ILM OCF1 | [8 empty] | SUR - Under SO Review | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-08-01 | Process | Stage 2 | DR |  | WIL21 |  | 131236-WIL21-DR-P-6003 | P&ID-FINE SCREENS 1,2 & 3 | [8 empty] | SUR - Under SO Review | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-08-01 | Process | Stage 2 | DR |  | WIL21 |  | 131236-WIL21-DR-P-6004 | P&ID-FINE SCREENS 4,5 & 6 | [8 empty] | SUR - Under SO Review | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-08-01 | Process | Stage 2 | DR |  | WIL21 |  | 131236-WIL21-DR-P-6006 | P&ID-GRIT TANKS 1 & 2 | [8 empty] | SUR - Under SO Review | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-08-01 | Process | Stage 2 | DR |  | WIL21 |  | 131236-WIL21-DR-P-6007 | P&ID-GRIT TANKS 3 & 4 | [8 empty] | SUR - Under SO Review | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 2 | DR |  | WIL11 |  | 131236-WIL11-DR-P-6008 | P&ID-GRIT TANKS 5 & 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-08-01 | Process | Stage 2 | DR |  | WIL21 |  | 131236-WIL21-DR-P-6008 | P&ID-GRIT TANKS 5 & 6 | [8 empty] | SUR - Under SO Review | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-08-01 | Process | Stage 2 | DR |  | WIL21 |  | 131236-WIL21-DR-P-6009 | P&ID-GRIT AIR BLOWERS | [8 empty] | SUR - Under SO Review | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-08-01 | Process | Stage 2 | DR |  | WIL21 |  | 131236-WIL21-DR-P-6010 | P&ID-GRIT CLASSIFIER AND CONVEYANCE SYSTEM | [8 empty] | SUR - Under SO Review | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-08-01 | Process | Stage 2 | DR |  | WIL21 |  | 131236-WIL21-DR-P-6011 | P&ID-COMMON LOADOUT FACILITY | [8 empty] | SUR - Under SO Review | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-08-01 | Process | Stage 2 | DR |  | WIL21 |  | 131236-WIL21-DR-P-6012 | P&ID-GREASE AND SCUM REMOVAL SYSTEM | [8 empty] | SUR - Under SO Review | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 2 | DR |  | WIL11 |  | 131236-WIL11-DR-P-6030 | P&ID-INDUSTRIAL LM1 &LM2 SECONDANRY TREATMENT PLANT DRAINAGE | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-08-01 | Process | Stage 2 | DR |  | WIL21 |  | 131236-WIL21-DR-P-6015 | P&ID-INDUSTRIAL LM2 PRIMARY TREATMENT & HEADWORKS PLANT DRAINAGE | [8 empty] | SUR - Under SO Review | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-08-01 | Process | Stage 2 | DR |  | WIL21 |  | 131236-WIL21-DR-P-6016 | P&ID-ILM2 PLANT DRAINAGE PUMPING STATION | [8 empty] | SUR - Under SO Review | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL22 |  | 131236-WIL22-DR-P-6011 | P&ID Primary Sedimentation Tanks 1 & 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL22 |  | 131236-WIL22-DR-P-6012 | P&ID Primary Sedimentation Tank 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL22 |  | 131236-WIL22-DR-P-6013 | P&ID Primary Scum Removal System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL22 |  | 131236-WIL22-DR-P-6023 | P&ID PSI Tanks and Transfer Pumps | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 2 | DR |  | WIL13 |  | 131236-WIL13-DR-P-6000 | P&ID MBR Fine Screens | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6000 | P&ID MBR Fine Screens | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6005 | P&ID Bioreactor Overall 1 & 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6006 | P&ID Bioreactor Overall 3 & 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6007 | P&ID Bioreactor Overall 5 & 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6011 | P&ID Bioreactor 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6012 | P&ID Bioreactor 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6013 | P&ID Bioreactor 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6014 | P&ID Bioreactor 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6015 | P&ID Bioreactor 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6016 | P&ID Bioreactor 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6017 | P&ID INDUSTRIAL LM2 SECONDARY TREATMENT PLANT DRAINAGE 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6018 | P&ID INDUSTRIAL LM2 SECONDARY TREATMENT PLANT DRAINAGE 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 2 | DR |  | WIL13 |  | 131236-WIL13-DR-P-6030 | P&ID Process Air Blowers Part 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6030 | P&ID Process Air Blowers Part 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6031 | P&ID Process Air Blowers Part 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 2 | DR |  | WIL13 |  | 131236-WIL13-DR-P-6032 | P&ID Membrane Air Blowers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6032 | P&ID Membrane Air Blowers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 2 | DR |  | WIL13 |  | 131236-WIL13-DR-P-6035 | P&ID DEOX/RAS Tanks | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6035 | P&ID DEOX/RAS Tanks | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6036 | P&ID ILM OCF2 ODOUR HEADERS AND PRE-FILTERS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 2 | DR |  | WIL13 |  | 131236-WIL13-DR-P-6041 | P&ID WAS Pumping No. 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6041 | P&ID WAS Pumping No. 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 2 | DR |  | WIL13 |  | 131236-WIL13-DR-P-6042 | P&ID WAS Pumping No. 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6042 | P&ID WAS Pumping No. 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6049 | P&ID Cleaning Pumps Part 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6050 | P&ID Cleaning Pumps Part 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6051 | P&ID Membrane Tank 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6052 | P&ID Membrane Tank 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6053 | P&ID Membrane Tank 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6054 | P&ID Membrane Tank 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6055 | P&ID Membrane Tank 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6056 | P&ID Membrane Tank 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6057 | P&ID Membrane Tank 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6058 | P&ID Membrane Tank 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6059 | P&ID Membrane Tank 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6060 | P&ID Membrane Tank 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6061 | P&ID Membrane Tank 11 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6062 | P&ID Membrane Tank 12 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6063 | P&ID Membrane Tank 13 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6064 | P&ID Membrane Tank 14 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6065 | P&ID Membrane Tank 15 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6066 | P&ID Membrane Tank 16 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6067 | P&ID Membrane Tank 17 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6068 | P&ID Membrane Tank 18 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6070 | P&ID LM1 MBR Filtrate Pumps 1, 2 & 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6071 | P&ID LM1 MBR Filtrate Pumps 4, 5 & 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6072 | P&ID LM1 MBR Filtrate Pumps 7, 8 & 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6073 | P&ID LM1 MBR Filtrate Pumps 10, 11 & 12 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6074 | P&ID LM1 MBR Filtrate Pumps 13 & 14 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6079 | P&ID MBR Filtrate Tank and Transfer Pumps Part 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6080 | P&ID MBR Filtrate Tank and Transfer Pumps Part 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 2 | DR |  | WIL13 |  | 131236-WIL13-DR-P-6081 | P&ID MBR Filtrate Tank and Transfer Pumps Part 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6081 | P&ID MBR Filtrate Tank and Transfer Pumps Part 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6085 | P&ID Membrane Staging Tanks | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6086 | P&ID Mixed Liquor Wet Well | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6090 | P&ID Membrane Scum Wet Wells 1 & 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6091 | P&ID Membrane Scum Wet Wells 3 & 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6092 | P&ID Membrane Scum Wet Wells 5 & 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 2 | DR |  | WIL23 |  | 131236-WIL23-DR-P-6093 | P&ID Membrane Scum Wet Well 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-08-01 | Process | Stage 2 | DR |  | WNS03 |  | 131236-WNS03-DR-P-6050 | P&ID SURGE VESSELS | [8 empty] | SUR - Under SO Review | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Process | Stage 2 | DR |  |  |  | 131236-DR-P-XXXX | COMPRESSED AIR SYSTEM | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Process | Stage 2 | DR |  |  |  | 131236-DR-P-XXXX | COMPRESSED AIR DISTRIBUTION | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Process | Stage 2 | DR |  |  |  | 131236-DR-P-XXXX | COMPRESSED AIR DISTRIBUTION | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Process | Stage 2 | DR |  |  |  | 131236-DR-P-XXXX | BIOREACTOR COMPRESSED AIR SYSTEM | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Process | Stage 2 | DR |  |  |  | 131236-DR-P-XXXX | SCREENING & GRIT HOPPER DISCHARGE SLIDE GATE COMPRESSED AIR SYSTEM | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 3 | QA | Centrifugal Pump | WSW46 |  | 131236-WSW46-QA-M-XXXX | ITP - Centrifugal Pumps | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 3 | QA | Centrifugal Pump | WSW46 |  | 131236-WSW46-QA-M-XXXX | FAT Procedure - Centrifugal Pumps | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 3 | QA | Vertical Turbine Pumps | WIL23 |  | 131236-WIL23-QA-M-XXXX | ITP - Vertical Turbine Pumps | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 3 | QA | Vertical Turbine Pumps | WIL23 |  | 131236-WIL23-QA-M-XXXX | FAT Procedure - Vertical Turbine Pumps | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 3 | QA | Concentric Tubular Casing Submersible Pump | WIL23 |  | 131236-WIL23-QA-M-XXXX | ITP - Concentric Tubular Casing Submersible Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 3 | QA | Concentric Tubular Casing Submersible Pump | WIL23 |  | 131236-WIL23-QA-M-XXXX | FAT Procedure - Concentric Tubular Casing Submersible Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 3 | QA | Screw Induced Flow Pumps | WSW46 |  | 131236-WSW46-QA-M-XXXX | ITP - Screw Induced Flow Pumps | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 3 | QA | Screw Induced Flow Pumps | WSW46 |  | 131236-WSW46-QA-M-XXXX | FAT Procedure - Screw Induced Flow Pumps | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 3 | QA | Submersible Pumps | WIL23 |  | 131236-WIL23-QA-M-XXXX | ITP - Submersible Pumps | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 3 | QA | Submersible Pumps | WIL23 |  | 131236-WIL23-QA-M-XXXX | FAT Procedure - Submersible Pumps | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 3 | QA | Double Disc Centrifugal Pumps | WSW46 |  | 131236-WSW46-QA-M-XXXX | ITP - Double Disc Centrifugal Pumps | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 3 | QA | Double Disc Centrifugal Pumps | WSW46 |  | 131236-WSW46-QA-M-XXXX | FAT Procedure - Double Disc Centrifugal Pumps | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 3 | QA | Sump Dewatering Pumps | WIL21 |  | 131236-WIL21-QA-M-XXXX | ITP - Sump Dewatering Pumps | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 3 | QA | Sump Dewatering Pumps | WIL21 |  | 131236-WIL21-QA-M-XXXX | FAT Procedure - Sump Dewatering Pumps | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 3 | QA | Recessed Impellel Pump | WIL21 |  | 131236-WIL21-QA-M-XXXX | ITP - Recessed Impellel Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 3 | QA | Recessed Impellel Pump | WIL21 |  | 131236-WIL21-QA-M-XXXX | FAT Procedure - Recessed Impellel Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Process | Stage 3 | QA | Progressive Cavity Pump | WIL21 |  | 131236-WIL21-QA-M-XXXX | ITP - Progressive Cavity Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Process | Stage 3 | QA | Progressive Cavity Pump | WIL21 |  | 131236-WIL21-QA-M-XXXX | FAT Procedure - Progressive Cavity Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Process | Stage 3 | QA | Chemical Dosing Pump | WIL06 |  | 131236-WIL06-QA-M-XXXX | ITP - Chemical Dosing Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Process | Stage 3 | QA | Chemical Dosing Pump | WIL06 |  | 131236-WIL06-QA-M-XXXX | FAT Procedure - Chemical Dosing Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Process | Stage 3 | QA | Compressed Air System | WIL23 |  | 131236-WIL23-QA-M-XXXX | ITP - Compressed Air System Including Compressors, Air Dryers and Air Receiver Tanks | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-06-01 | Process | Stage 3 | QA | Hyperboloid Mixer | WIL23 |  | 131236-WIL23-QA-M-0001 | ITP & FAT - Hyperbolic Mixer | [8 empty] | SUR - Under SO Review | AWC - Approved with Comments |  |  |  | 0 | 1
Planned | 2026-10-01 | Process | Stage 3 | QA | Diffuser | WSW46 |  | 131236-WSW46-QA-M-XXXX | ITP - Air Diffuser – Grit System and Bioreactors | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 3 | QA | High Speed Turbo Blower | WIL21 |  | 131236-WIL21-QA-M-XXXX | ITP - High Speed Turbo Blower (Grit Aeration Blower) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 3 | QA | High Speed Turbo Blower | WIL21 |  | 131236-WIL21-QA-M-XXXX | FAT Procedure - High Speed Turbo Blower (Grit Aeration Blower) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Process | Stage 3 | QA | Integrally Geared Blowers | WIL23 |  | 131236-WIL23-QA-M-XXXX | ITP-Integrally Single Stage Centrifugal Geared Air Blower Sub System Works IGV Blower | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-08-01 | Process | Stage 3 | QA | MFS (Polymeric Membrane) | WIL23 |  | 131236-WIL23-QA-M-0002 | ITP - MFS (Membrane) | [8 empty] | SUR - Under SO Review | NAP - Not Approved |  |  |  | 0 | 1
Planned | 2027-03-01 | Process | Stage 3 | QA | MFS (Polymeric Membrane) | WIL23 |  | 131236-WIL23-QA-M-XXXX | ITP - MFS (Membrane Tank Steel Works) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Process | Stage 3 | QA | MFS (Polymeric Membrane) | WIL23 |  | 131236-WIL23-QA-M-XXXX | FAT Procedure - MFS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Process | Stage 3 | QA | Valve | WSW46 |  | 131236-WSW46-QA-M-XXXX | ITP - Air Flow Control Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Process | Stage 3 | QA | Valve | WSW46 |  | 131236-WSW46-QA-M-XXXX | ITP - Liquid Flow Control Valves And Actuators | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Process | Stage 3 | QA | Valve | WSW46 |  | 131236-WSW46-QA-M-XXXX | ITP - Accumulators | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Process | Stage 3 | QA | Ejector | WIL23 |  | 131236-WIL23-QA-M-XXXX | ITP & FAT Procedure- MFS Air Ejector | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2028-06-01 | Process | Stage 3 | RT | Centrifugal Pump | WIL00 |  | 131236-WIL00-RT-M-XXXX | FAT Report - ILM2 Plant Water High Pressure Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2028-06-01 | Process | Stage 3 | RT | Centrifugal Pump | WIL23 |  | 131236-WIL23-RT-M-XXXX | FAT Report - ILM2 Membrane Cleaning Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2028-06-01 | Process | Stage 3 | RT | Centrifugal Pump | WIL23 |  | 131236-WIL23-RT-M-XXXX | FAT Report - ILM2 MBR Filtrate Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2028-06-01 | Process | Stage 3 | RT | Vertical Turbine Pumps | WIL23 |  | 131236-WIL23-RT-M-XXXX | FAT Report - ILM2 G2I Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2028-06-01 | Process | Stage 3 | RT | Concentric Tubular Casing Submersible Pump | WIL23 |  | 131236-WIL23-RT-M-XXXX | FAT Report - ILM2 DEOX/RAS Tank RAS Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2028-06-01 | Process | Stage 3 | RT | Concentric Tubular Casing Submersible Pump | WIL23 |  | 131236-WIL23-RT-M-XXXX | FAT Report - ILM2 Mixed Liquor Return Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2028-06-01 | Process | Stage 3 | RT | Screw Induced Flow Pumps | WIL21 |  | 131236-WIL21-RT-M-XXXX | FAT Report - ILM Plant Drainage PS Wet Well Compartment 2 Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2028-06-01 | Process | Stage 3 | RT | Screw Induced Flow Pumps | WIL22 |  | 131236-WIL22-RT-M-XXXX | FAT Report - ILM2 PST Primary Sludge Transfer Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2028-06-01 | Process | Stage 3 | RT | Screw Induced Flow Pumps | WIL23 |  | 131236-WIL23-RT-M-XXXX | FAT Report - ILM2 WAS Wet Well WAS Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2028-06-01 | Process | Stage 3 | RT | Submersible Pumps | WIL23 |  | 131236-WIL23-RT-M-XXXX | FAT Report - ILM2 Bioreactor Drainage Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2028-06-01 | Process | Stage 3 | RT | Submersible Pumps | WIL23 |  | 131236-WIL23-RT-M-XXXX | FAT Report - ILM2 DEOX/RAS Tank Drainage Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2028-06-01 | Process | Stage 3 | RT | Submersible Pumps | WIL23 |  | 131236-WIL23-RT-M-XXXX | FAT Report - ILM2 MBR Filtrate Tank Drainage Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2028-06-01 | Process | Stage 3 | RT | Double Disc Centrifugal Pumps | WIL21 |  | 131236-WIL21-RT-M-XXXX | FAT Report - ILM2 Grease and Scum Wet Well Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2028-06-01 | Process | Stage 3 | RT | Double Disc Centrifugal Pumps | WIL22 |  | 131236-WIL22-RT-M-XXXX | FAT Report - ILM2 Primary Scum Wet Well Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2028-06-01 | Process | Stage 3 | RT | Double Disc Centrifugal Pumps | WIL23 |  | 131236-WIL23-RT-M-XXXX | FAT Report - ILM2 Membrane Scum Wet Well Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2028-06-01 | Process | Stage 3 | RT | Recessed Impellel Pump | WIL21 |  | 131236-WIL21-RT-M-XXXX | FAT Report - ILM2 Influent Flowmeter Chamber Drainage Sump Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2028-06-01 | Process | Stage 3 | RT | Recessed Impeller Pump | WIL21 |  | 131236-WIL21-RT-M-XXXX | FAT Report - ILM2 Grit Tank Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2028-02-01 | Process | Stage 3 | RT | Progressive Cavity Pump | WIL21 |  | 131236-WIL21-RT-M-XXXX | FAT Report - ILM2 Grit Tanks Inlet Sampling Point Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2028-02-01 | Process | Stage 3 | RT | Progressive Cavity Pump | WIL22 |  | 131236-WIL22-RT-M-XXXX | FAT Report - ILM2 PSI Transfer Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2028-02-01 | Process | Stage 3 | RT | Progressive Cavity Pump | WIL23 |  | 131236-WIL23-RT-M-XXXX | FAT Report - ILM2 Bioreactor Sampling Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2028-02-01 | Process | Stage 3 | RT | Progressive Cavity Pump | WIL23 |  | 131236-WIL23-RT-M-XXXX | FAT Report - ILM2 MBR Filtrate Tank Membrane Filtrate Sampling Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-12-01 | Process | Stage 3 | RT | Chemical Dosing Pump | WIL06 |  | 131236-WIL06-RT-M-XXXX | FAT Report - ILM2 MFS Citric Acid Dosing Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-12-01 | Process | Stage 3 | RT | Chemical Dosing Pump | WIL06 |  | 131236-WIL06-RT-M-XXXX | FAT Report - ILM2 MFS Sodium Hypochlorite Dosing Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | Process | Stage 3 | RT | Hyperboloid Mixer | WIL23 |  | 131236-WIL23-RT-M-XXXX | FAT Report - Hyperbolic Mixer | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Process | Stage 3 | RT | Diffuser | WIL21 |  | 131236-WIL21-RT-M-XXXX | FAT Report - Coarse Bubble Diffuser – Grit System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Process | Stage 3 | RT | Diffuser | WIL23 |  | 131236-WIL23-RT-M-XXXX | FAT Report - Fine Bubble Diffuser – Bioreactor | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-10-01 | Process | Stage 3 | RT | High Speed Turbo Blower | WIL21 |  | 131236-WIL21-RT-M-XXXX | FAT Report - ILM2 Grit Air Blower | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-10-01 | Process | Stage 3 | RT | Integrally Geared Blowers | WIL23 |  | 131236-WIL23-RT-M-XXXX | FAT Report - ILM2 Bioreactor Process Aeration Blowers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-10-01 | Process | Stage 3 | RT | Integrally Geared Blowers | WIL23 |  | 131236-WIL23-RT-M-XXXX | FAT Report - ILM2 Membrane Air Scour Blowers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2028-01-01 | Process | Stage 3 | RT | MFS (Polymeric Membrane) | WIL23 |  | 131236-WIL23-RT-M-XXXX | FAT Report - MFS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2028-02-01 | Process | Stage 3 | RT | Valve | WIL21 |  | 131236-WIL21-RT-M-XXXX | FAT Report for Grit Tank Aeration Flow Control Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2028-02-01 | Process | Stage 3 | RT | Valve | WIL23 |  | 131236-WIL23-RT-M-XXXX | FAT Report for Bioreactor Aeration Flow Control Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2028-02-01 | Process | Stage 3 | RT | Ejector | WIL23 |  | 131236-WIL23-RT-M-XXXX | FAT Report- MFS Air Ejector | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2028-02-01 | Process | Stage 3 | RT | Valve | WIL21 |  | 131236-WIL21-RT-M-XXXX | FAT Report for WDL21 Flow Control Eccentric Butterfly Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-06-01 | Process | Stage 3 | RT | Mixer | WIL23 |  | 131236-WIL23-RT-M-0001 | CFD Report for Bioreactor Mixed Liquor Mixer | [8 empty] | RTR - Returned for Resubmission | NAP - Not Approved |  |  |  | 0 | 1
Planned |  | Process | Stage 3 | RT |  | WSW46 |  | 131236-WSW46-RT-M-XXXX | Hazop Report For Compressed Air, Fine Screen Cleaning, MBR Fine Screen Cleaning, Lamella Cleaning System, Membrane Filtration System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 3 | RT |  | WIL21 |  | 131236-WIL21-RT-M-XXXX | ALMOP Report (Grit Tank Area, Intermediate and Fine Screen Area) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 3 | RT |  | WIL21 |  | 131236-WIL21-RT-M-XXXX | ALMOP Report (Grit Blowers & Grit Pumps) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 3 | RT |  | WIL22 |  | 131236-WIL22-RT-M-XXXX | ALMOP Report for PST Pump and PSD Holding Tank Pump Area | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 3 | RT |  | WIL22 |  | 131236-WIL22-RT-M-XXXX | ALMOP Report for PST Tanks | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 3 | RT |  | WIL23 |  | 131236-WIL23-RT-M-XXXX | DeOX/RAS Tank Physical Sump Model Test Report | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 3 | RT |  | WIL23 |  | 131236-WIL23-RT-M-XXXX | ALMOP Report for Chemical Dosing and MBR Fine Screen Area | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WSW46 |  | 131236-WSW46-MS-M-XXXX | Method Statement And Risk Assessment For FRP Pipe Fabrication | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL23 |  | 131236-WIL23-MS-M-XXXX | Method Statement and Risk Assessment for Fine Bubble Diffuser Installation Work at WIL23 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WSW46 |  | 131236-WSW46-MS-M-XXXX | Method Statement and Risk Assessment for Stainless Steel Pipe Fabrication at C3B2 Workshop | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WSW46 |  | 131236-WSW46-MS-M-XXXX | Method Statement and Risk Assessment for Fire Proofing (Intumescent) Coating System | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL06 |  | 131236-WIL06-MS-M-XXXX | Method Statement and Risk Assessment for Structure Installation Work at WIL06 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL06 |  | 131236-WIL06-MS-M-XXXX | Method Statement and Risk Assessment for Roofing Installation Work at WIL06 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WSW46 |  | 131236-WSW46-MS-M-XXXX | Method Statement For HAZOP Study | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WSW46 |  | 131236-WSW46-MS-M-XXXX | Method Statement For Access Lifting Maintainability And Operability (ALMOP) Study | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WSW46 |  | 131236-WSW46-MS-M-XXXX | Method Statement And Risk Assessment For Mobilization Of Equipment & Materials | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WSW46 |  | 131236-WSW46-MS-M-XXXX | Method Statement And Risk Assessment For HDPE Pipe Welding And Site Installation | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WSW46 |  | 131236-WSW46-MS-M-XXXX | Method Statement And Risk Assessment For Steel Pipe Fabrication And Welding | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WSW46 |  | 131236-WSW46-MS-M-XXXX | DFS (Design For Safety) Review Methodology | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL21 |  | 131236-WIL21-MS-M-XXXX | Submission Of Method Statement And Risk Assessment For Lifting of Carbon Steel Cement Lined Pipe and Fitting | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WSW46 |  | 131236-WSW46-MS-M-XXXX | Submission Of Method Statement And Risk Assessment For Hydrostatic Test Procedur | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL21 |  | 131236-WIL21-MS-M-XXXX | Method Statement and Risk Assessment For Assembling and Installation of the Submerged Screw Conveyor | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WSW46 |  | 131236-WSW46-MS-M-XXXX | Method Statement and Risk Assessment For Installation of the Generic Equipment | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL22 |  | 131236-WIL22-MS-M-XXXX | Method Statement and Risk Assessment for PST Tank Support Installation Method Statement | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL22 |  | 131236-WIL22-MS-M-XXXX | Method Statement and Risk Assessment for Delivery of Materials, Pipe, Pipe Support and Equipment Installation, Fabrication, and Welding | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL21 |  | 131236-WIL21-MS-M-XXXX | Method Statement and Risk Assessment for Installation of Grit and Screening Hopper | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL21 |  | 131236-WIL21-MS-M-XXXX | Method Statement and Risk Assessment for Grit Pump Installation at WIL21 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL21 |  | 131236-WIL21-MS-M-XXXX | Method Statement and Risk Assessment for Installation of Submersible Pump With Guide Rail at DPS | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL21 |  | 131236-WIL21-MS-M-XXXX | Method Statement and Risk Assessment for Installation of Launder at Grit Tank | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL21 |  | 131236-WIL21-MS-M-XXXX | Method Statement and Risk Assessment for Installation of Picket Fence at Grit Tank | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL21 |  | 131236-WIL21-MS-M-XXXX | Method Statement and Risk Assessment for Installation of Coarse Bubble Diffuser at Inlet/Outlet Channel and Grit Tank | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL21 |  | 131236-WIL21-MS-M-XXXX | Method Statement and Risk Assessment for Installation of Intermediate Screen, Fine Screen and Dewatering Press at WIL21 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL21 |  | 131236-WIL21-MS-M-XXXX | Method Statement and Risk Assessment for Installation of Grit Classifier at WIL21 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WSW46 |  | 131236-WSW46-MS-M-XXXX | Method Statement and Risk Assessment for Delivery of Materials, Site Fabrication and Installation for Pipe Support and FRP PIPE | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL21 |  | 131236-WIL21-MS-M-XXXX | Method Statement and Risk Assessment for Installation of Scum Scrapper at Grit Tank No.1 to No.5 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WSW46 |  | 131236-WSW46-MS-M-XXXX | Method Statement and Risk Assessment for Erection, Dismantling and Modification of Scaffolding | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WSW46 |  | 131236-WSW46-MS-M-XXXX | Method Statement and Risk Assessment for EOTC, JIB Crane and Monorail Crane | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL21 |  | 131236-WIL21-MS-M-XXXX | Method Statement and Risk Assessment for Installation of Pipe Rack at WIL21 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL21 |  | 131236-WIL21-MS-M-XXXX | Method Statement and Risk Assessment for Delivery of Materials, Site Fabrication and Installation for FRP Pipe Support & Pipe at WIL21 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL21 |  | 131236-WIL21-MS-M-XXXX | Method Statement and Risk Assessment for Installation of Grit Conveyor , Loadout and Cross Conveyor | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WSW46 |  | 131236-WSW46-MS-M-XXXX | MSRA for Installation of Submersible Pump with Guide Rail at C3B2 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WSW46 |  | 131236-WSW46-MS-M-XXXX | MSRA for Installation of Centrifugal Pump at C3B2 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL21 |  | 131236-WIL21-MS-M-XXXX | Method Statement and Risk Assessment for Installation of Removable Panel Inlet and Outlet Grit Tank #06 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WSW46 |  | 131236-WSW46-MS-M-XXXX | Method Statement and Risk Assessment for Concrete Floor Coring and Cast-In Pipe Installation | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL23 |  | 131236-WIL23-MS-M-XXXX | Method Statement and Risk Assessment for Installation of Scum Wet Well Pump at C3B2 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL21 |  | 131236-WIL21-MS-M-XXXX | MSRA for WIL21 Hopper Leak Test | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WSW46 |  | 131236-WSW46-MS-M-XXXX | MSRA for Plant Testing and Commissioning Activities (Site Wide) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL22 |  | 131236-WIL22-MS-M-XXXX | Method Statement and Risk Assessment For Unloading Of Lamella Materials Applying Anti-Fungal Solution To Wooden Crates | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL22 |  | 131236-WIL22-MS-M-XXXX | Method Statement and Risk Assessment for Installation of Lamella Support Structure & Maintenance Platform Structure | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL22 |  | 131236-WIL22-MS-M-XXXX | Submission of Method Statement and Risk Assessment for Installation of Lamella, Rotating Scraper & Surface Scraper | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL22 |  | 131236-WIL22-MS-M-XXXX | Method Statement and Risk Assessment for WIL22 Pipe and Pipe Support Installation | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL22 |  | 131236-WIL22-MS-M-XXXX | Method Statement and Risk Assessment for WIL22 MBR Fine Screen, Launder & Dewatering Press Installation | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL23 |  | 131236-WIL23-MS-M-XXXX | MSRA for Hyperbolic Mixer Installation at C3B2 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL23 |  | 131236-WIL23-MS-M-XXXX | Method Statement and Risk Assessment for Aeration Blower Installation Work at WIL23 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL23 |  | 131236-WIL23-MS-M-XXXX | Method Statement and Risk Assessment for MBR Tank Steel Structure Installation | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL23 |  | 131236-WIL23-MS-M-XXXX | Method Statement and Risk Assessment for Epoxy Floor Application | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL23 |  | 131236-WIL23-MS-M-XXXX | Method Statement and Risk Assessment for MBR Tank Inlet Baffle Wall Installation | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL23 |  | 131236-WIL23-MS-M-XXXX | MSRA for Installation of Vertical Turbine Pump at WIL23 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL23 |  | 131236-WIL23-MS-M-XXXX | Method Statement and Risk Assessment for MBR Filtrate Pipe Rack and Pipe Installation | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL23 |  | 131236-WIL23-MS-M-XXXX | Method Statement and Risk Assessment for Installation of Temporary Lifeline at MBR Tank | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL23 |  | 131236-WIL23-MS-M-XXXX | MSRA for RAS/Mixed Liquid Return Pipe Support, Pipe And Pump at C3B2 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL23 |  | 131236-WIL23-MS-M-XXXX | Method Statement and Risk Assessment for Installation of SS Piping at Blower Pipe Rack | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL23 |  | 131236-WIL23-MS-M-XXXX | MS For MBR Membrane Module Bubble Test | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 5 | MS |  | WIL23 |  | 131236-WIL23-MS-M-XXXX | MSRA for Membrane Installation & Wet Preservation of Membrane Tank | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 3 | QA |  | WIL21 |  | 131236-WIL21-QA-N-XXXX | Commissioning Plan for Plant Drainage Pumping System | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 3 | QA |  | WIL21 |  | 131236-WIL21-QA-N-XXXX | Commissioning Plan For Grease And Scum Wet Well Pumping System | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 3 | QA |  | WIL21 |  | 131236-WIL21-QA-N-XXXX | Commissioning Plan For Grit Tank System | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 3 | QA |  | WIL21 |  | 131236-WIL21-QA-N-XXXX | Commissioning Plan For Headworks Screening System | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 3 | QA |  | WIL21 |  | 131236-WIL21-QA-N-XXXX | Commissioning Plan For Grit Classifier & Hopper System | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 3 | QA |  | WIL21 |  | 131236-WIL21-QA-N-XXXX | Testing and Commissioning Checksheet Templates | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 3 | QA |  | WIL22 |  | 131236-WIL22-QA-N-XXXX | Commissioning Plan For Primary Scum Pumping System | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 3 | QA |  | WIL22 |  | 131236-WIL22-QA-N-XXXX | Commissioning Plan For Primary Sludge Industrial (PSI) Transfer System | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 3 | QA |  | WIL22 |  | 131236-WIL22-QA-N-XXXX | Commissioning Plan For Primary Sedimentation Tank (PST) System | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 3 | QA |  | WIL23 |  | 131236-WIL23-QA-N-XXXX | Commissioning Plan For Plant Water (G2I) System | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Process | Stage 3 | QA |  | WIL23 |  | 131236-WIL23-QA-N-XXXX | Commissioning Plan For MBR Fine Screen System | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 1 | VI |  | WIL00 | NO | 131236-WIL00-VI-B-0001 | Vendor Information For Licensed Plumber for Site Office (M-Stars Engineering & Construction Pte Ltd) | [8 empty] | NTS - No Resubmission Required | APP - Approved |  |  |  | 0 | 1
Planned |  | BS | Stage 1 | VI | Lift | WIL22 | NO | 131236-WIL22-VI-B-0001 | Vendor Information For Electric Lift Works (XJ Elevator Private Limited) | [8 empty] | RTR - Returned for Resubmission | REJ - Rejected |  |  |  | 0 | 1
Planned |  | BS | Stage 1 | VI | Fire Protection System | WSW46 | NO | 131236-WSW46-VI-B-0001 | Vendor Information for Addressable Fire Alarm System (Acclaim System Private Limited) | [8 empty] | RTR - Returned for Resubmission | REJ - Rejected |  |  |  | 0 | 1
Planned |  | BS | Stage 1 | VI | Fire Protection System | WSW46 | NO | 131236-WSW46-VI-B-0002 | Vendor Information for Two-Way Emergency Voice Communication System (Acclaim System Private Limited) | [8 empty] | RTR - Returned for Resubmission | REJ - Rejected |  |  |  | 0 | 1
Planned | 2026-08-01 | BS | Stage 1 | VI | Fire Protection System | WSW46 | NO | 131236-WSW46-VI-B-0003 | Vendor Information for Gas Suppression System (Federal Fire Engineering Pte Ltd) | [8 empty] | RTR - Returned for Resubmission | REJ - Rejected |  |  |  | 0 | 1
Planned | 2026-10-01 | BS | Stage 1 | VI | ACMV | WSW46 | NO | 131236-WSW46-VI-B-0004 | Vendor Information for Water-cooled Chiller (Midea (Singapore) Product Pte. Ltd.) | [8 empty] | RTR - Returned for Resubmission | NAP - Not Approved |  |  |  | 0 | 1
Planned | 2026-10-01 | BS | Stage 1 | VI | ACMV |  |  | 131236-VI-B | Vendor Information of ACMV System Contractor | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | BS | Stage 1 | VI | Fire Protection, Detection & Fire Alarm System |  | NO | 131236-VI-B | Vendor Information of Fire Protection System Contractor | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 1 | VI | Intergrated Security Management System |  | NO | 131236-VI-B | Vendor Information of ISMS Installation Contractor | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 1 | VI | Voice Over Internet Protocol |  | NO | 131236-VI-B | Vendor Information of VOiP Installation Contractor | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI | Fire Protection, Detection & Fire Alarm System |  | NO | 131236-VI-B | Vendor Information For Sprinkler Control Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI | Fire Protection, Detection & Fire Alarm System |  | NO | 131236-VI-B | Vendor Information For Breeching inlet | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI | Fire Protection, Detection & Fire Alarm System |  | NO | 131236-VI-B | Vendor Information For Flow Switch | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI | Fire Protection, Detection & Fire Alarm System |  |  | 131236-VI-B | Vendor Information For Pipe and Fitting (DICL) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI | Fire Protection, Detection & Fire Alarm System |  |  | 131236-VI-B | Vendor Information For Sprinkler Heads | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI | Fire Protection, Detection & Fire Alarm System |  |  | 131236-VI-B | Vendor Information For Water Monitoring System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI | Fire Protection, Detection & Fire Alarm System |  |  | 131236-VI-B | Vendor Approval For Hosereel, Cabinet with complete sets | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI | Fire Protection, Detection & Fire Alarm System |  |  | 131236-VI-B | Vendor Approval For Gate Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI | Fire Protection, Detection & Fire Alarm System |  |  | 131236-VI-B | Vendor Approval For SS 304 Pipework | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI | Fire Protection, Detection & Fire Alarm System |  |  | 131236-VI-B | Vendor Approval For Breeching Inlet | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI | Fire Protection, Detection & Fire Alarm System |  |  | 131236-VI-B | Vendor Approval For Standby Fire Hose including Cabinet | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI | Fire Protection, Detection & Fire Alarm System |  |  | 131236-VI-B | Vendor Approval For Landing Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI | Fire Protection, Detection & Fire Alarm System |  |  | 131236-VI-B | Vendor Approval For Manual Ball Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI | Fire Protection, Detection & Fire Alarm System |  |  | 131236-VI-B | Vendor Approval For Pipes (HDG) and Fittings (Wrought Iron Steel) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 1 | VI | Fire Protection, Detection & Fire Alarm System |  |  | 131236-VI-B | Data Sheet For Amplifiers / Pre Amplifiers System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 1 | VI | Fire Protection, Detection & Fire Alarm System |  |  | 131236-VI-B | Data Sheet For PA Speaker | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI | ACMV |  |  | 131236-VI-B | Vendor Approval For MV fan | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI | ACMV |  |  | 131236-VI-B | Vendor Approval For SS 304 Ductwork | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI | ACMV |  |  | 131236-VI-B | Vendor Approval For Dampers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI | ACMV |  |  | 131236-VI-B | Vendor Approval For Air handling unit | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI | ACMV |  |  | 131236-VI-B | Vendor Approval For SS 304 Insulated Ductwork | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI | ACMV |  |  | 131236-VI-B | Vendor Approval For Ceiling mounted ducted unit | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI | ACMV |  |  | 131236-VI-B | Vendor Approval For Expension tank | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI | ACMV |  |  | 131236-VI-B | Vendor Approval For Pre-insulated water pipeworks | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI | ACMV |  |  | 131236-VI-B | Vendor Approval For Chilled water pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI | ACMV |  |  | 131236-VI-B | Vendor Approval For Manual Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI | ACMV |  |  | 131236-VI-B | Vendor Approval For Temperature Transmitter | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI | ACMV |  |  | 131236-VI-B | Vendor Approval For Pressure Transmitter | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI | ACMV |  |  | 131236-VI-B | Vendor Approval For Pressure Differential Switch | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI | ACMV |  |  | 131236-VI-B | Vendor Approval For Pressure Differential Transmitter | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 1 | VI | ACMV |  |  | 131236-VI-B | Vendor Approval For CO2 Sensor | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 1 | VI | ACMV |  |  | 131236-VI-B | Vendor Approval For Smoke Detector | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 1 | VI | ACMV |  |  | 131236-VI-B | Vendor Approval For Duct Smoke Detector | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 1 | VI | ACMV |  |  | 131236-VI-B | Vendor Approval For Electromagnetic Flowmeter | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 1 | VI | ACMV |  |  | 131236-VI-B | Vendor Approval For Level Gauge | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 1 | VI | ACMV |  |  | 131236-VI-B | Vendor Approval For Modulating Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 1 | VI | Lift |  |  | 131236-VI-B | Vendor Approval For POE Network Switch | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 1 | VI | Fire Alarm System |  |  | 131236-VI-B | Vendor Approval For Fibre Patch Panel | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 1 | VI |  |  |  | 131236-VI-B | Vendor Approval For Cables (FO) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 1 | VI |  |  |  | 131236-VI-B | Vendor Approval For Cable tray / conduit | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 1 | VI |  |  |  | 131236-VI-B | Vendor Approval For Cables (CAT6) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 1 | VI |  |  |  | 131236-VI-B | Vendor Approval For Single Mode Fibre Cable | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 1 | VI |  |  |  | 131236-VI-B | Vendor Approval For Patch Panel | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 1 | VI | 2-Way ECV System |  |  | 131236-VI-B | Vendor Approval For Network Switch | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI |  |  |  | 131236-VI-B | Vendor Approval For PLC | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI | Gas Suppression System |  |  | 131236-VI-B | Vendor Approval For BIO Panel | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI |  |  |  | 131236-VI-B | Vendor Approval For Network Switch | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI |  |  |  | 131236-VI-B | Vendor Approval For Patch Panel | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 1 | VI |  |  |  | 131236-VI-B | Vendor Approval For Cable | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Date Sheet For Electric Lift | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Date Sheet For Alarm Panels | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Date Sheet For Heat Detectors | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Date Sheet For Smoke Detectors | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | BS | Stage 2 | DS | Fire Sprinkler System |  |  | 131236-DS-B | Date Sheet For Strobe Light | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Date Sheet For Manual call Point | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Date Sheet For Fire Alarm Cables | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Fireman Intercom main Panels / Supervisory Panel | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Headset | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Warning Alarm System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Fire Panels | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Solenoid Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | BS | Stage 2 | DS | Fire Hosereel System |  |  | 131236-DS-B | Data Sheet For Smoke Detectors | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Nozzles | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Gas cylinders | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Breathing Apparatus | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 2 | DS | Dry Riser System |  |  | 131236-DS-B | Data Sheet For Pipes and Fittings (SS 304) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Sprinkler Control Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Breeching inlet | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Flow Switch | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Pipe and Fitting (DICL) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Gate Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | BS | Stage 2 | DS | 1-Way EVC System |  |  | 131236-DS-B | Data Sheet For Sprinkler Heads | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Water Monitoring System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Auto Air Release Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | BS | Stage 2 | DS | MV System |  |  | 131236-DS-B | Data Sheet For Hosereel complete with nozzles | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Gate Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Auto Venting Valve / Air Release Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Pipes and Fittings (SS 304) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Breeching Inlet | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | BS | Stage 2 | DS | Air Handling System |  |  | 131236-DS-B | Data Sheet For Auto Vending Valve / Pressure Relief Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Landing Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Manual Ball Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Pipes (HDG) and Fittings (Wrought Iron Steel) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Vendor Approval For Standby Fire Hose including Cabinet | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DS | Fan Coil Unit |  |  | 131236-DS-B | Data Sheet For Amplifiers / Pre Amplifiers System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DS | Chilled water system |  |  | 131236-DS-B | Data Sheet For Speaker | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For IP Networks Switch / Audio Adaptor | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For MV fan | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For SS 304 Ductwork | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Cables | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Dampers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Sensors | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 2 | DS | Security CCTV System |  |  | 131236-DS-B | Data Sheet For Air handling unit | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For SS 304 Insulated Ductwork | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Cables | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Dampers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DS | Access Control System |  |  | 131236-DS-B | Data Sheet For Sensors | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 2 | DS | VoIP |  |  | 131236-DS-B | Data Sheet For Ceiling mounted ducted unit | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-09-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Expension tank | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Pre-insulated water pipeworks | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Chiller | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DS | BMS System |  |  | 131236-DS-B | Data Sheet For Chilled water pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Motor starter | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Sensors | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 2 | DS | Security CCTV System |  |  | 131236-DS-B | Data Sheet For POE Network Switch | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Fibre Patch Panel | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Cables | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Cable tray / conduit | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 2 | DS | Access Control System |  |  | 131236-DS-B | Data Sheet For Cables | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 2 | DS | VoIP |  |  | 131236-DS-B | Data Sheet For Single Mode Fibre Cable | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Cables | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Patch Panel | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Network Switch | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | BS | Stage 2 | DS | BMS System |  |  | 131236-DS-B | Data Sheet For PLC | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For RIO Module | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Network Switch | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Patch Panel | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | BS | Stage 2 | DS |  |  |  | 131236-DS-B | Data Sheet For Cable | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | CL |  |  |  | 131236-CL-B | Sprinkler System - Hydraulic Calculation at WIL 21 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | CL |  |  |  | 131236-CL-B | Sprinkler System - Hydraulic Calculation at WIL 22 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | CL |  |  |  | 131236-CL-B | Sprinkler System - Hydraulic Calculation at WIL 23 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | CL |  |  |  | 131236-CL-B | Gas Suppression System - Performance calculation at WIL 22 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | CL |  |  |  | 131236-CL-B | Gas Suppression System - Performance calculation at WIL 23 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | CL |  |  |  | 131236-CL-B | Fire Hosereel System - Hydraulic Calculation at WIL 21 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | CL |  |  |  | 131236-CL-B | Fire Hosereel System - Hydraulic Calculation at WIL 22 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | CL |  |  |  | 131236-CL-B | Fire Hosereel System - Hydraulic Calculation at WIL 23 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | CL |  |  |  | 131236-CL-B | MV System - Performance calculation at WIL 21 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | CL |  |  |  | 131236-CL-B | MV System - Performance calculation at WIL 22 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | CL |  |  |  | 131236-CL-B | MV System - Performance calculation at WIL 23 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | CL |  |  |  | 131236-CL-B | AHU System - Performance calculation at WIL 21 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | CL |  |  |  | 131236-CL-B | AHU System - Performance calculation at WIL 22 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | CL |  |  |  | 131236-CL-B | AHU System - Performance calculation at WIL 23 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | CL |  |  |  | 131236-CL-B | Chilled Water System - Hydraulic Calculation at WIL 21 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | CL |  |  |  | 131236-CL-B | Chilled Water System - Hydraulic Calculation at WIL 22 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | CL |  |  |  | 131236-CL-B | Chilled Water System - Hydraulic Calculation at WIL 23 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR | Fire Sprinkler System |  |  | 131236-DR-B | Fire sprinkler system GA at WIL 21 1st Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire sprinkler system GA at WIL 21 2nd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire sprinkler system GA at WIL 21 3rd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire sprinkler system GA at WIL 22 1st Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire sprinkler system GA at WIL 22 2nd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire sprinkler system GA at WIL 22 3rd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire sprinkler system GA of Water Monitoring System at WIL 22 PST Tank | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire sprinkler system GA at WIL 23 1st Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire sprinkler system GA at WIL 23 2nd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire sprinkler system GA at WIL 23 3rd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire sprinkler system GA at WIL 23 4th Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire sprinkler system GA at WIL 23 5th Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire sprinkler system GA at WIL 23 6th Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire sprinkler system Schematic Drawing for whole ILM 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR | Fire Alarm System |  |  | 131236-DR-B | Fire alarm system GA at WIL 21 1st Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire alarm system GA at WIL 21 2nd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire alarm system GA at WIL 21 3rd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire alarm system GA at WIL 21 Roof Area | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire alarm system GA at WIL 22 +05.30m | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire alarm system GA at WIL 22 +15.80m | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire alarm system GA at WIL 22 +19.47m | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire alarm system GA at WIL 22 +26.40m | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire alarm system GA at WIL 22 +28.90m | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire alarm system GA at WIL 22 +35.60m | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire alarm system GA at WIL 23 1st Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire alarm system GA at WIL 23 3rd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire alarm system GA at WIL 23 4th Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire alarm system GA at WIL 23 5th Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire alarm system GA at WIL 23 6th Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire alarm system GA at WIL 23 Roof Area | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire alarm system Schematic Drawing for whole ILM 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR | Gas Suppression System |  |  | 131236-DR-B | Gas suppression system GA at WIL 22 +15.80m | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Gas suppression system GA at WIL 22 +26.40m | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Gas suppression system GA at WIL 23 6th Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Gas suppression system Schematic Drawing for whole ILM 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR | Fire Hosereel System |  |  | 131236-DR-B | Fire hosereel system GA at WIL 21 1st Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire hosereel system GA at WIL 21 2nd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire hosereel system GA at WIL 21 3rd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire hosereel system GA at WIL 21 Roof Area | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire hosereel system GA at WIL 22 1st Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire hosereel system GA at WIL 22 2nd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire hosereel system GA at WIL 22 3rd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire hosereel system GA at WIL 22 6th Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire hosereel system GA at WIL 22 Roof Area | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire hosereel system GA at WIL 23 1st Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire hosereel system GA at WIL 23 2nd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire hosereel system GA at WIL 23 3rd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire hosereel system GA at WIL 23 4th Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire hosereel system GA at WIL 23 5th Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire hosereel system GA at WIL 23 6th Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire hosereel system GA at WIL 23 7th Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire hosereel system GA at WIL 23 Roof Area | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fire hosereel system Schematic Drawing for whole ILM 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Dry riser system GA at WIL 21 1st Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR | Dry Riser System |  |  | 131236-DR-B | Dry riser system GA at WIL 21 2nd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Dry riser system GA at WIL 21 3rd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Dry riser system GA at WIL 21 Roof Area | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Dry riser system GA at WIL 22 1st Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Dry riser system GA at WIL 22 2nd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Dry riser system GA at WIL 22 3rd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Dry riser system GA at WIL 22 6th Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Dry riser system GA at WIL 22 Roof Area | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Dry riser system GA at WIL 23 1st Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Dry riser system GA at WIL 23 2nd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Dry riser system GA at WIL 23 3rd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Dry riser system GA at WIL 23 4th Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Dry riser system GA at WIL 23 5th Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Dry riser system GA at WIL 23 6th Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Dry riser system GA at WIL 23 7th Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Dry riser system Schematic Drawing for whole ILM 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR | 2-Way ECV System |  |  | 131236-DR-B | 2-way EVC system at WIL 21 1st Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | 2-way EVC system at WIL 21 3rd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | 2-way EVC system at WIL 21 Roof Area | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | 2-way EVC system at WIL 22 1st Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | 2-way EVC system at WIL 22 3rd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | 2-way EVC system at WIL 22 Roof Area | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | 2-way EVC system at WIL 23 1st Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | 2-way EVC system at WIL 23 4th Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | 2-way EVC system at WIL 23 6th Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | 2-way EVC system at WIL 23 Roof Area | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | 2-way EVC system Schematic Drawing for whole ILM 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR | 1-Way EVC System |  |  | 131236-DR-B | 1-way EVC system at WIL 21 1st Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | 1-way EVC system at WIL 21 2nd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | 1-way EVC system at WIL 21 3rd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | 1-way EVC system at WIL 21 Roof Area | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | 1-way EVC system at WIL 22 1st Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | 1-way EVC system at WIL 22 2nd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | 1-way EVC system at WIL 22 Switchroom | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | 1-way EVC system at WIL 22 3rd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | 1-way EVC system at WIL 22 Switchroom | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | 1-way EVC system at WIL 22 Roof Area | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | 1-way EVC system at WIL 23 1st Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | 1-way EVC system at WIL 23 2nd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | 1-way EVC system at WIL 23 3rd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | 1-way EVC system at WIL 23 4th Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | 1-way EVC system at WIL 23 5th Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | 1-way EVC system at WIL 23 6th Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | 1-way EVC system at WIL 23 7th Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | 1-way EVC system at WIL 23 Roof Area | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | 1-way EVC system Schematic Drawing for whole ILM 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR | MV System |  |  | 131236-DR-B | Mechanical ventilation system GA at WIL 21 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Mechanical ventilation system GA at WIL 22 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Mechanical ventilation system GA at WIL 23 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Mechanical ventilation system GA Schematic Drawing for whole ILM 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR | Air Handling System |  |  | 131236-DR-B | Air handling system GA at WIL 21 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Air handling system GA at WIL 22 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Air handling system GA at WIL 23 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Air handling system GA Schematic Drawing for whole ILM 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR | Fan Coil Unit |  |  | 131236-DR-B | Fan coil unit GA at WIL 21 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Fan coil unit GA Schematic Drawing for whole ILM 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR | Chilled water system |  |  | 131236-DR-B | Chilled water system GA at WIL 21 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Chilled water system GA at WIL 22 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Chilled water system GA at WIL 23 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Chilled water system GA Schematic Drawing for whole ILM 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR | Security CCTV System |  |  | 131236-DR-B | Security CCTV system GA at WIL 21 1st Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Security CCTV system GA at WIL 22 1st Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Security CCTV system GA at WIL 22 2nd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Security CCTV system GA at WIL 22 3rd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Security CCTV system GA at WIL 22 6th Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Security CCTV system GA at WIL 23 6th Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Security CCTV system Schematic Drawing for whole ILM 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR | Plant CCTV System |  |  | 131236-DR-B | Plant CCTV system GA at WIL 21 1st Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Plant CCTV system GA at WIL 21 3rd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Plant CCTV system GA at WIL 21 Roof Area | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Plant CCTV system GA at WIL 22 1st Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Plant CCTV system GA at WIL 22 2nd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Plant CCTV system GA at WIL 22 6th Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Plant CCTV system GA at WIL 22 Roof Area | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Plant CCTV system GA at WIL 23 1st Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Plant CCTV system GA at WIL 23 3rd Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Plant CCTV system GA at WIL 23 6th Storey | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Plant CCTV system Schematic Drawing for whole ILM 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR | Access Control System |  |  | 131236-DR-B | Access control system GA at WIL 21 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Access control system GA at WIL 22 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Access control system GA at WIL 23 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Access control system GA Schematic Drawing for whole ILM 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR | VoIP |  |  | 131236-DR-B | Telephone system GA at WIL 21 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Telephone system GA WIL 22 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Telephone system Schematic Drawing for whole ILM 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | Telephone system Schematic for VoIP Backbone | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR | BMS System |  |  | 131236-DR-B | BMS system GA at WIL 21 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | BMS system GA at WIL 22 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | BMS system GA at WIL 23 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | BMS system Schematic Drawing for whole ILM 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | BS | Stage 2 | DR |  |  |  | 131236-DR-B | BMS system Schematic for Non-Process Backbone BMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | BS | Stage 2 | DR | Lift System |  |  | 131236-DR-B | Lift system GA at WIL 22 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 2 | DR |  |  |  | 131236-DR-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-04-01 | BS | Stage 3 | QA |  |  |  | 131236-QA-B | ITP of FAT - Mechanical Ventilation Fans | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-04-01 | BS | Stage 3 | QA |  |  |  | 131236-QA-B | ITP of FAT - Chilled Water Pumps | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-04-01 | BS | Stage 3 | QA |  |  |  | 131236-QA-B | ITP of FAT - Air Handling Units | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-04-01 | BS | Stage 3 | QA |  |  |  | 131236-QA-B | ITP of FAT - Fan Coil Unit | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-04-01 | BS | Stage 3 | QA |  |  |  | 131236-QA-B | ITP of FAT - Water-Cooled Chiller | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-04-01 | BS | Stage 3 | QA |  |  |  | 131236-QA-B | ITP of FAT - Electric Lift | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-04-01 | BS | Stage 3 | QA |  |  |  | 131236-QA-B | ITP of FAT - BIO / RIO Panel | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - MV Fan | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - Chilled Water Pumps | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - Air Handling Units | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - Fan Coil Unit | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - Water-Cooled Chiller | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - Auto Tube Cleaning System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - Expansion Tank | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - Pre-Insulated Chilled Water Pipe | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - HDPE Condenser Pipe | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - Ducting | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - Ducting Insulation | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - Refrigerant Pipe | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - Strainer | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - Damper | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - Temperature Transmitter | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - Pressure Transmitter | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - Pressure Differential Switch | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - Pressure Differential Transmitter | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - CO2 Sensor | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - Smoke Detector | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - Duct Smoke Detector | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - Electromagnetic Flowmeter | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - Level Gauge | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - Modulating Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - Ductile Iron Cement Line Pipes & Fitting | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - Hot Dipped Galvanized Steel Pipe | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - Stainless Steel 304 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - Fire Alarm Panel & Mimic Panel | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - FR Cables | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - Alarm Bell, Strobe light, Manual Call Points | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - Clean Gas System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - Clean Gas Panel. | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - Breeching Inlet | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - Sprinkler Head | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - Water Monitoring System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - 2 Way EVC Panels | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - 1 Way EVC Panels | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - RIO Panel | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - Fibre Patch Panel | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - FO Cables | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | Manufacturer Certificate of Conformance - CAT 6 Cables | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - Electric Lift | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 21 BIO Panel 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 21 BIO Panel 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 21 BIO Panel 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 21 BIO Panel 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 21 BIO Panel 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 21 BIO Panel 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 21 BIO Panel 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 21 BIO Panel 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 21 BIO Panel 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 21 BIO Panel 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 22 BIO Panel 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 22 BIO Panel 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 22 BIO Panel 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 22 BIO Panel 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 22 BIO Panel 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-08-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 22 BIO Panel 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-08-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 22 BIO Panel 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-08-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 22 BIO Panel 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-08-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 22 BIO Panel 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-08-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 22 BIO Panel 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-08-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 23 BIO Panel 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-08-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 23 BIO Panel 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-08-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 23 BIO Panel 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-08-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 23 BIO Panel 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-08-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 23 BIO Panel 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-08-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 23 BIO Panel 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-08-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 23 BIO Panel 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-08-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 23 BIO Panel 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-08-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 23 BIO Panel 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-08-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 23 BIO Panel 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-08-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 23 BIO Panel 11 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-08-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 23 BIO Panel 12 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-08-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 23 BIO Panel 13 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-08-01 | BS | Stage 3 | RT |  |  |  | 131236-RT-B | FAT Report - WIL 23 BIO Panel 14 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 4 | SH |  |  |  | 131236-SH-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-04-01 | BS | Stage 5 | MS |  |  |  | 131236-MS-B | MSRA For Mechanical Ventilation Installation | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-04-01 | BS | Stage 5 | MS |  |  |  | 131236-MS-B | MSRA For Pre-insulated Chilled Water And Condenser Water Supply/Return Pipework System Installation | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-04-01 | BS | Stage 5 | MS |  |  |  | 131236-MS-B | MSRA For Air Handling Systems Installation | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-04-01 | BS | Stage 5 | MS |  |  |  | 131236-MS-B | MSRA For Fan Coil Units Installation | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | BS | Stage 5 | MS |  |  |  | 131236-MS-B | MSRA For Chilled water And Condenser Water Pump System Installation. | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | BS | Stage 5 | MS |  |  |  | 131236-MS-B | MSRA For Fan Coil Units Installation | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | BS | Stage 5 | MS |  |  |  | 131236-MS-B | MSRA For Lifting, Moving and Shifting Materials at Site Activities | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | BS | Stage 5 | MS |  |  |  | 131236-MS-B | MSRA For Chiller | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | BS | Stage 5 | MS |  |  |  | 131236-MS-B | Method Statement and Risk Assessments For Delivery of ACMV Equipment | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-08-01 | BS | Stage 5 | QA |  |  |  | 131236-QA-B | Testing and Commissioning Procedure For Air Handling Unit | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-08-01 | BS | Stage 5 | QA |  |  |  | 131236-QA-B | Testing and Commissioning Procedure For MV Fan | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-09-01 | BS | Stage 5 | QA |  |  |  | 131236-QA-B | Testing and Commissioning Procedure For Pump | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-09-01 | BS | Stage 5 | QA |  |  |  | 131236-QA-B | Testing and Commissioning Procedure For Water Cooled Chiller | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-09-01 | BS | Stage 5 | QA |  |  |  | 131236-QA-B | Testing and Commissioning Procedure For Duct Leakage Test | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-09-01 | BS | Stage 5 | MS |  |  |  | 131236-MS-B | Method Statement and Risk Assessment For Stainless Steel Branch Pipe Connection Fabrication and Welding On Site | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-10-01 | BS | Stage 5 | MS |  |  |  | 131236-MS-B | Method Statement and Risk Assessment of Chemical Flushing for Air-Conditioning Chilled & Condenser Water Pipe System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-10-01 | BS | Stage 5 | MS |  |  |  | 131236-MS-B | Method Statement for Air Balancing of ACMV System (AHU / MV FAN) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | BS | Stage 5 | MS |  |  |  | 131236-MS-B | MSRA For Ductile Iron Cement Lined (DICL) Pipe & Fittings | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | BS | Stage 5 | MS |  |  |  | 131236-MS-B | MSRA For Dry Riser System Installation | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | BS | Stage 5 | MS |  |  |  | 131236-MS-B | MSRAFor Sprinkler System Installation | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | BS | Stage 5 | MS |  |  |  | 131236-MS-B | MSRA For Hose Reel System Installation | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | BS | Stage 5 | MS |  |  |  | 131236-MS-B | MSRA For Site Delivery/Installation of Fire Alarm System, 1-Way & 2-Way EVC System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | BS | Stage 5 | MS |  |  |  | 131236-MS-B | Method Statement and Risk Assessment For Site Delivery/Installation of Clean Gas System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | BS | Stage 5 | MS |  |  |  | 131236-MS-B | Method Statement And Risk Assessment For Breeching Inlet Earthing System Installation | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-09-01 | BS | Stage 5 | QA |  |  |  | 131236-QA-B | Testing and Commissioning Procedure of Dry Riser System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-09-01 | BS | Stage 5 | QA |  |  |  | 131236-QA-B | Testing and Commissioning Procedure of Hosereel System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-10-01 | BS | Stage 5 | QA |  |  |  | 131236-QA-B | Testing and Commissioning Procedure of Sprinkler System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-10-01 | BS | Stage 5 | QA |  |  |  | 131236-QA-B | Testing and Commissioning Procedure of 2-Way EVCS System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-10-01 | BS | Stage 5 | QA |  |  |  | 131236-QA-B | Testing and Commissioning Procedure of Fire Alarm System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-10-01 | BS | Stage 5 | QA |  |  |  | 131236-QA-B | Testing and Commissioning Procedure of Clean Gas System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-10-01 | BS | Stage 5 | QA |  |  |  | 131236-QA-B | Testing and Commissioning Procedure of Fire Hydrant System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | BS | Stage 5 | MS |  |  |  | 131236-MS-B | MSRA For Passenger And Service Lift Installation | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-10-01 | BS | Stage 5 | MS |  |  |  | 131236-MS-B | Method Statement For Testing & Commissioning Of Electric Lift | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 6 | QA |  |  |  | 131236-QA-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 6 | QA |  |  |  | 131236-QA-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 6 | QA |  |  |  | 131236-QA-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 6 | QA |  |  |  | 131236-QA-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 6 | QA |  |  |  | 131236-QA-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 6 | QA |  |  |  | 131236-QA-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 6 | QA |  |  |  | 131236-QA-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 6 | QA |  |  |  | 131236-QA-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 6 | QA |  |  |  | 131236-QA-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 6 | QA |  |  |  | 131236-QA-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 6 | QA |  |  |  | 131236-QA-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 6 | QA |  |  |  | 131236-QA-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 6 | QA |  |  |  | 131236-QA-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 6 | QA |  |  |  | 131236-QA-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 6 | QA |  |  |  | 131236-QA-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 6 | QA |  |  |  | 131236-QA-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 6 | QA |  |  |  | 131236-QA-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 6 | QA |  |  |  | 131236-QA-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 6 | QA |  |  |  | 131236-QA-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 6 | QA |  |  |  | 131236-QA-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 7 | OM |  |  |  | 131236-OM-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 7 | OM |  |  |  | 131236-OM-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 7 | OM |  |  |  | 131236-OM-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 7 | OM |  |  |  | 131236-OM-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 7 | OM |  |  |  | 131236-OM-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 7 | OM |  |  |  | 131236-OM-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 7 | OM |  |  |  | 131236-OM-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 7 | OM |  |  |  | 131236-OM-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 7 | OM |  |  |  | 131236-OM-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 7 | OM |  |  |  | 131236-OM-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 7 | OM |  |  |  | 131236-OM-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 7 | OM |  |  |  | 131236-OM-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 7 | OM |  |  |  | 131236-OM-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 7 | OM |  |  |  | 131236-OM-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 7 | OM |  |  |  | 131236-OM-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 7 | OM |  |  |  | 131236-OM-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 7 | OM |  |  |  | 131236-OM-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 7 | OM |  |  |  | 131236-OM-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 7 | OM |  |  |  | 131236-OM-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BS | Stage 7 | OM |  |  |  | 131236-OM-B | [9 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 1 | VI | Static Mixer | WIL23 |  | 131236-WIL23-VI-M | Vendor Approval - Static Mixer | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-06-01 | Mech | Stage 1 | VI | Surge Vessel | WNS03 |  | 131236-WNS03-VI-M-0001 | Vendor Information Submission For Design, Supply, Manufacturing, FAT, and Delivery Of Surge Vessel Including Instrument and Structure Support (SYNCHONG HOE ENGINEERING SDN. BHD.) | [8 empty] | RTR - Returned for Resubmission | AWC - Approved with Comments |  |  |  | 0 | 1
Planned | 2026-10-01 | Mech | Stage 1 | VI | Lifting Equipment | WSW46 |  | 131236-WSW46-VI-M | Vendor Approval - Lifting Equipment(EOTC, Monorail, Travelling Jib Crane and Davit Cranes) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-07-01 | Mech | Stage 1 | VI | Intermediate Screen, Dewatering Press | WIL21 |  | 131236-WIL21-VI-M-0001 | Vendor Information For Intermediate Screen And Its Associated Dewatering Press (WAM Singapore BHM Pte Ltd) | [8 empty] | RTR - Returned for Resubmission | AWC - Approved with Comments |  |  |  | 0 | 1
Planned | 2026-05-01 | Mech | Stage 1 | VI | Grit Classifier | WIL21 |  | 131236-WIL21-VI-M-0002 | Vendor Information For Grit Classifier (WAM Singapore BHM Pte Ltd) | [8 empty] | RTR - Returned for Resubmission | AWC - Approved with Comments |  |  |  | 0 | 1
Planned | 2026-06-01 | Mech | Stage 1 | VI | Conveyor | WIL21 |  | 131236-WIL21-VI-M-0003 | Vendor Information For Conveyor (WAM Singapore BHM Pte Ltd) | [8 empty] | RTR - Returned for Resubmission | AWC - Approved with Comments |  |  |  | 0 | 1
Planned | 2026-10-01 | Mech | Stage 1 | VI | Fine Screen | WSW46 |  | 131236-WSW46-VI-M-0002 | Vendor Approval - Fine Screen, And MBR Fine Screen | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Mech | Stage 1 | VI | Slide Gate | WIL21 |  | 131236-WIL21-VI-M | Vendor Information - Slide Gates (for Screenings and Grits Hoppers) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-08-01 | Mech | Stage 1 | VI | Scum and Grease Removal Equipment | WIL21 |  | 131236-WIL21-VI-M-0004 | Vendor Information for Grit Tank Grease And Scum Removal Equipment (PROBIG GmbH) | [8 empty] | RTR - Returned for Resubmission | NAP - Not Approved |  |  |  | 0 | 1
Planned | 2027-05-01 | Mech | Stage 1 | VI | Auto Lubrication System | WSW46 |  | 131236-WSW46-VI-M | Vendor Approval - Auto Lubrication System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 1 | VI | Tank Cover | WSW46 |  | 131236-WSW46-VI-M | Vendor Information - Odour Containment Covers for Grit Tank and PST Tank | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 1 | VI | Safety Shower | WSW46 |  | 131236-WSW46-VI-M | Vendor Information for Safety Shower and Eyewash | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 1 | VI | Valve | WSW46 |  | 131236-WSW46-VI-M | Vendor Approval - Supply, Manufacturing, Factory Acceptance Test & Delivery of Foul Air FRP Dampers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 1 | VI | Valve | WSW46 |  | 131236-WSW46-VI-M | Vendor Approval - Air Release (Combination) Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 1 | VI | Valve | WSW46 |  | 131236-WSW46-VI-M | Vendor Approval - Metal Ball Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 1 | VI | Valve | WSW46 |  | 131236-WSW46-VI-M | Vendor Approval - Non-Return Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 1 | VI | Valve | WSW46 |  | 131236-WSW46-VI-M | Vendor Approval - Butterfly Valves And Actuators | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 1 | VI | Valve | WSW46 |  | 131236-WSW46-VI-M | Vendor Approval - Knife Gate Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 1 | VI | Valve | WSW46 |  | 131236-WSW46-VI-M | Vendor Approval - Pressure Reducing Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 1 | VI | Valve | WSW46 |  | 131236-WSW46-VI-M | Vendor Approval - Pressure Sustaining Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 1 | VI | Valve | WIL06 |  | 131236-WIL06-VI-M | Vendor Approval - Plastic Ball Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 1 | VI | Valve | WIL06 |  | 131236-WIL06-VI-M | Vendor Approval - Plastic Ball Check Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 1 | VI | Valve | WIL06 |  | 131236-WIL06-VI-M | Vendor Approval - Plastic Back Pressure Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 1 | VI | Valve | WIL06 |  | 131236-WIL06-VI-M | Vendor Approval - Plastic Pressure Relief Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Mech | Stage 1 | VI | Hopper | WIL21 |  | 131236-WIL21-VI-M | Vendor Information - Screenings and Grits Hoppers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Mech | Stage 1 | VI | Grit Tank Launder, Scum Cover Plate, Picket Fence And Removable Panel | WIL21 |  | 131236-WIL21-VI-M | Vendor Information - Grit Tank Launder, Scum Cover Plate, Picket Fence And Removable Panel | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Mech | Stage 1 | VI | Baffle Plate | WIL23 |  | 131236-WIL23-VI-M | Vendor Approval - Stainless Steel (SS316L) Plates | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Mech | Stage 1 | VI | Removable Panel | WIL21 |  | 131236-WIL21-VI-M | Vendor Information for Supply and Delivery of SS Grit Tank Inlet and Outlet Removable Panel | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 1 | VI | Valve | WNS03 |  | 131236-WNS03-VI-M | Vendor Approval - Safety Relief Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 1 | VI | Spray Nozzle | WSW46 |  | 131236-WSW46-VI-M | Preliminary Design Submission for Design, Supply, Manufacturing, FAT, Delivery, Supervision of Installation and T&C for Spray Nozzle | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 1 | VI | Penstock | WIL23 |  | 131236-WIL23-VI-M | Vendor Approval - Penstock | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Mech | Stage 2 | DS | Static Mixer | WIL23 |  | 131236-WIL23-DS-M | Datasheet - ILM2 Membrane Cleaning Pump Citric Acid Static Mixer | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Mech | Stage 2 | DS | Static Mixer | WIL23 |  | 131236-WIL23-DS-M | Datasheet - ILM2 Membrane Cleaning Pump Sodium Hypochlorite Static Mixer | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 2 | DS | Surge Vessel | WNS03 |  | 131236-WNS03-DS-M | Datasheet - Surge Vessel | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DS | Lifting Equipment | WIL21 |  | 131236-WIL21-DS-M | Datasheet - ILM2 WIL21 Lifting Equipment EOT Crane | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DS | Lifting Equipment | WIL21 |  | 131236-WIL21-DS-M | Datasheet - ILM2 WIL21 Lifting Equipment Monorail | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DS | Lifting Equipment | WIL21 |  | 131236-WIL21-DS-M | Datasheet - ILM2 WIL21 Davit Crane | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DS | Lifting Equipment | WIL22 |  | 131236-WIL22-DS-M | Datasheet - ILM2 WIL22 Lifting Equipment Monorail | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DS | Lifting Equipment | WIL22 |  | 131236-WIL22-DS-M | Datasheet - ILM2 WIL22 Davit Crane | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DS | Lifting Equipment | WIL23 |  | 131236-WIL23-DS-M | Datasheet - ILM2 WIL23 Lifting Equipment EOT Crane | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DS | Lifting Equipment | WIL23 |  | 131236-WIL23-DS-M | Datasheet - ILM2 WIL23 Lifting Equipment Monorail | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DS | Lifting Equipment | WIL23 |  | 131236-WIL23-DS-M | Datasheet - ILM2 DeOx RAS Tank Monorail Beam with Electric Chain Hoist | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DS | Lifting Equipment | WIL23 |  | 131236-WIL23-DS-M | Datasheet - ILM2 WIL23 Mobile Crane | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 2 | DS | Intermediate Screen, Dewatering Press | WIL21 |  | 131236-WIL21-DS-M | Datasheet - ILM2 Intermediate Screens and Dewatering Presses | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 2 | DS | Grit Classifier | WIL21 |  | 131236-WIL21-DS-M | Datasheet - ILM2 Grit Classifiers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 2 | DS | Conveyor | WIL21 |  | 131236-WIL21-DS-M | Datasheet - ILM2 Intermediate Screen Loadout Conveyor | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DS | Fine Screen | WIL21 |  | 131236-WIL21-DS-M | Datasheet - ILM2 Fine Screens Dewatering Presses | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Mech | Stage 2 | DS | Conveyor | WIL21 |  | 131236-WIL21-DS-M | Datasheet - ILM2 Fine Screen Loadout Conveyor | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DS | Fine Screen | WIL23 |  | 131236-WIL23-DS-M | Datasheet - ILM2 MBR Fine Screen With Launder and Dewatering Press | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 2 | DS | Slide Gate | WIL21 |  | 131236-WIL21-DS-M | Datasheet - Slide Gates (for Screenings and Grits Hoppers) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DS | Scum and Grease Removal Equipment | WIL21 |  | 131236-WIL21-DS-M | Datasheet - ILM2 Grit Tank Scum Collector | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | Mech | Stage 2 | DS | Auto Lubrication System | WSW46 |  | 131236-WSW46-DS-M | Datasheet - ILM2 Automatic Lubrication System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Mech | Stage 2 | DS | Tank Cover | WIL21 |  | 131236-WIL21-DS-M | Datasheet - ILM2 Aerated Grit Tank Covers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Mech | Stage 2 | DS | Tank Cover | WIL22 |  | 131236-WIL22-DS-M | Datasheet - ILM2 PST Covers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Mech | Stage 2 | DS | Safety Shower | WSW46 |  | 131236-WSW46-DS-M | Datasheet - Safety Shower and Eyewash | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Mech | Stage 2 | DS | Valve | WIL21 |  | 131236-WIL21-DS-M | Datasheet - WIL21 Foul Air FRP Dampers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Mech | Stage 2 | DS | Valve | WIL22 |  | 131236-WIL22-DS-M | Datasheet - WIL22 Foul Air FRP Dampers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Mech | Stage 2 | DS | Valve | WIL23 |  | 131236-WIL23-DS-M | Datasheet -WIL23 Foul Air FRP Dampers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL21 |  | 131236-WIL21-DS-M | Datasheet - WIL21 Dual Flap Check Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL21 |  | 131236-WIL21-DS-M | Datasheet - WIL21 Motorised Butterfly Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL21 |  | 131236-WIL21-DS-M | Datasheet - WIL21 Manual Butterfly Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL21 |  | 131236-WIL21-DS-M | Datasheet - WIL21 Swing Check Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL21 |  | 131236-WIL21-DS-M | Datasheet - WIL21 DN1600 Eccentric Butterfly Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL21 |  | 131236-WIL21-DS-M | Datasheet - WIL21 Manual Knife Gate Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL21 |  | 131236-WIL21-DS-M | Datasheet - WIL21 Motorised Knife Gate Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL21 |  | 131236-WIL21-DS-M | Datasheet - WIL21 Lift Check Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL21 |  | 131236-WIL21-DS-M | Datasheet - WIL21 Pressure Regulating Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL21 |  | 131236-WIL21-DS-M | Datasheet - WIL21 Ball Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL21 |  | 131236-WIL21-DS-M | Datasheet - WIL21 Air Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL21 |  | 131236-WIL21-DS-M | Datasheet - WIL21 Pressure Relief Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL22 |  | 131236-WIL22-DS-M | Datasheet - WIL22 Manual Knife Gate Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL22 |  | 131236-WIL22-DS-M | Datasheet - WIL22 Motorised Knife Gate Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL22 |  | 131236-WIL22-DS-M | Datasheet - WIL22 Manual Butterfly Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL22 |  | 131236-WIL22-DS-M | Datasheet - WIL22 Motorised Butterfly Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL22 |  | 131236-WIL22-DS-M | Datasheet - WIL22 Swing Check Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL23 |  | 131236-WIL23-DS-M | Datasheet - WIL23 Dual Flap Check Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL23 |  | 131236-WIL23-DS-M | Datasheet - WIL23 Swing Check Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL23 |  | 131236-WIL23-DS-M | Datasheet - WIL23 Manual Knife Gate Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL23 |  | 131236-WIL23-DS-M | Datasheet - WIL23 Motorised Knife Gate Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL23 |  | 131236-WIL23-DS-M | Datasheet - WIL23 Lift Check Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL23 |  | 131236-WIL23-DS-M | Datasheet - WIL23 Manual Butterfly Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL23 |  | 131236-WIL23-DS-M | Datasheet - WIL23 Motorised Butterfly Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL23 |  | 131236-WIL23-DS-M | Datasheet - WIL23 Pneumatic Butterfly Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL00 |  | 131236-WIL00-DS-M | Datasheet - WIL00 Dual Flap Check Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL00 |  | 131236-WIL00-DS-M | Datasheet - WIL00 Manual Butterfly Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL00 |  | 131236-WIL00-DS-M | Datasheet - WIL00 Motorised Butterfly Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL06 |  | 131236-WIL06-DS-M | Datasheet - WIL06 Plastic Ball Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL06 |  | 131236-WIL06-DS-M | Datasheet - WIL06 Plastic Ball Check Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL06 |  | 131236-WIL06-DS-M | Datasheet - WIL06 Plastic Back Pressure Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WIL06 |  | 131236-WIL06-DS-M | Datasheet - WIL06 Plastic Pressure Relief Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Hopper | WIL21 |  | 131236-WIL21-DS-M | Datasheet - ILM2 Screening and Grit Hopper | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DS | Valve | WNS03 |  | 131236-WNS03-DS-M | Datasheet - ILM00 Safety Relief Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 2 | DS | Spray Nozzle | WIL21 |  | 131236-WIL21-DS-M | Datasheet - WIL21 Spray Nozzle | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 2 | DS | Spray Nozzle | WIL22 |  | 131236-WIL22-DS-M | Datasheet - WIL22 Spray Nozzle | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 2 | DS | Spray Nozzle | WIL23 |  | 131236-WIL23-DS-M | Datasheet - WIL23 Spray Nozzle | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Mech | Stage 2 | DS | Conveyor | WIL21 |  | 131236-WIL21-DS-M | Datasheet - ILM2 Submerged Grit Screw Conveyor | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Mech | Stage 2 | DS | Conveyor | WIL21 |  | 131236-WIL21-DS-M | Datasheet - ILM2 Grit Loadout Conveyor | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | CL | Chemical Dosing Pump | WIL06 |  | 131236-WIL06-CL-M | Dosing Pump Plinth Design And Calculation | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | CL |  | WIL21 |  | 131236-WIL21-CL-M | WIL 21 Plinth Design and Calculation | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | CL |  | WIL22 |  | 131236-WIL22-CL-M | WIL22 Plinth Design and Calculation | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | CL |  | WIL23 |  | 131236-WIL23-CL-M | WIL23 Plinth Design and Calculation | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 2 | CL | Compressed Air System | WNS03 |  | 131236-WNS03-CL-M | Portable Compressure for Surge Tank Sizing Calculation | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 2 | CL | Hopper | WIL21 |  | 131236-WIL21-CL-M | Calculation Report For Grit And Screening Hopper | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-04-01 | Mech | Stage 2 | CL | Lifting Equipment | WSW46 |  | 131236-WSW46-CL-M-0001 | Design Calculation For Existing RC Slab And Beam For Max.10 Tons Mini Spider Crane Parking And Access At SFL. 15.8m Industrial LM2 (WIL 21 AND 22) | [8 empty] | RTR - Returned for Resubmission | NAP - Not Approved |  |  |  | 0 | 1
Planned | 2026-10-01 | Mech | Stage 2 | CL |  | WIL21 |  | 131236-WIL21-CL-M | Calculation For Grit Tank Weir And Launder Sizing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Mech | Stage 2 | CL |  | WIL21 |  | 131236-WIL21-CL-M | Design Calculation For SS316L Removable Panels For Future Grit Tank | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Mech | Stage 2 | CL |  | WIL21 |  | 131236-WIL21-CL-M | Design Calculation For Grit Picket Fence Report | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Mech | Stage 2 | CL |  | WIL21 |  | 131236-WIL21-CL-M | Design Calculation for Grit Launder and Scum Cover Plate Report | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 2 | CL |  | WIL23 |  | 131236-WIL23-CL-M | Design Calculation for Membrane Scum Wet Well Sizing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | CL |  | WIL23 |  | 131236-WIL23-CL-M | MBR Tank Concrete Stump Design And Calculation | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Mech | Stage 2 | DR | Static Mixer | WIL23 |  | 131236-WIL23-DR-M | GA Drawing - ILM2 Membrane Cleaning Pump Citric Acid Static Mixer | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Mech | Stage 2 | DR | Static Mixer | WIL23 |  | 131236-WIL23-DR-M | GA Drawing - ILM2 Membrane Cleaning Pump Sodium Hypochlorite Static Mixer | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 2 | DR | Surge Vessel | WNS03 |  | 131236-WNS03-DR-M | GA Drawing - Surge Vessel | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 2 | DR | Compressed Air System | WNS03 |  | 131236-WNS03-DR-M | GA Drawing - Portable Compressure for Surge Tank | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 2 | DR | Lifting Equipment | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - ILM2 WIL21 Lifting Equipment EOT Crane | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 2 | DR | Lifting Equipment | WIL21 |  | 131236-WIL21-DR-M | ILM2 WIL21 Lifting Equipment EOT Crane Plan View | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 2 | DR | Lifting Equipment | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - ILM2 WIL21 Lifting Equipment Monorail | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 2 | DR | Lifting Equipment | WIL21 |  | 131236-WIL21-DR-M | ILM2 WIL21 Lifting Equipment Monorail Plan View | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 2 | DR | Lifting Equipment | WIL21 |  | 131236-WIL21-DR-M | ILM2 Grit Pumps Monorail Plan View | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 2 | DR | Lifting Equipment | WIL21 |  | 131236-WIL21-DR-M | ILM2 Grit Pumps Monorail Side View | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 2 | DR | Lifting Equipment | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - ILM2 WIL21 Davit Crane | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 2 | DR | Lifting Equipment | WIL22 |  | 131236-WIL22-DR-M | GA Drawing - ILM2 WIL22 Lifting Equipment Monorail | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 2 | DR | Lifting Equipment | WIL22 |  | 131236-WIL22-DR-M | GA Drawing - ILM2 WIL22 Davit Crane | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 2 | DR | Lifting Equipment | WIL23 |  | 131236-WIL23-DR-M | GA Drawing - ILM2 WIL23 Lifting Equipment EOT Crane | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 2 | DR | Lifting Equipment | WIL23 |  | 131236-WIL23-DR-M | GA Drawing - ILM2 WIL23 Lifting Equipment Monorail | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 2 | DR | Lifting Equipment | WIL23 |  | 131236-WIL23-DR-M | GA Drawing - ILM2 DeOx RAS Tank Monorail Beam with Electric Chain Hoist | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 2 | DR | Lifting Equipment | WIL23 |  | 131236-WIL23-DR-M | GA Drawing - ILM2 WIL23 Mobile Crane | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 2 | DR | Intermediate Screen, Dewatering Press | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - ILM2 Intermediate Screens and Dewatering Presses 1 of 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 2 | DR | Intermediate Screen, Dewatering Press | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - ILM2 Intermediate Screens and Dewatering Presses 2 of 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 2 | DR | Intermediate Screen, Dewatering Press | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - ILM2 Intermediate Screens and Dewatering Presses 3 of 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 2 | DR | Intermediate Screen, Dewatering Press | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - ILM2 Intermediate Screens and Dewatering Presses Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 2 | DR | Intermediate Screen, Dewatering Press | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - ILM2 Grit Classifiers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 2 | DR | Conveyor | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - ILM2 Intermediate Screen Loadout Conveyor | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 2 | DR | Conveyor | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - ILM2 Intermediate Screen Cross Conveyor Sheet 1 of 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 2 | DR | Conveyor | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - ILM2 Intermediate Screen Cross Conveyor Sheet 2 of 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 2 | DR | Conveyor | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - ILM2 Intermediate Screen Cross Conveyor Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DR | Fine Screen | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - ILM2 Fine Screens Dewatering Presses | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DR | Fine Screen | WIL21 |  | 131236-WIL21-DR-M | Fine Screen and Dewatering Press Setting Out Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DR | Fine Screen | WIL21 |  | 131236-WIL21-DR-M | Fine Screen and Dewatering Press Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DR | Conveyor | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - ILM2 Fine Screen Loadout Conveyor | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DR | Conveyor | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - ILM2 Fine Screen Cross Conveyor Sheet 1 of 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DR | Conveyor | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - ILM2 Fine Screen Cross Conveyor Sheet 2 of 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DR | Fine Screen | WIL23 |  | 131236-WIL23-DR-M | GA Drawing - ILM2 MBR Fine Screen With Launder and Dewatering Press | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DR | Fine Screen | WIL23 |  | 131236-WIL23-DR-M | MBR Fine Screen and Dewatering Press Setting Out Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DR | Fine Screen | WIL23 |  | 131236-WIL23-DR-M | MBR Fine Screen and Dewatering Press Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DR | Slide Gate | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - Slide Gates (for Screenings and Grits Hoppers) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DR | Scum and Grease Removal Equipment | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - ILM2 Grit Tank Scum Collector | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DR | Scum and Grease Removal Equipment | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - ILM2 Grit Tank Scum Collector Nameplate Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DR | Scum and Grease Removal Equipment | WIL21 |  | 131236-WIL21-DR-M | GENERAL ARRANGEMENT CHAIN AND FLIGHT SCRAPER FOR SURFACE SCUM REMOVAL | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DR | Scum and Grease Removal Equipment | WIL21 |  | 131236-WIL21-DR-M | DETAIL DRAWING MAIN SHAFT DETAIL 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DR | Scum and Grease Removal Equipment | WIL21 |  | 131236-WIL21-DR-M | DETAIL DRAWING DRIVE UNIT DETAIL 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DR | Scum and Grease Removal Equipment | WIL21 |  | 131236-WIL21-DR-M | DETAIL DRAWING FLIGHT PRO9 FLOTAT DETAIL 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DR | Scum and Grease Removal Equipment | WIL21 |  | 131236-WIL21-DR-M | DETAIL DRAWING CORNER SHAFT DETAIL 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DR | Scum and Grease Removal Equipment | WIL21 |  | 131236-WIL21-DR-M | DETAIL DRAWING RETURN TRACK DETAIL 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DR | Scum and Grease Removal Equipment | WIL21 |  | 131236-WIL21-DR-M | DETAIL DRAWING SUPPORT TRACK DETAIL 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 2 | DR | PST Lamella/Scraper/Scum Collector | WIL22 |  | 131236-WIL22-DR-M | GA Drawing - ILM2 Primary Sedimentation Tank Lamella Settlement System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 2 | DR | PST Lamella/Scraper/Scum Collector | WIL22 |  | 131236-WIL22-DR-M | ILM2 Secondary Treatment - Details LAMELLA Cleaning Assembly | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 2 | DR | PST Lamella/Scraper/Scum Collector | WIL22 |  | 131236-WIL22-DR-M | ILM2 Secondary Treatment - LAMELLA LPS88 Baffle Plate | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Mech | Stage 2 | DR | Auto Lubrication System | WSW46 |  | 131236-WSW46-DR-M | GA Drawing - ILM2 Automatic Lubrication System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Tank Cover | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - ILM2 Aerated Grit Tank Covers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Tank Cover | WIL22 |  | 131236-WIL22-DR-M | GA Drawing - ILM2 PST Covers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Mech | Stage 2 | DR | Safety Shower | WSW46 |  | 131236-WSW46-DR-M | GA Drawing - Safety Shower and Eyewash | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - WIL21 Foul Air FRP Dampers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL22 |  | 131236-WIL22-DR-M | GA Drawing - WIL22 Foul Air FRP Dampers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL23 |  | 131236-WIL23-DR-M | GA Drawing -WIL23 Foul Air FRP Dampers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - WIL21 Dual Flap Check Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - WIL21 Motorised Butterfly Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - WIL21 Manual Butterfly Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - WIL21 Swing Check Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - WIL21 DN1600 Eccentric Butterfly Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - WIL21 Manual Knife Gate Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - WIL21 Motorised Knife Gate Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - WIL21 Lift Check Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - WIL21 Pressure Regulating Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - WIL21 Ball Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - WIL21 Air Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - WIL21 Pressure Relief Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL22 |  | 131236-WIL22-DR-M | GA Drawing - WIL22 Manual Knife Gate Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL22 |  | 131236-WIL22-DR-M | GA Drawing - WIL22 Motorised Knife Gate Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL22 |  | 131236-WIL22-DR-M | GA Drawing - WIL22 Manual Butterfly Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL22 |  | 131236-WIL22-DR-M | GA Drawing - WIL22 Motorised Butterfly Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL22 |  | 131236-WIL22-DR-M | GA Drawing - WIL22 Swing Check Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL23 |  | 131236-WIL23-DR-M | GA Drawing - WIL23 Dual Flap Check Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL23 |  | 131236-WIL23-DR-M | GA Drawing - WIL23 Swing Check Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL23 |  | 131236-WIL23-DR-M | GA Drawing - WIL23 Manual Knife Gate Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL23 |  | 131236-WIL23-DR-M | GA Drawing - WIL23 Motorised Knife Gate Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL23 |  | 131236-WIL23-DR-M | GA Drawing - WIL23 Lift Check Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL23 |  | 131236-WIL23-DR-M | GA Drawing - WIL23 Manual Butterfly Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL23 |  | 131236-WIL23-DR-M | GA Drawing - WIL23 Motorised Butterfly Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL23 |  | 131236-WIL23-DR-M | GA Drawing - WIL23 Pneumatic Butterfly Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL00 |  | 131236-WIL00-DR-M | GA Drawing - WIL00 Dual Flap Check Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL00 |  | 131236-WIL00-DR-M | GA Drawing - WIL00 Manual Butterfly Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL00 |  | 131236-WIL00-DR-M | GA Drawing - WIL00 Motorised Butterfly Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL06 |  | 131236-WIL06-DR-M | GA Drawing - WIL06 Plastic Ball Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL06 |  | 131236-WIL06-DR-M | GA Drawing - WIL06 Plastic Ball Check Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL06 |  | 131236-WIL06-DR-M | GA Drawing - WIL06 Plastic Back Pressure Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WIL06 |  | 131236-WIL06-DR-M | GA Drawing - WIL06 Plastic Pressure Relief Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Mech | Stage 2 | DR | Hopper | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - ILM2 Screening and Grit Hopper 1 of 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Mech | Stage 2 | DR | Hopper | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - ILM2 Screening and Grit Hopper 2 of 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Mech | Stage 2 | DR | Hopper | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - ILM2 Screening and Grit Hopper 3 of 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Mech | Stage 2 | DR | Hopper | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - ILM2 Screening and Grit Hopper 4 of 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Mech | Stage 2 | DR | Hopper | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - Hopper Baseplate And Details | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Mech | Stage 2 | DR | Grit Tank Launder, Scum Cover Plate, Picket Fence And Removable Panel | WIL21 |  | 131236-WIL21-DR-M | DOMESTIC LM2 HEADWORKS GRIT TANK LAUNDER AND PICKET FENCE PLAN VIEW | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Mech | Stage 2 | DR | Grit Tank Launder, Scum Cover Plate, Picket Fence And Removable Panel | WIL21 |  | 131236-WIL21-DR-M | DOMESTIC LM2 HEADWORKS GRIT TANK LAUNDER AND PICKET FENCE SECTION VIEW SHEET 1 OF 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Mech | Stage 2 | DR | Grit Tank Launder, Scum Cover Plate, Picket Fence And Removable Panel | WIL21 |  | 131236-WIL21-DR-M | DOMESTIC LM2 HEADWORKS GRIT TANK LAUNDER AND PICKET FENCE SECTION VIEW SHEET 2 OF 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Mech | Stage 2 | DR | Grit Tank Launder, Scum Cover Plate, Picket Fence And Removable Panel | WIL21 |  | 131236-WIL21-DR-M | DOMESTIC LM2 HEADWORKS GRIT TANK LAUNDER DETAILS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Mech | Stage 2 | DR | Grit Tank Launder, Scum Cover Plate, Picket Fence And Removable Panel | WIL21 |  | 131236-WIL21-DR-M | DOMESTIC LM2 HEADWORKS GRIT TANK LAUNDER PLAN AND SECTION SHEET 1 OF 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Mech | Stage 2 | DR | Grit Tank Launder, Scum Cover Plate, Picket Fence And Removable Panel | WIL21 |  | 131236-WIL21-DR-M | DOMESTIC LM2 HEADWORKS GRIT TANK LAUNDER DETAILS SHEET 2 OF 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 2 | DR | Baffle Plate | WIL23 |  | 131236-WIL23-DR-M | ILM2 MBR TANK INLET BAFFLE WALL DETAIL DESIGN | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 2 | DR | Removable Panel | WIL21 |  | 131236-WIL21-DR-M | GRIT TANK INLET AND OUTLET REMOVABLE PANEL PLAN | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 2 | DR | Removable Panel | WIL21 |  | 131236-WIL21-DR-M | GRIT TANK INLET AND OUTLET REMOVABLE PANEL SECTION | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 2 | DR | Removable Panel | WIL21 |  | 131236-WIL21-DR-M | DOMESTIC LM2 HEADWORKS GRIT TANK OUTLET REMOVABLE PANEL | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 2 | DR | Removable Panel | WIL21 |  | 131236-WIL21-DR-M | DOMESTIC LM2 HEADWORKS GRIT TANK INLET REMOVABLE PANEL | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 2 | DR | Valve | WNS03 |  | 131236-WNS03-DR-M | GA Drawing - ILM00 Safety Relief Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 2 | DR | Spray Nozzle | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - WIL21 Spray Nozzle | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 2 | DR | Spray Nozzle | WIL22 |  | 131236-WIL22-DR-M | GA Drawing - WIL22 Spray Nozzle | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 2 | DR | Spray Nozzle | WIL23 |  | 131236-WIL23-DR-M | GA Drawing - WIL23 Spray Nozzle | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 2 | DR | Conveyor | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - ILM2 Submerged Grit Screw Conveyor | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 2 | DR | Conveyor | WIL21 |  | 131236-WIL21-DR-M | GA Drawing - ILM2 Grit Loadout Conveyor | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DR | Penstock | WIL23 |  | 131236-WIL23-DR-M | GA Drawing - ILM2 Membrane Scum Wet Well Penstock | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 2 | DR | Penstock | WIL23 |  | 131236-WIL23-DR-M | GA Drawing - ILM2 MBR Fine Screens Common Outlet Penstock | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DR | PST Lamella/Scraper/Scum Collector | WIL22 |  | 131236-WIL22-DR-M | Domestic LM2 Secondary Treatment - Surface Scum Scapper For PST 1, 2, and 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DR | PST Lamella/Scraper/Scum Collector | WIL22 |  | 131236-WIL22-DR-M | Domestic LM2 Secondary Treatment Rotating Bottom Scaper | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DR | PST Lamella/Scraper/Scum Collector | WIL22 |  | 131236-WIL22-DR-M | Domestic LM2 Secondary Treatment - Scum Beach With Trough, 1 pcsFor PST 1, 2, and 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DR | PST Lamella/Scraper/Scum Collector | WIL22 |  | 131236-WIL22-DR-M | Domestic LM2 Secondary Treatment - Details Scum Beach With Trough, 1 pcs Z6900 For PST 1, 2, and 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DR | Staging Tank | WIL22 |  | 131236-WIL22-DR-M | GA Drawing - Staging Tank Plan View | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DR | Staging Tank | WIL22 |  | 131236-WIL22-DR-M | GA Drawing - Staging Tank Section Views | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DR | Staging Tank | WIL22 |  | 131236-WIL22-DR-M | GA Drawing - Staging Tank Support Brackets & Mounting Layout Section Views | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DR | Staging Tank | WIL22 |  | 131236-WIL22-DR-M | Detailed Drawing - Staging Tank Rack Support Brackets | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 2 | DR | Staging Tank | WIL22 |  | 131236-WIL22-DR-M | Detailed Drawing - Staging Tank Rack Locator Frame & Support Angle | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 2 | DR | Spray Nozzle | WIL22 |  | 131236-WIL22-DR-M | WDL23 MBR COMMON CHANNEL AND MBR SCUM WET WELL SPRAYING SYSTEM OVERALL PLAN VIEW | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 2 | DR | Spray Nozzle | WIL22 |  | 131236-WIL22-DR-M | WDL23 MBR COMMON CHANNEL 1,2,3 ENLARGED PLAN VIEW (TYPICAL) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 2 | DR | Spray Nozzle | WIL22 |  | 131236-WIL22-DR-M | WDL23 MBR COMMON CHANNEL 1,2,3 SECTION VIEW (TYPICAL) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 2 | DR | Spray Nozzle | WIL22 |  | 131236-WIL22-DR-M | WDL23 MBR SCUM WET WELL 1,2,3 ENLARGED PLAN VIEW (TYPICAL) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 2 | DR | Intake Chamber | WIL22 |  | 131236-WIL22-DR-M | WDL23 MBR SCUM WET WELL 1,2,3 SECTION VIEW (TYPICAL) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Mech | Stage 3 | QA | Static Mixer | WIL23 |  | 131236-WIL23-QA-M | ITP - Static Mixer | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Mech | Stage 3 | QA | Static Mixer | WIL23 |  | 131236-WIL23-QA-M | FAT Procedure- Static Mixer | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Mech | Stage 3 | QA | Surge Vessel | WNS03 |  | 131236-WNS03-QA-M | ITP - Surge Vessel Including Instrument and Structure Support | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 3 | QA | Lifting Equipment | WSW46 |  | 131236-WSW46-QA-M | ITP & FAT Procedure- Lifting Equipment(EOTC, Monorail, Travelling Jib Crane and Davit Cranes) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 3 | QA | Intermediate Screen, Dewatering Press | WIL21 |  | 131236-WIL21-QA-M | ITP - Intermediate Screen And Its Associated Dewatering Press | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 3 | QA | Grit Classifier | WIL21 |  | 131236-WIL21-QA-M | ITP - Grit Classifier | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 3 | QA | Grit Classifier | WIL21 |  | 131236-WIL21-QA-M | FAT Procedure - Grit Classifier | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 3 | QA | Conveyor | WIL21 |  | 131236-WIL21-QA-M | Inspection & Test Plan and Factory Acceptance Test Procedure for Headworks Conveyor System (Screenings Conveyor, Grit Conveyor, Slide Gate, Diverter Chute) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 3 | QA | Fine Screen | WSW46 |  | 131236-WSW46-QA-M | ITP & FAT Procedure for Fine Screen (WDL21), MBR Fine Screen (WDL23), Including Associated Dewatering Press And Launder | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 3 | QA | Slide Gate | WIL21 |  | 131236-WIL21-QA-M | ITP & FAT Procedure- Slide Gates (for Screenings and Grits Hoppers) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Mech | Stage 3 | QA | Scum and Grease Removal Equipment | WIL21 |  | 131236-WIL21-QA-M | ITP - Grit Tank Grease And Scum Removal Equipment | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 3 | QA | PST Lamella/Scraper/Scum Collector | WIL22 |  | 131236-WIL22-QA-M | ITP & FAT Procedure - Lamella Settlement, Lamella support structure, PST Sludge Scraper and PST Scum Skimming and Removal System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Mech | Stage 3 | QA | Auto Lubrication System | WSW46 |  | 131236-WSW46-QA-M | ITP - Auto Lubrication System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 3 | QA | Tank Cover | WSW46 |  | 131236-WSW46-QA-M | ITP & FAT Procedure - Odour Containment Covers for Grit Tank and PST Tank | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 3 | QA | Safety Shower | WSW46 |  | 131236-WSW46-QA-M | ITP - Safety Shower and Eyewash | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Mech | Stage 3 | QA | Valve | WSW46 |  | 131236-WSW46-QA-M | ITP and FAT Procedure - FRP Dampers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Mech | Stage 3 | QA | Valve | WSW46 |  | 131236-WSW46-QA-M | ITP - Air Release (Combination) Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Mech | Stage 3 | QA | Valve | WSW46 |  | 131236-WSW46-QA-M | ITP - Metal Ball Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Mech | Stage 3 | QA | Valve | WSW46 |  | 131236-WSW46-QA-M | ITP - Non-Return Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Mech | Stage 3 | QA | Valve | WSW46 |  | 131236-WSW46-QA-M | FAT Procedure - Non-Return Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Mech | Stage 3 | QA | Valve | WSW46 |  | 131236-WSW46-QA-M | ITP - Butterfly Valves And Actuators | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Mech | Stage 3 | QA | Valve | WSW46 |  | 131236-WSW46-QA-M | FAT Procedure - Butterfly Valves And Actuators | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Mech | Stage 3 | QA | Valve | WSW46 |  | 131236-WSW46-QA-M | ITP - Knife Gate Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Mech | Stage 3 | QA | Valve | WSW46 |  | 131236-WSW46-QA-M | ITP - Pressure Reducing Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Mech | Stage 3 | QA | Valve | WSW46 |  | 131236-WSW46-QA-M | ITP - Pressure Sustaining Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Mech | Stage 3 | QA | Valve | WIL06 |  | 131236-WIL06-QA-M | ITP - Plastic Ball Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Mech | Stage 3 | QA | Valve | WIL06 |  | 131236-WIL06-QA-M | ITP - Plastic Ball Check Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Mech | Stage 3 | QA | Valve | WIL06 |  | 131236-WIL06-QA-M | ITP - Plastic Back Pressure Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Mech | Stage 3 | QA | Valve | WIL06 |  | 131236-WIL06-QA-M | ITP - Plastic Pressure Relief Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 3 | QA | Hopper | WIL21 |  | 131236-WIL21-QA-M | ITP - Screenings and Grits Hoppers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 3 | QA | Hopper | WIL21 |  | 131236-WIL21-QA-M | Welding Procedure Specification (WPS) For Screen And Grit Hopper | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 3 | QA | Hopper | WIL21 |  | 131236-WIL21-QA-M | Welder Qualification For Screen And Grit Hopper | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-01-01 | Mech | Stage 3 | QA | Hopper | WIL21 |  | 131236-WIL21-QA-M | NDT For Screen And Grit Hopper | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-01-01 | Mech | Stage 3 | QA | Hopper | WIL21 |  | 131236-WIL21-QA-M | Factory Acceptance Test Procedure For Screening And Grit Hoppers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Mech | Stage 3 | QA | Grit Tank Launder, Scum Cover Plate, Picket Fence And Removable Panel | WIL21 |  | 131236-WIL21-QA-M | ITP - Grit Tank Launder, Scum Cover Plate, Picket Fence And Removable Panel | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Mech | Stage 3 | QA | Grit Tank Launder, Scum Cover Plate, Picket Fence And Removable Panel | WIL21 |  | 131236-WIL21-QA-M | FAT Procedure for Grit Tank Launder | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Mech | Stage 3 | QA | Baffle Plate | WIL23 |  | 131236-WIL23-QA-M | ITP - Stainless Steel (SS316L) Plates | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Mech | Stage 3 | QA | Removable Panel | WIL21 |  | 131236-WIL21-QA-M | ITP - SS Grit Tank Inlet and Outlet Removable Panel | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Mech | Stage 3 | QA | Valve | WNS03 |  | 131236-WNS03-QA-M | ITP - Safety Relief Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 3 | QA | Spray Nozzle | WSW46 |  | 131236-WSW46-QA-M | ITP - Spray Nozzle | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 3 | QA | Penstock | WIL23 |  | 131236-WIL23-QA-M | ITP & FAT Procedure - Penstock | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Mech | Stage 3 | QA | Valve | WIL21 |  | 131236-WIL21-QA-M | ITP & FAT Procedure for WDL21 Flow Control Eccentric Butterfly Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Mech | Stage 3 | RT | Static Mixer | WIL23 |  | 131236-WIL23-RT-M | FAT Report- Citric Acid Static Mixer | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Mech | Stage 3 | RT | Static Mixer | WIL23 |  | 131236-WIL23-RT-M | FAT Report- Sodium Hypochlorite Static Mixer | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 3 | RT | Surge Vessel | WNS03 |  | 131236-WNS03-RT-M | FAT Report Surge Vessel Including Instrument and Structure Support | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | Mech | Stage 3 | RT | Lifting Equipment | WSW46 |  | 131236-WSW46-RT-M | FAT Report- Lifting Equipment(EOTC, Monorail, Travelling Jib Crane and Davit Cranes) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | Mech | Stage 3 | RT | Grit Classifier | WIL21 |  | 131236-WIL21-RT-M | FAT Report - Grit Classifier | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Mech | Stage 3 | RT | Conveyor | WIL21 |  | 131236-WIL21-RT-M | FAT Report - Headworks Conveyor System (Screenings Conveyor, Grit Conveyor, Slide Gate, Diverter Chute) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | Mech | Stage 3 | RT | Fine Screen | WSW46 |  | 131236-WSW46-RT-M | FAT Report for Fine Screen (WDL21), MBR Fine Screen (WDL23), Including Associated Dewatering Press And Launder | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 3 | RT | Slide Gate | WIL21 |  | 131236-WIL21-RT-M | FAT Report- Slide Gates (for Screenings and Grits Hoppers) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Mech | Stage 3 | RT | PST Lamella/Scraper/Scum Collector | WIL22 |  | 131236-WIL22-RT-M | FAT Report - Lamella Settlement, Lamella support structure, PST Sludge Scraper and PST Scum Skimming and Removal System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Mech | Stage 3 | RT | Tank Cover | WSW46 |  | 131236-WSW46-RT-M | FAT Report - Odour Containment Covers for Grit Tank and PST Tank | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-10-01 | Mech | Stage 3 | RT | Valve | WSW46 |  | 131236-WSW46-RT-M | FAT Report for Dual Plate Check Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-10-01 | Mech | Stage 3 | RT | Valve | WSW46 |  | 131236-WSW46-RT-M | FAT Report for Swing Check Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-10-01 | Mech | Stage 3 | RT | Valve | WSW46 |  | 131236-WSW46-RT-M | FAT Report for Lift Check Valve | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-10-01 | Mech | Stage 3 | RT | Valve | WSW46 |  | 131236-WSW46-RT-M | FAT Report for Swing Check Valve with Counterweight | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-10-01 | Mech | Stage 3 | RT | Valve | WSW46 |  | 131236-WSW46-RT-M | FAT Report - FRP Dampers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-10-01 | Mech | Stage 3 | RT | Valve | WSW46 |  | 131236-WSW46-RT-M | FAT Report - Non-Return Valves | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-10-01 | Mech | Stage 3 | RT | Valve | WSW46 |  | 131236-WSW46-RT-M | FAT Report - Butterfly Valves And Actuators | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 3 | RT | Hopper | WIL21 |  | 131236-WIL21-RT-M | FAT Report- Screening And Grit Hoppers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Mech | Stage 3 | RT | Grit Tank Launder, Scum Cover Plate, Picket Fence And Removable Panel | WIL21 |  | 131236-WIL21-RT-M | FAT Report for Grit Tank Launder | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Mech | Stage 3 | RT | Penstock | WIL23 |  | 131236-WIL23-RT-M | FAT Report - Penstock | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 3 | RT |  | WIL21 |  | 131236-WIL21-RT-M | DFS For WIL21 Pipe Racks | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 3 | RT |  | WIL21 |  | 131236-WIL21-RT-M | DFS For WIL21 Platform | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 3 | RT |  | WIL22 |  | 131236-WIL22-RT-M | DFS For WIL22 Lamella Support and Platform | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Mech | Stage 3 | RT |  | WIL23 |  | 131236-WIL23-RT-M | DFS for WIL23 Pipe Rack | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Piping | Stage 1 | VI |  | WIL00 | NO | 131236-WIL00-VI-M-0002 | Vendor Information For Stainless Steel Pipes and Fittigngs | [8 empty] | RTR - Returned for Resubmission | AWC - Approved with Comments |  |  |  | 0 | 1
Planned | 2026-11-01 | Piping | Stage 1 | VI |  | WSW46 | NO | 131236-WSW46-VI-PI-0002 | Vendor Information For CS lined PL Pipes and Fittigngs | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Piping | Stage 1 | VI |  | WSW46 | NO | 131236-WSW46-VI-PI-0003 | Vendor Information For cPVC Pipes and Fittigngs | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Piping | Stage 1 | VI |  | WSW46 | NO | 131236-WSW46-VI-PI-0004 | Vendor Information For HDPE Pipes and Fittigngs | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Piping | Stage 1 | VI |  | WSW46 | NO | 131236-WSW46-VI-PI-0005 | Vendor Information For Flange Coupling | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Piping | Stage 1 | VI |  | WSW46 | NO | 131236-WSW46-VI-PI-0006 | Vendor Information For Hose Reel | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Piping | Stage 2 | SP |  | WSW46 | NO | 131236-WSW46-SP-PI-0001 | Piping Meterial Specification | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Piping | Stage 2 | SP |  | WSW46 | NO | 131236-WSW46-SP-PI-0002 | Standard Piping Support | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Piping | Stage 2 | SP |  | WSW46 | NO | 131236-WSW46-SP-PI-0003 | Piping Insulation Specification | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | Piping | Stage 2 | SP |  | WSW46 | NO | 131236-WSW46-SP-PI-0004 | Piping Identification and Labelling Specification | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Piping | Stage 2 | CL |  | WSW46 | NO | 131236-WSW46-CL-PI-0001 | SS16 Pipe Thickness Calculation PN10 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Piping | Stage 2 | CL |  | WSW46 | NO | 131236-WSW46-CL-PI-0002 | SS16 Pipe Thickness Calculation PN16 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Piping | Stage 2 | CL |  | WSW46 | NO | 131236-WSW46-CL-PI-0003 | CSPL Pipe Thickness Calculation | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Piping | Stage 2 | CL |  | WSW46 | NO | 131236-WSW46-CL-PI-0004 | SS16 Flange Thickness Calculation PN10 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-10-01 | Piping | Stage 2 | CL |  | WSW46 | NO | 131236-WSW46-CL-PI-0005 | SS16 Flange Thickness Calculation PN16 | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Piping | Stage 2 | CL |  | WSW46 | NO | 131236-WSW46-CL-PI-0006 | FRP Pipe Thickness Calculation | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Piping | Stage 2 | CL |  | WSW46 | NO | 131236-WSW46-CL-PI-0007 | CPVC Pipe & Fitting Catalogue | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Piping | Stage 4 | CL |  | WSW48 | NO | 131238-WSW48-CL-PI-0008 | HDPE Pipe & Fitting Catalogue | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Piping | Stage 3 | DR |  | WNS03 | NO | 131236-WNS03-DR-M-1001 | Surge Vessel Area-General Arrangement Equipment Layout At SHD +5.300M(Part-2) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Piping | Stage 3 | DR |  | WNS03 | NO | 131236-WNS03-DR-M-1002 | Surge Vessel Area-General Arrangement Equipment Layout At SHD +5.300M(Part-1) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Piping | Stage 3 | DR |  | WNS03 | NO | 131236-WNS03-DR-M-3001 | Surge Vessel Area- Equipment Layout Section-A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Piping | Stage 3 | DR |  | WNS03 | NO | 131236-WNS03-DR-M-3002 | Surge Vessel Area- Equipment Layout Section-B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Piping | Stage 3 | DR |  | WNS03 | NO | 131236-WNS03-DR-M-3003 | Surge Vessel Area- Equipment Layout Section-C | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL06 | NO | 131236-WIL06-DR-M-1001 | Chemical Area-General Arrangement Equipment Layout At SHD +5.300M(Part-1) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL06 | NO | 131236-WIL06-DR-M-1002 | Chemical Area-General Arrangement Equipment Layout At SHD +5.300M(Part-2) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL06 | NO | 131236-WIL06-DR-M-1003 | Chemical Area-General Arrangement Equipment Layout At SHD +5.300M(Part-3) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL06 | NO | 131236-WIL06-DR-M-3001 | Chemical Area- Equipment Layout Section-A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL06 | NO | 131236-WIL06-DR-M-3002 | Chemical Area- Equipment Layout Section-B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL06 | NO | 131236-WIL06-DR-M-3003 | Chemical Area- Equipment Layout Section-C | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Piping | Stage 3 | DR |  | WIL21 | NO | 131236-WIL21-DR-M-1001 | ILM2-Headworks General Arrangement Equipment Layout At SHD +5.300M(Part-1) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Piping | Stage 3 | DR |  | WIL21 | NO | 131236-WIL21-DR-M-1002 | ILM2-Headworks General Arrangement Equipment Layout At SHD +5.300M(Part-2) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Piping | Stage 3 | DR |  | WIL21 | NO | 131236-WIL21-DR-M-1003 | ILM2-Headworks General Arrangement Equipment Layout At SHD +8.200M | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Piping | Stage 3 | DR |  | WIL21 | NO | 131236-WIL21-DR-M-1004 | ILM2-Headworks General Arrangement Equipment Layout At SHD.+10.100M (Part-1) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Piping | Stage 3 | DR |  | WIL21 | NO | 131236-WIL21-DR-M-1005 | ILM2-Headworks General Arrangement Equipment Layout At SHD.+10.100M (Part-2) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Piping | Stage 3 | DR |  | WIL21 | NO | 131236-WIL21-DR-M-1006 | ILM2-Headworks General Arrangement Equipment Layout At SHD +12.225M(Part-1) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Piping | Stage 3 | DR |  | WIL21 | NO | 131236-WIL21-DR-M-1007 | ILM2-Headworks General Arrangement Equipment Layout At SHD +12.225M(Part-2) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-04-01 | Piping | Stage 3 | DR |  | WIL21 | NO | 131236-WIL21-DR-M-1008 | ILM2-Headworks General Arrangement Equipment Layout At SHD +15.825M(Part-1) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-04-01 | Piping | Stage 3 | DR |  | WIL21 | NO | 131236-WIL21-DR-M-1009 | ILM2-Headworks General Arrangement Equipment Layout At SHD +15.825M(Part-2) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Piping | Stage 3 | DR |  | WIL21 | NO | 131236-WIL21-DR-M-1010 | ILM2-Headworks General Arrangement Equipment Layout At SHD +21.800M(Part-1) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Piping | Stage 3 | DR |  | WIL21 | NO | 131236-WIL21-DR-M-1011 | ILM2-Headworks General Arrangement Equipment Layout At SHD +21.800M(Part-2) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Piping | Stage 3 | DR |  | WIL21 | NO | 131236-WIL21-DR-M-1012 | ILM2-Headworks General Arrangement Equipment Layout At SHD +27.200M(Part-1) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Piping | Stage 3 | DR |  | WIL21 | NO | 131236-WIL21-DR-M-1013 | ILM2-Headworks General Arrangement Equipment Layout At SHD +27.200M(Part-2) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | Piping | Stage 3 | DR |  | WIL21 | NO | 131236-WIL21-DR-M-1014 | ILM2-Headworks General Arrangement Equipment Layout At SHD +30.400M(Part-1) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | Piping | Stage 3 | DR |  | WIL21 | NO | 131236-WIL21-DR-M-1015 | ILM2-Headworks General Arrangement Equipment Layout At SHD +30.400M(Part-2) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Piping | Stage 3 | DR |  | WIL21 | NO | 131236-WIL21-DR-M-3001 | ILM2-Headworks Equipment Layout Section-A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Piping | Stage 3 | DR |  | WIL21 | NO | 131236-WIL21-DR-M-3002 | ILM2-Headworks Equipment Layout Section-B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Piping | Stage 3 | DR |  | WIL21 | NO | 131236-WIL21-DR-M-3003 | ILM2-Headworks Equipment Layout Section-C | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Piping | Stage 3 | DR |  | WIL21 | NO | 131236-WIL21-DR-M-3004 | ILM2-Headworks Equipment Layout Section-D | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Piping | Stage 3 | DR |  | WIL21 | NO | 131236-WIL21-DR-M-3005 | ILM2-Headworks Equipment Layout Section-E | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Piping | Stage 3 | DR |  | WIL21 | NO | 131236-WIL21-DR-M-3006 | ILM2-Headworks Equipment Layout Section-F | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-04-01 | Piping | Stage 3 | DR |  | WIL21 | NO | 131236-WIL21-DR-M-3007 | ILM2-Headworks Equipment Layout Section-G | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-04-01 | Piping | Stage 3 | DR |  | WIL21 | NO | 131236-WIL21-DR-M-3008 | ILM2-Headworks Equipment Layout Section-H | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Piping | Stage 3 | DR |  | WIL21 | NO | 131236-WIL21-DR-M-3009 | ILM2-Headworks Equipment Layout Section-J | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Piping | Stage 3 | DR |  | WIL21 | NO | 131236-WIL21-DR-M-3010 | ILM2-Headworks Equipment Layout Section-K | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | Piping | Stage 3 | DR |  | WIL21 | NO | 131236-WIL21-DR-M-3011 | ILM2-Headworks Equipment Layout Section-L | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | Piping | Stage 3 | DR |  | WIL21 | NO | 131236-WIL21-DR-M-3012 | ILM2-Headworks Equipment Layout Section-M | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Piping | Stage 3 | DR |  | WIL22 | NO | 131236-WIL22-DR-M-1001 | ILM2-Primary Treatment General Arrangement Equipment Layout At SHD +5.300M(Part-1) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Piping | Stage 3 | DR |  | WIL22 | NO | 131236-WIL22-DR-M-1002 | ILM2-Primary Treatment General Arrangement Equipment Layout At SHD +5.300M(Part-2) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Piping | Stage 3 | DR |  | WIL22 | NO | 131236-WIL22-DR-M-1003 | ILM2-Primary Treatment General Arrangement Equipment Layout At SHD.+10.100M (Part-1) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Piping | Stage 3 | DR |  | WIL22 | NO | 131236-WIL22-DR-M-1004 | ILM2-Primary Treatment General Arrangement Equipment Layout At SHD.+10.100M (Part-2) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Piping | Stage 3 | DR |  | WIL22 | NO | 131236-WIL22-DR-M-1005 | ILM2-Primary Treatment General Arrangement Equipment Layout At SHD +12.225M(Part-1) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Piping | Stage 3 | DR |  | WIL22 | NO | 131236-WIL22-DR-M-1006 | ILM2-Primary Treatment General Arrangement Equipment Layout At SHD +12.225M(Part-2) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Piping | Stage 3 | DR |  | WIL22 | NO | 131236-WIL22-DR-M-1007 | ILM2-Primary Treatment General Arrangement Equipment Layout At SHD +15.825M(Part-1) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Piping | Stage 3 | DR |  | WIL22 | NO | 131236-WIL22-DR-M-1008 | ILM2-Primary Treatment General Arrangement Equipment Layout At SHD +15.825M(Part-2) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Piping | Stage 3 | DR |  | WIL22 | NO | 131236-WIL22-DR-M-1009 | ILM2-Primary Treatment General Arrangement Equipment Layout At SHD +21.800M(Part-1) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Piping | Stage 3 | DR |  | WIL22 | NO | 131236-WIL22-DR-M-1010 | ILM2-Primary Treatment General Arrangement Equipment Layout At SHD +21.800M(Part-2) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Piping | Stage 3 | DR |  | WIL22 | NO | 131236-WIL22-DR-M-1011 | ILM2-Primary Treatment General Arrangement Equipment Layout At SHD +27.200M(Part-1) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Piping | Stage 3 | DR |  | WIL22 | NO | 131236-WIL22-DR-M-1012 | ILM2-Primary Treatment General Arrangement Equipment Layout At SHD +27.200M(Part-2) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Piping | Stage 3 | DR |  | WIL22 | NO | 131236-WIL22-DR-M-1013 | ILM2-Primary Treatment General Arrangement Equipment Layout At SHD +30.400M(Part-1) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Piping | Stage 3 | DR |  | WIL22 | NO | 131236-WIL22-DR-M-1014 | ILM2-Primary Treatment General Arrangement Equipment Layout At SHD +30.400M(Part-2) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Piping | Stage 3 | DR |  | WIL22 | NO | 131236-WIL22-DR-M-3001 | ILM2-Primary Treatment Equipment Layout Section-A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Piping | Stage 3 | DR |  | WIL22 | NO | 131236-WIL22-DR-M-3002 | ILM2-Primary Treatment Equipment Layout Section-B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Piping | Stage 3 | DR |  | WIL22 | NO | 131236-WIL22-DR-M-3003 | ILM2-Primary Treatment Equipment Layout Section-C | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Piping | Stage 3 | DR |  | WIL22 | NO | 131236-WIL22-DR-M-3004 | ILM2-Primary Treatment Equipment Layout Section-D | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Piping | Stage 3 | DR |  | WIL22 | NO | 131236-WIL22-DR-M-3005 | ILM2-Primary Treatment Equipment Layout Section-E | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Piping | Stage 3 | DR |  | WIL22 | NO | 131236-WIL22-DR-M-3006 | ILM2-Primary Treatment Equipment Layout Section-F | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Piping | Stage 3 | DR |  | WIL22 | NO | 131236-WIL22-DR-M-3007 | ILM2-Primary Treatment Equipment Layout Section-G | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Piping | Stage 3 | DR |  | WIL22 | NO | 131236-WIL22-DR-M-3008 | ILM2-Primary Treatment Equipment Layout Section-H | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Piping | Stage 3 | DR |  | WIL22 | NO | 131236-WIL22-DR-M-3009 | ILM2-Primary Treatment Equipment Layout Section-J | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Piping | Stage 3 | DR |  | WIL22 | NO | 131236-WIL22-DR-M-3010 | ILM2-Primary Treatment Equipment Layout Section-K | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1001 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +3.700M(Part-1) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1002 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +3.700M(Part-2) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1003 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +3.700M(Part-3) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1004 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +5.300M(Part-1) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1005 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +5.300M(Part-2) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1006 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +5.300M(Part-3) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1007 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +8.000M(Part-1) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1008 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +8.000M(Part-2) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-06-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1009 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +8.000M(Part-3) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1010 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +13.000M(Part-1) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1011 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +13.000M(Part-2) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1012 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +13.000M(Part-3) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1013 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +15.100M(Part-1) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1014 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +15.100M(Part-2) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1015 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +15.100M(Part-3) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1016 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +17.000M(Part-1) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1017 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +17.000M(Part-2) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1018 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +17.000M(Part-3) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1019 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +23.100M(Part-1) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1020 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +23.100M(Part-2) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1021 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +23.100M(Part-3) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1022 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +33.900M(Part-1) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1023 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +33.900M(Part-2) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1024 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +33.900M(Part-3) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1025 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +35.700M(Part-1) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1026 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +35.700M(Part-2) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1027 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +35.700M(Part-3) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1028 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +36.900M(Part-1) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1029 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +36.900M(Part-2) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1030 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +36.900M(Part-3) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1031 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +38.300M(Part-1) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1032 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +38.300M(Part-2) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-1033 | ILM2-Secondary Treatment General Arrangement Equipment Layout At SHD +38.300M(Part-3) | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-3001 | ILM2-Secondary Treatment Equipment Layout Section-A | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-3002 | ILM2-Secondary Treatment Equipment Layout Section-B | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-05-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-3003 | ILM2-Secondary Treatment Equipment Layout Section-C | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-3004 | ILM2-Secondary Treatment Equipment Layout Section-D | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-3005 | ILM2-Secondary Treatment Equipment Layout Section-E | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-3006 | ILM2-Secondary Treatment Equipment Layout Section-F | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-3007 | ILM2-Secondary Treatment Equipment Layout Section-G | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-3008 | ILM2-Secondary Treatment Equipment Layout Section-H | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-3009 | ILM2-Secondary Treatment Equipment Layout Section-J | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-3010 | ILM2-Secondary Treatment Equipment Layout Section-K | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-3011 | ILM2-Secondary Treatment Equipment Layout Section-L | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-3012 | ILM2-Secondary Treatment Equipment Layout Section-M | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-3013 | ILM2-Secondary Treatment Equipment Layout Section-N | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-3014 | ILM2-Secondary Treatment Equipment Layout Section-P | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-3015 | ILM2-Secondary Treatment Equipment Layout Section-Q | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-3016 | ILM2-Secondary Treatment Equipment Layout Section-R | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-3017 | ILM2-Secondary Treatment Equipment Layout Section-S | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-3018 | ILM2-Secondary Treatment Equipment Layout Section-T | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-3019 | ILM2-Secondary Treatment Equipment Layout Section-U | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-07-01 | Piping | Stage 3 | DR |  | WIL23 | NO | 131236-WIL23-DR-M-3020 | ILM2-Secondary Treatment Equipment Layout Section-V | [8 empty] | Unassigned | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-07-01 | Electrical | Stage 1 | VI |  | WSW46 | NO | 131236-WSW46-VI-E-0001 | Vendor Information For Electrical Power Transformer & Distribution Transformer (TECO ELECTRIC & MACHINERY PTE LTD) | [8 empty] | RTR - Returned for Resubmission | AWC - Approved with Comments |  |  |  | 0 | 1
Planned | 2026-07-01 | Electrical | Stage 1 | VI |  | WSW46 | NO | 131236-WSW46-VI-E-0002 | Vendor Information For Electrical High Voltage Switchgear Panel (SCHNEIDER ELECTRIC PTE LTD) | [8 empty] | RTR - Returned for Resubmission | AWC - Approved with Comments |  |  |  | 0 | 1
Planned | 2026-07-01 | Electrical | Stage 1 | VI |  | WSW46 | NO | 131236-WSW46-VI-E-0003 | Vendor Information For Low Voltage Electrical Equipment Works (SUNLIGHT ELECTRICAL PTE LTD) | [8 empty] | RTR - Returned for Resubmission | NAP - Not Approved |  |  |  | 0 | 1
Planned | 2026-08-01 | Electrical | Stage 1 | VI |  | WSW46 | NO | 131236-WSW46-VI-E-0004 | Vendor Information For Cable Raceway (TRI-STAR INDUSTRIES PTE LTD) | [8 empty] | RTR - Returned for Resubmission | AWC - Approved with Comments |  |  |  | 0 | 1
Planned | 2026-08-01 | Electrical | Stage 1 | VI |  | WSW46 | NO | 131236-WSW46-VI-E-0005 | Vendor Information For Electrical High Voltage DOL Panel (SCHNEIDER ELECTRIC PTE LTD) | [8 empty] | RTR - Returned for Resubmission | NAP - Not Approved |  |  |  | 0 | 1
Planned | 2026-08-01 | Electrical | Stage 1 | VI |  | WSW46 | NO | 131236-WSW46-VI-E-0006 | Vendor Information For Emergency Generator (VIBROPOWER PTE LTD) | [8 empty] | RTR - Returned for Resubmission | AWC - Approved with Comments |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 1 | VI |  |  | NO | 131236-VI-E | Vendor Approval - Electrical System Analysis Consultant & PE/LEW For The 22kV, 6.6kV And 415V Electrical System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 1 | VI |  |  | NO | 131236-VI-E | Vendor Approval - Earthing & Lightning Consultant | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 1 | VI |  |  | NO | 131236-VI-E | Vendor Approval - LPS & Earthing System Accessories | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 1 | VI |  |  | NO | 131236-VI-E | Vendor Approval - Continuous On-line hot spot temperature Monitoring and Alert System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 1 | VI |  |  | NO | 131236-VI-E | Vendor Approval - Low Voltage System Equipment - Standalone LV VFDs | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 1 | VI |  |  |  | 131236-VI-E | Vendor Approval - Low Voltage System Equipment - Standalone LV | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 1 | VI |  |  |  | 131236-VI-E | Vendor Approval - Electrical Works Sub-Contractor | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 1 | VI |  |  |  | 131236-VI-E | Vendor Approval - 22kV & 6.6kV Cable | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 1 | VI |  |  |  | 131236-VI-E | Vendor Approval - Low Voltage System Busways | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 1 | VI |  |  |  | 131236-VI-E | Vendor Approval - Earthing & Lightning Protection System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 1 | VI |  |  |  | 131236-VI-E | Vendor Approval - Electrical Cast in uPVC Pipe Vendor Approval | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 1 | VI |  |  |  | 131236-VI-E | Vendor Approval - 30V Battery Charger | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 1 | VI |  |  |  | 131236-VI-E | Vendor Approval - Low Voltage Cable Vendor Approval | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 1 | VI |  |  |  | 131236-VI-E | Vendor Approval - Low Voltage Cable Vendor Approval | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 1 | VI |  |  |  | 131236-VI-E | Vendor Approval - Supply Switch, S.S.O, And Isolator | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 1 | VI |  |  |  | 131236-VI-E | Vendor Approval - Supply Light Fittings | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 1 | VI |  |  |  | 131236-VI-E | Vendor Approval - Electrical Works Sub-Contractor | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 1 | VI |  | WIL23 |  | 131236-WIL23-VI-E | Vendor Information For Supply Of Busway System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 1 | VI |  |  |  | 131236-VI-E | Vendor Approval - Preliminary Design Submission For Supply Of High Voltage Cable | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 1 | VI |  |  |  | 131236-VI-E | Vendor Approval - Preliminary Design Submission for Supply of Raceways | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 1 | VI |  |  |  | 131236-VI-E | Vendor Approval - Preliminary Design Submission For Supply Of Pilot Cable | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 1 | VI |  |  |  | 131236-VI-E | Vendor Information for MCT | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 1 | VI |  |  |  | 131236-VI-E | Vendor Information for HV Cables | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 1 | VI |  |  |  | 131236-VI-E | Vendor Information for Cable Tester and Jointer | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 1 | VI |  |  |  | 131236-VI-E | Vendor Information for Rubber & Plastic | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 1 | VI |  |  |  | 131236-VI-E | Vendor Information for Electrical Cable Gland | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | CL |  |  |  | 131236-CL-E | VFD Heat Dissipation Calculation | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | CL |  |  |  | 131236-CL-E | LVSG Heat Dissipation Calculation | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | CL |  |  |  | 131236-CL-E | CT/PT sizing calculations for 22 kV GIS Switchgear (WIL00-HVSG-0002A & 2B) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | CL |  |  |  | 131236-CL-E | WIL00-HVSG-0002A & 2B Battery sizing calc | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | CL |  |  |  | 131236-CL-E | Cable Ladder / Cabble Tray Sizing Calculations - 22kV Main Incoming Cable | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | CL |  |  |  | 131236-CL-E | Cable Ladder / Cabble Tray Sizing Calculations -WIL06 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | CL |  |  |  | 131236-CL-E | Raceway Combined Support Structure Outside of WIL06 Switch Room | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | CL |  |  |  | 131236-CL-E | Lighting Lux Calculations -WIL21 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | CL |  |  |  | 131236-CL-E | Cable Ladder / Cabble Tray Sizing Calculations -WIL21 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | CL |  |  |  | 131236-CL-E | Lighting Lux Calculations-WIL21 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | CL |  |  |  | 131236-CL-E | Transfomer K factor | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | CL |  |  |  | 131236-CL-E | Cable Ladder / Cabble Tray Sizing Calculations -WIL22 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | CL |  |  |  | 131236-CL-E | Lighting Lux Calculations-WIL22 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | CL |  |  |  | 131236-CL-E | Transfomer K factor | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | CL |  |  |  | 131236-CL-E | 01xx series Reserve for Standalone Motor Starters (Soft Starter) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | CL |  |  |  | 131236-CL-E | 22kV Vertical Cable Support Calculation | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | CL |  |  |  | 131236-CL-E | WIL23 EICA Combined Cable Support Structure at Membrane Tank Area GL1-16 Calculation | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Electrical | Stage 2 | CL |  |  |  | 131236-CL-E | WIL23 EICA Raceway Combined Cable Support Structure at GL A, 1-16 Calculation | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | CL |  |  |  | 131236-CL-E | WIL23-HVSG-0001A & B Battery sizing calc | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | CL |  |  |  | 131236-CL-E | Cable Ladder / Cabble Tray Sizing Calculations -WIL23 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | CL |  |  |  | 131236-CL-E | Lighting Lux Calculations-WIL23 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | CL |  |  |  | 131236-CL-E | Transfomer K factor | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | CL |  |  |  | 131236-CL-E | 01xx series Reserve for Standalone Motor Starters (VFDs) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | CL |  |  |  | 131236-CL-E | Calculation For Earth Conductor Sizing - ILM2 TWRP | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | 22kV HT Cable FAT Report | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | Transformers FAT Report | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | Battery Charger FAT Reports | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | HT Cable Sizing & Short Circuit Calculation | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | FAT Report For 22kV HV Cable (Route A) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | WIL06 Detailed Voltage Drop And Cable Sizing Schedule | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | WIL21 Detailed Voltage Drop And Cable Sizing Schedule | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | WIL21 ILM2 Power System Study (Load Flow) Report | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | ILM2 Power System Study (Short Circuit) Report | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | ILM2 Power System Study (Harmonic Analysis) Report | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | WIL21 Raceway FAT Report | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | ILM2 WIL21-LVSG-0001A&B FAT Report | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | FAT Report for WIL21 LV Cables | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | WIL21-MCC-0001A&1B FAT Report | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | FAT Report for ILM2 WIL21-MDB-0001A & 1B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | FAT Report for ILM2 WIL21-MCC-0002A & 2B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | WIL22 Detailed Voltage Drop And Cable Sizing Schedule | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | Cable Sizing And Voltage Drop Calculation Report | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | WIL22-LVSG-0001A & WIL22-LVSG-0001B FAT Report | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | WIL22-LVSG-0002A & WIL22-LVSG-0002B FAT Report | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | WIL22-MDB-0001A&B, WIL22-MDB-0002A&B, WIL22-MDB-0003A&B FAT Report | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | WIL23 Detailed Voltage Drop And Cable Sizing Schedule | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | WIL23 6.6kV DOL FAT Report | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | WIL23 NER FAT Report | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | WIL23 22kV HVSG FAT Report | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | WIL23 6.6kV HVSG FAT Report | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | WIL23-LVSG-0002A & WIL23-LVSG-0002B FAT Report | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | WIL23-LVSG-0003A & WIL23-LVSG-0003B FAT Report | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | 90kW, 280kW & 430kW LV VFD FAT Report | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | WIL23-LVSG-0001A & WIL23-LVSG-0001B FAT Report | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | Battery Charger FAT Reports | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | LV VFD FAT Report | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | LV VFD FAT Report (Batch 3) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | WIL23-TRF-0004B Transformer Oil Leakage Investigation Report | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | LV VFD FAT Report (Batch 4) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | LV VFD FAT Report (Batch 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | WIL23-MDB-0001A&B, WIL23-MDB-0002A&B, WIL23-MDB-0003A&B, WIL23-MDB-0004A&B FAT Report | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | ETAP Model | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | Cable Sizing And Voltage Drop Calculation Report (Detailed) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | Power System Study - Load Flow Analysis (Detailed) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | Power System Study - Short-circuit Analysis (Detailed) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | Power System Study - Motor Starting Analysis (Detailed) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | ILM2 Power System Study (Protective Device Coordination Analysis) Report | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | RT |  |  |  | 131236-RT-E | Power System Study - Harmonic Analysis (Detailed) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | SH |  |  |  | 131236-SH-E | Electrical Equipment Schedule | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | SH |  |  |  | 131236-SH-E | C3B2 Load List | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: 22kV Switchgear - WIL00-HVSG-0002A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: 22kV Switchgear - WIL00-HVSG-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MCC - WIL06-MCC-0002A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MCC - WIL06-MCC-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment LCS - WIL06-LCS-0001 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MCC - WIL13-MCC-0006 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MCC - WIL13-MCC-0007 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MCC - WIL21-MCC-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MCC - WIL21-MCC-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MCC - WIL21-MCC-0002A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MCC - WIL21-MCC-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MCC - WIL21-MCC-0003A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MCC - WIL21-MCC-0003B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MDB - WIL21-MDB-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MDB - WIL21-MDB-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment LCS - WIL21-LCS-0001 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: 22/0.415kV Transformer - WIL21-TRF-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: 22/0.415kV Transformer - WIL21-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment LVSG - WIL22-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment LVSG - WIL22-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment LVSG - WIL22-LVSG-0002A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment LVSG - WIL22-LVSG-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MCC - WIL22-MCC-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MCC - WIL22-MCC-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MCC - WIL22-MCC-0002A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MCC - WIL22-MCC-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MCC - WIL22-MCC-0003A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MCC - WIL22-MCC-0003B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MDB - WIL22-MDB-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MDB - WIL22-MDB-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MDB - WIL22-MDB-0002A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MDB - WIL22-MDB-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MDB - WIL22-MDB-0003A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MDB - WIL22-MDB-0003B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment LCS - WIL22-LCS-0001 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: 250kW LV Soft Starter | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: 22/0.415kV Transformer - WIL22-TRF-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: 22/0.415kV Transformer - WIL22-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: 22/0.415kV Transformer - WIL22-TRF-0002A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: 22/0.415kV Transformer - WIL22-TRF-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: 6.6kV Switchgear - WIL23-HVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: 6.6kV Switchgear - WIL23-HVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment LVSG - WIL23-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment LVSG - WIL23-LVSG-0002A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment LVSG - WIL23-LVSG-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment LVSG - WIL23-LVSG-0003A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment LVSG - WIL23-LVSG-0003B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MCC - WIL23-MCC-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MCC - WIL23-MCC-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MCC - WIL23-MCC-0002A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MCC - WIL23-MCC-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MCC - WIL23-MCC-0003A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MCC - WIL23-MCC-0003B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MCC - WIL23-MCC-0004A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MCC - WIL23-MCC-0004B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MCC - WIL23-MCC-0005A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MCC - WIL23-MCC-0005B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MDB - WIL23-MDB-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MDB - WIL23-MDB-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MDB - WIL23-MDB-0002A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MDB - WIL23-MDB-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MDB - WIL23-MDB-0003A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MDB - WIL23-MDB-0003B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MDB - WIL23-MDB-0004A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment MDB - WIL23-MDB-0004B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: Low Voltage System Equipment LCS - WIL23-LCS-0001 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: 6.6kV DOL Starter | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: 400kW LV VFD | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: 225kW LV VFD | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: 160kW LV VFD | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: 75kW LV VFD | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: 22/6.6kV Transformer - WIL23-TRF-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: 22/6.6kV Transformer - WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: 22/0.415kV Transformer - WIL23-TRF-0002A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: 22/0.415kV Transformer - WIL23-TRF-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: 22/0.415kV Transformer - WIL23-TRF-0003A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: 22/0.415kV Transformer - WIL23-TRF-0003B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: 22/0.415kV Transformer - WIL23-TRF-0004A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DS |  |  |  | 131236-DS-E | Data Sheet: 22/0.415kV Transformer - WIL23-TRF-0004B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | SD |  |  |  | 131236-SD-E | Shop Drawings - High Voltage System Equipment - 22kV Switchgear Battery & Battery Chargers (1 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | SD |  |  |  | 131236-SD-E | Shop Drawings - High Voltage System Equipment - 22kV Switchgear Battery & Battery Chargers (2 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | SD |  |  |  | 131236-SD-E | Shop Drawings - High Voltage System Equipment - 22kV Switchgear Battery & Battery Chargers (3 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | SD |  |  |  | 131236-SD-E | Shop Drawings - High Voltage System Equipment - 22kV Switchgear Battery & Battery Chargers (4 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | SD |  |  |  | 131236-SD-E | Shop Drawings - High Voltage System Equipment - 22kV Switchgear Battery & Battery Chargers (5 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 22kV Switchgear - WIL00-HVSG-0002A (Sheet 1 of 12) - General Arrangement | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 22kV Switchgear - WIL00-HVSG-0002A (Sheet 2 of 12) - General Arrangement | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 22kV Switchgear - WIL00-HVSG-0002A (Sheet 3 of 12) - Constructional Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 22kV Switchgear - WIL00-HVSG-0002A (Sheet 4 of 12) - Constructional Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 22kV Switchgear - WIL00-HVSG-0002A (Sheet 5 of 12) - In Details (JZ03a) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 22kV Switchgear - WIL00-HVSG-0002A (Sheet 6 of 12) - In Details (JZ03) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 22kV Switchgear - WIL00-HVSG-0002A (Sheet 7 of 12) - In Details (JZ01) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 22kV Switchgear - WIL00-HVSG-0002A (Sheet 8 of 12) - In Details (JZ04) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 22kV Switchgear - WIL00-HVSG-0002A (Sheet 9 of 12) - In Details (JZ02) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 22kV Switchgear - WIL00-HVSG-0002A (Sheet 10 of 12) - In Details (JZ05) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 22kV Switchgear - WIL00-HVSG-0002A (Sheet 11 of 12) - Gas Compartment | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 22kV Switchgear - WIL00-HVSG-0002A (Sheet 12 of 12) - Gas Compartment | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 22kV Switchgear - WIL00-HVSG-0002B (Sheet 1 of 11) - General Arrangement | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 22kV Switchgear - WIL00-HVSG-0002B (Sheet 2 of 11) - General Arrangement | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 22kV Switchgear - WIL00-HVSG-0002B (Sheet 3 of 11) - Constructional Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 22kV Switchgear - WIL00-HVSG-0002B (Sheet 4 of 11) - Constructional Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 22kV Switchgear - WIL00-HVSG-0002B (Sheet 5 of 11) - In Details (JZ05) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 22kV Switchgear - WIL00-HVSG-0002B (Sheet 6 of 11) - In Details (JZ02) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 22kV Switchgear - WIL00-HVSG-0002B (Sheet 7 of 11) - In Details (JZ03) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 22kV Switchgear - WIL00-HVSG-0002B (Sheet 8 of 11) - In Details (JZ01) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 22kV Switchgear - WIL00-HVSG-0002B (Sheet 9 of 11) - In Details (JZ04) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 22kV Switchgear - WIL00-HVSG-0002B (Sheet 10 of 11) - In Details {JZ03a} | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 22kV Switchgear - WIL00-HVSG-0002B (Sheet 11 of 11) - Gas Compartment | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 22kV Switchgear - WIL00-HVSG-0002B (Sheet 11 of 11) - Gas Compartment | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Remote Control Panel WIL00-HVSG-0002A General Arrangement | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Remote Control Panel WIL00-HVSG-0002A Schematic | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Remote Control Panel WIL00-HVSG-0002A Termination List | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Remote Control Panel WIL00-HVSG-0002A Bill Of Materials | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Remote Control Panel WIL00-HVSG-0002B General Arrangement | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Remote Control Panel WIL00-HVSG-0002B Schematic | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Remote Control Panel WIL00-HVSG-0002B Termination List | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Remote Control Panel WIL00-HVSG-0002B Bill Of Materials | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002A GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002A Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002A General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002A General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002A General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002A General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002A General Arrangement - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002B GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002B Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002B General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002B General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002B General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002B General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0001B General Arrangement - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LCS - WIL06-LCS-0001 (Sheet 1 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0006 GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0006 Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0006 General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0006 General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0006 General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0006 General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0006 General Arrangement - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0006 General Arrangement - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0007 GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0007 Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0007 General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0007 General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0007 General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0007 General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0007 General Arrangement - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0007 General Arrangement - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LCS - WIL13-LCS-0001 (Sheet 1 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001A LEGEND | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001A TECHNICAL DATA | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001A GENERAL ARRANGEMENT - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001A GENERAL ARRANGEMENT - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001A GENERAL ARRANGEMENT - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001A GENERAL ARRANGEMENT - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Part List - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Part List - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Part List - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001B LEGEND | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001B TECHNICAL DATA | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001B GENERAL ARRANGEMENT - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001B GENERAL ARRANGEMENT - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001B GENERAL ARRANGEMENT - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001B GENERAL ARRANGEMENT - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Parts List - Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Parts List - Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Parts List - Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MCC - WIL21-MCC-0001A (Sheet 1 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MCC - WIL21-MCC-0001A (Sheet 2 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MCC - WIL21-MCC-0001A (Sheet 3 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MCC - WIL21-MCC-0001A (Sheet 4 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MCC - WIL21-MCC-0001A (Sheet 5 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MCC - WIL21-MCC-0001A (Sheet 5 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MCC - WIL21-MCC-0001A (Sheet 5 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MCC - WIL21-MCC-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MCC - WIL21-MCC-0001B (Sheet 1 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MCC - WIL21-MCC-0001B (Sheet 2 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MCC - WIL21-MCC-0001B (Sheet 3 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MCC - WIL21-MCC-0001B (Sheet 4 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MCC - WIL21-MCC-0001B (Sheet 5 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MCC - WIL21-MCC-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MCC - WIL21-MCC-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MCC - WIL21-MCC-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A General Arrangement - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A General Arrangement - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B General Arrangement - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B General Arrangement - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A General Arrangement - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A General Arrangement - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B General Arrangement - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B General Arrangement - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001A GA LEGEND | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001A TECHNICAL DATA | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001A GENERAL ARRANGEMENT - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001A GENERAL ARRANGEMENT - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001A GENERAL ARRANGEMENT - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001A GENERAL ARRANGEMENT - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MDB - WIL21-MDB-0001A (Sheet 4 of 9) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MDB - WIL21-MDB-0001A (Sheet 5 of 9) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MDB - WIL21-MDB-0001A (Sheet 6 of 9) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MDB - WIL21-MDB-0001A (Sheet 7 of 9) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MDB - WIL21-MDB-0001A (Sheet 8 of 9) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MDB - WIL21-MDB-0001A (Sheet 9 of 9) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001B GA LEGEND | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001B TECHNICAL DATA | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001B GENERAL ARRANGEMENT - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001B GENERAL ARRANGEMENT - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001B GENERAL ARRANGEMENT - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001B GENERAL ARRANGEMENT - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MDB - WIL21-MDB-0001B (Sheet 7 of 9) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MDB - WIL21-MDB-0001B (Sheet 8 of 9) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MDB - WIL21-MDB-0001B (Sheet 9 of 9) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LCS - WIL21-LCS-0001 (Sheet 1 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LCS - WIL21-LCS-0001 (Sheet 1 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LCS - WIL21-LCS-0001 (Sheet 1 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LCS - WIL21-LCS-0001 (Sheet 1 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LCS - WIL21-LCS-0001 (Sheet 1 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LCS - WIL21-LCS-0001 (Sheet 1 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LCS - WIL21-LCS-0001 (Sheet 1 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LCS - WIL21-LCS-0001 (Sheet 1 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LCS - WIL21-LCS-0001 (Sheet 1 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LCS - WIL21-LCS-0001 (Sheet 1 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LCS - WIL21-LCS-0001 (Sheet 1 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LCS - WIL21-LCS-0001 (Sheet 1 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LCS - WIL21-LCS-0001 (Sheet 1 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LCS - WIL21-LCS-0001 (Sheet 1 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | GA - Low Voltage System Equipment - 22/0.415kV Transformer (3MVA) - WIL21-TRF-0001A & WIL21-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | The transformer vendor GA into the layout: 22/0.415kV Transformer (3MVA) - WIL21-TRF-0001A & WIL21-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001A GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001A Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001A General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001A General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001A General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001A General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL22-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL22-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL22-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL22-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001B Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001B Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001B General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001B General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001B General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001B General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL22-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL22-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL22-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL22-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002A GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002A Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002A General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002A General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002A General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002A General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL22-LVSG-0002A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL22-LVSG-0002A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL22-LVSG-0002A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL22-LVSG-0002A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002B GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002B Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002B General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002B General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002B General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002B General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL22-LVSG-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL22-LVSG-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL22-LVSG-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001A GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001A Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001A General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001A General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001A General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001A General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001A General Arrangement - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001A General Arrangement - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001B GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001B Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001B General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001B General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001B General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001B General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001B General Arrangement - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001B General Arrangement - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002A GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002A Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002A General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002A General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002A General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002A General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002A General Arrangement - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002A General Arrangement - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002B GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002B Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002B General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002B General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002B General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002B General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002B General Arrangement - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002B General Arrangement - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003A GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003A Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003A General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003A General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003A General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003A General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003A General Arrangement - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003A General Arrangement - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003B GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003B Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003B General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003B General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003B General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003B General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003B General Arrangement - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003B General Arrangement - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001A GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001A Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001A General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001A General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001A General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001A General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001B GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001B Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001B General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001B General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001B General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001B General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002A GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002A Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002A General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002A General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002A General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002A General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002B GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002B Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002B General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002B General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002B General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002B General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003A GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003A Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003A General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003A General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003A General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003A General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003B GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003B Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003B General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003B General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003B General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003B General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA Low Voltage System Equipment - MDB WIL22-MDB-0003B (Sheet 3 of 8) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA Low Voltage System Equipment - MDB WIL22-MDB-0003B (Sheet 4 of 8) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA Low Voltage System Equipment - MDB WIL22-MDB-0003B (Sheet 5 of 8) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA Low Voltage System Equipment - MDB WIL22-MDB-0003A (Sheet 6 of 8) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA Low Voltage System Equipment - MDB WIL22-MDB-0003B (Sheet 7 of 8) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA Low Voltage System Equipment - MDB WIL22-MDB-0003B (Sheet 8 of 8) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LCS - WIL22-LCS-0001 (Sheet 1 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LCS - WIL22-LCS-0001 (Sheet 1 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LCS - WIL22-LCS-0001 (Sheet 1 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LCS - WIL22-LCS-0001 (Sheet 1 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LCS - WIL22-LCS-0001 (Sheet 1 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LCS - WIL22-LCS-0001 (Sheet 1 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LCS - WIL22-LCS-0001 (Sheet 1 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LCS - WIL22-LCS-0001 (Sheet 1 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LCS - WIL22-LCS-0001 (Sheet 1 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LCS - WIL22-LCS-0001 (Sheet 1 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LCS - WIL22-LCS-0001 (Sheet 1 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LCS - WIL22-LCS-0001 (Sheet 1 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LCS - WIL22-LCS-0001 (Sheet 1 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LCS - WIL22-LCS-0001 (Sheet 1 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 250kW LV SS (Sheet 01 of 04) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 250kW LV SS (Sheet 02 of 04) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 250kW LV SS (Sheet 03 of 04) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 250kW LV SS (Sheet 04 of 04) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | General Arrangement: 22/0.415kV Transformer (2MVA) - WIL22-TRF-0001A, WIL22-TRF-0001B, WIL22-TRF-0002A, WIL22-TRF-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | GA into the layout: 22/0.415kV Transformer (2MVA) - WIL22-TRF-0001A, WIL22-TRF-0001B, WIL22-TRF-0002A, WIL22-TRF-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Shop Drawings - High Voltage System Equipment - 6.6kV Switchgear Battery & Battery Chargers (1 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Shop Drawings - High Voltage System Equipment - 6.6kV Switchgear Battery & Battery Chargers (2 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Shop Drawings - High Voltage System Equipment - 6.6kV Switchgear Battery & Battery Chargers (3 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Shop Drawings - High Voltage System Equipment - 6.6kV Switchgear Battery & Battery Chargers (4 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Shop Drawings - High Voltage System Equipment - 6.6kV Switchgear Battery & Battery Chargers (5 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | 0 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 6.6kV Switchgear - WIL23-HVSG-0001A - Constructional Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 6.6kV Switchgear - WIL23-HVSG-0001A - In Detail (LZ02 = LZ03) - Circuit Breaker Panel 1000A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 6.6kV Switchgear - WIL23-HVSG-0001A - In Detail (LZ01 = LZ05) - Circuit Breaker Panel 1250A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 6.6kV Switchgear - WIL23-HVSG-0001B - General Arrangement | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 6.6kV Switchgear - WIL23-HVSG-0001B - Constructional Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 6.6kV Switchgear - WIL23-HVSG-0001B - In Detail (LZ01 = LZ05) - Circuit Breaker Panel 1250A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 6.6kV Switchgear - WIL23-HVSG-0001B - In Detail (LZ02 = LZ03) - Circuit Breaker Panel 1000A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 6.6kV DOL Starter - Membrane Air Blower 510kW - General Arrangement (Sheet 01 of 02) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 6.6kV DOL Starter - Membrane Air Blower 510kW - Foundation details (Sheet 02 of 02) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 6.6kV DOL Starter - Process Air Blower 1205kW- General Arrangement (Sheet 01 of 02) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 6.6kV DOL Starter - Process Air Blower 1205kW - Foundation details (Sheet 02 of 02) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001A GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001A Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001A General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001A General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001A General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001A General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Part List - Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Part List - Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Part List - Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001B GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001B Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001B General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001B General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001B General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001B General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002A GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002A Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002A General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002A General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002A General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002A General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Legend Symbol - Low Voltage System Equipment LVSG - WIL23-LVSG-0002A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Data Sheet - Low Voltage System Equipment LVSG - WIL23-LVSG-0002A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL23-LVSG-0002A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL23-LVSG-0002A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL23-LVSG-0002A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL23-LVSG-0002A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL23-LVSG-0002A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Part List - Low Voltage System Equipment LVSG - WIL23-LVSG-0002A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Part List - Low Voltage System Equipment LVSG - WIL23-LVSG-0002A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Part List - Low Voltage System Equipment LVSG - WIL23-LVSG-0002A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002B GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002B Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002B General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002B General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002B General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002B General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL23-LVSG-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Part List - Low Voltage System Equipment LVSG - WIL23-LVSG-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Part List - Low Voltage System Equipment LVSG - WIL23-LVSG-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Part List - Low Voltage System Equipment LVSG - WIL23-LVSG-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003A GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003A Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003A General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003A General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003A General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003A General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL23-LVSG-0003A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Part List - Low Voltage System Equipment LVSG - WIL23-LVSG-0003A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Part List - Low Voltage System Equipment LVSG - WIL23-LVSG-0003A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Part List - Low Voltage System Equipment LVSG - WIL23-LVSG-0003A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Legend Symbol - Low Voltage System Equipment LVSG - WIL23-LVSG-0003B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Data Sheet - Low Voltage System Equipment LVSG - WIL23-LVSG-0003B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL23-LVSG-0003B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL23-LVSG-0003B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL23-LVSG-0003B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL23-LVSG-0003B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LVSG - WIL23-LVSG-0003B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Part List - Low Voltage System Equipment LVSG - WIL23-LVSG-0003B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Part List - Low Voltage System Equipment LVSG - WIL23-LVSG-0003B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Part List - Low Voltage System Equipment LVSG - WIL23-LVSG-0003B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001A GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001A Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001A General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001A General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001A General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001A General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001A General Arrangement - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001A General Arrangement - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001B GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001B Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001B General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001B General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001B General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001B General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001B General Arrangement - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001B General Arrangement - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002A GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002A Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002A General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002A General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002A General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002A General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002A General Arrangement - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002A General Arrangement - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002B GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002B Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002B General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002B General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002B General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002B General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002B General Arrangement - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002B General Arrangement - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003A GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003A Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003A General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003A General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003A General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003A General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003A General Arrangement - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003A General Arrangement - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003B GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003B Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003B General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003B General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003B General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003B General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003B General Arrangement - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004A GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004A Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004A General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004A General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004A General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004A General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004A General Arrangement - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004B GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004B Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004B General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004B General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004B General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004B General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004B General Arrangement - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A General Arrangement - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A General Arrangement - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B General Arrangement - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B General Arrangement - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001A GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001A Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001A General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001A General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001A General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001A General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001B GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001B Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001B General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001B General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001B General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001B General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002A GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002A Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002A General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002A General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002A General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002A General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002B GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002B Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002B General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002B General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002B General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002B General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003A GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003A Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003A General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003A General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003A General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003A General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003B GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003B Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003B General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003B General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003B General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003B General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004A GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004A Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004A General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004A General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004A General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004A General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004B GA Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004B Technical Data | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004B General Arrangement - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004B General Arrangement - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004B General Arrangement - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004B General Arrangement - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MDB - WIL23-MDB-0003B (Sheet 01 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MDB - WIL23-MDB-0004A (Sheet 01 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MDB - WIL23-MDB-0004A (Sheet 01 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MDB - WIL23-MDB-0004A (Sheet 01 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MDB - WIL23-MDB-0004A (Sheet 01 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MDB - WIL23-MDB-0004A (Sheet 01 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MDB - WIL23-MDB-0004A (Sheet 01 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MDB - WIL23-MDB-0004A (Sheet 01 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MDB - WIL23-MDB-0004A (Sheet 01 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MDB - WIL23-MDB-0004B (Sheet 01 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MDB - WIL23-MDB-0004B (Sheet 01 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MDB - WIL23-MDB-0004B (Sheet 01 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MDB - WIL23-MDB-0004B (Sheet 01 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MDB - WIL23-MDB-0004B (Sheet 01 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MDB - WIL23-MDB-0004B (Sheet 01 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MDB - WIL23-MDB-0004B (Sheet 01 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment MDB - WIL23-MDB-0004B (Sheet 01 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - Low Voltage System Equipment LCS - WIL23-LCS-0001 (Sheet 01 of XXX) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 450kW LV VFD (Sheet 01 of 06) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 450kW LV VFD (Sheet 02 of 06) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 450kW LV VFD (Sheet 03 of 06) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 450kW LV VFD (Sheet 04 of 06) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 450kW LV VFD (Sheet 05 of 06) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 450kW LV VFD (Sheet 06 of 06) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 280kW LV VFD (Sheet 01 of 06) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 280kW LV VFD (Sheet 02 of 06) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 280kW LV VFD (Sheet 03 of 06) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 280kW LV VFD (Sheet 04 of 06) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 280kW LV VFD (Sheet 05 of 06) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 280kW LV VFD (Sheet 06 of 06) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 315kW LV VFD (Sheet 01 of 06) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 315kW LV VFD (Sheet 02 of 06) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 315kW LV VFD (Sheet 03 of 06) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 315kW LV VFD (Sheet 04 of 06) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 315kW LV VFD (Sheet 05 of 06) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 315kW LV VFD (Sheet 06 of 06) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 225kW LV VFD (Sheet 01 of 04) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 225kW LV VFD (Sheet 02 of 04) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 225kW LV VFD (Sheet 03 of 04) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 225kW LV VFD (Sheet 04 of 04) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 160kW LV VFD (Sheet 01 of 04) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 160kW LV VFD (Sheet 02 of 04) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 160kW LV VFD (Sheet 03 of 04) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 160kW LV VFD (Sheet 04 of 04) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 90kW LV VFD (Sheet 01 of 06) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 90kW LV VFD (Sheet 02 of 06) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 90kW LV VFD (Sheet 03 of 06) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 90kW LV VFD (Sheet 04 of 06) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 90kW LV VFD (Sheet 05 of 06) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 90kW LV VFD (Sheet 06 of 06) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 75kW LV VFD (Sheet 01 of 04) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 75kW LV VFD (Sheet 02 of 04) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 75kW LV VFD (Sheet 03 of 04) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel GA - 75kW LV VFD (Sheet 04 of 04) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | General Arrangement: 22/6.6kV Transformer (8/11MVA) - WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | General Arrangement: 22/0.415kV Transformer (2.5MVA) - WIL23-TRF-0002A & WIL23-TRF-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | General Arrangement: 22/0.415kV Transformer (2MVA) - WIL23-TRF-0003A & WIL23-TRF-0003B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | General Arrangement: 22/0.415kV Transformer (3MVA) - WIL23-TRF-0004A & WIL23-TRF-0004B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | The transformer vendor GA into the layout: 22/6.6kV Transformer (8/11MVA) - WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | The transformer vendor GA into the layout: 22/0.415kV Transformer (2.5MVA) - WIL23-TRF-0002A & WIL23-TRF-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | The transformer vendor GA into the layout: 22/0.415kV Transformer (2MVA) - WIL23-TRF-0003A & WIL23-TRF-0003B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | The transformer vendor GA into the layout: 22/0.415kV Transformer (3MVA) - WIL23-TRF-0004A & WIL23-TRF-0004B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Remote Control Panel WIL23-HVSG-0001A General Arrangement | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Remote Control Panel WIL23-HVSG-0001A Schematic | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Remote Control Panel WIL23-HVSG-0001A Termination List | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Remote Control Panel WIL23-HVSG-0001A Bill Of Materials | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Remote Control Panel WIL23-HVSG-0001B General Arrangement | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Remote Control Panel WIL23-HVSG-0001B Schematic | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Remote Control Panel WIL23-HVSG-0001B Termination List | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Remote Control Panel WIL23-HVSG-0001B Bill Of Materials | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Reserved for Overall Schematic | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Reserved for Overall Schematic | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Reserved for Overall Schematic | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Reserved for Overall Schematic | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Reserved for Overall Schematic | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Reserved for Overall Schematic | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Reserved for Overall Schematic | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Reserved for Overall Schematic | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Reserved for Overall Schematic | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Reserved for Overall Schematic | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Reserved for Overall Schematic | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Reserved for Overall Schematic | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Reserved for Overall Schematic | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Reserved for Overall Schematic | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Reserved for Overall Schematic | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Reserved for Overall Schematic | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Reserved for Overall Schematic | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | LCS Type 9A Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | LCS Type 9A Control Schematic Diagram | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | LCS Type 9B Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | LCS Type 9B Control Schematic Diagram | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel SLD - 22kV Switchgear - WIL00-HVSG-0002A (Sheet 1 of 4) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel SLD - 22kV Switchgear - WIL00-HVSG-0002A (Sheet 2 of 4) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel SLD - 22kV Switchgear - WIL00-HVSG-0002A (Sheet 3 of 4) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel SLD - 22kV Switchgear - WIL00-HVSG-0002A (Sheet 4 of 4) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel SLD - 22kV Switchgear - WIL00-HVSG-0002B (Sheet 1 of 4) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel SLD - 22kV Switchgear - WIL00-HVSG-0002B (Sheet 2 of 4) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel SLD - 22kV Switchgear - WIL00-HVSG-0002B (Sheet 3 of 4) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel SLD - 22kV Switchgear - WIL00-HVSG-0002B (Sheet 4 of 4) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002A SLD Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002A Single Line Diagram | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002A Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002B SLD Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002B Single Line Diagram | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002B Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0006 Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0006 Single Line Diagram | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0006 Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0007 Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0007 Single Line Diagram | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0007 Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001A LEGEND | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001A SINGLE LINE DIAGRAM – 1 (Sheet 1 of 2) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001A SINGLE LINE DIAGRAM – 1 (Sheet 2 of 2) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001A LEGEND | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001B LEGEND | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001B SINGLE LINE DIAGRAM – 1 (Sheet 1 of 2) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001B SINGLE LINE DIAGRAM – 1 (Sheet 2 of 2) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001B BILL OF MATERIALS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel SLD - Low Voltage System Equipment MCC - WIL21-MCC-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel SLD - Low Voltage System Equipment MCC - WIL21-MCC-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel SLD - Low Voltage System Equipment MCC - WIL21-MCC-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel SLD - Low Voltage System Equipment MCC - WIL21-MCC-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel SLD - Low Voltage System Equipment MCC - WIL21-MCC-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel SLD - Low Voltage System Equipment MCC - WIL21-MCC-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel SLD - Low Voltage System Equipment MCC - WIL21-MCC-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A Single Line Diagram - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A Single Line Diagram - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A Single Line Diagram - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A Bill of Material - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A Bill of Material - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A Bill of Material - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A Bill of Material - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A Bill of Material - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B Single Line Diagram - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B Single Line Diagram - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B Bill of Material - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B Bill of Material - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B Bill of Material - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B Bill of Material - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B Bill of Material - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A Single Line Diagram - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A Single Line Diagram - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A Bill of Material - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A Bill of Material - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A Bill of Material - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A Bill of Material - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A Bill of Material - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B Single Line Diagram - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B Bill of Material - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B Bill of Material - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B Bill of Material - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B Bill of Material - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001A SLD LEGEND | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001A SINGLE LINE DIAGRAM - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001A SINGLE LINE DIAGRAM - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001A SINGLE LINE DIAGRAM - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001A BILL OF MATERIAL | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001B SLDLEGEND | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001B SINGLE LINE DIAGRAM - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001B SINGLE LINE DIAGRAM - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001B SINGLE LINE DIAGRAM - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001B SINGLE LINE DIAGRAM - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001A Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001A Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001A Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001A Bill of Materials | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001B Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001B Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001B Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001B Bill of Materials | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002A Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002A Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002A Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002A Bill of Materials | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002B Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002B Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002B Bill of Materials | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001A Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001A Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001A Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001A Single Line Diagram - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001A Bill of Material - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001A Bill of Material - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001A Bill of Material - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001A Bill of Material - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001B Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001B Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001B Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001B Single Line Diagram - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001B Bill of Material - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001B Bill of Material - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001B Bill of Material - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001B Bill of Material - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002A Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002A Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002A Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002A Single Line Diagram - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002A Bill of Material - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002A Bill of Material - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002A Bill of Material - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002B Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002B Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002B Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002B Single Line Diagram - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002B Bill of Material - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002B Bill of Material - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002B Bill of Material - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003A Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003A Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003A Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003A Single Line Diagram - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003A Bill of Material - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003A Bill of Material - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003A Bill of Material - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003B Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003B Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003B Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003B Single Line Diagram - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003B Bill of Material - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003B Bill of Material - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003B Bill of Material - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001A SLD Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001A Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001A Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001A Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001B SLD Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001B Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001B Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001B Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002A SLD Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002A Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002A Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002B SLD Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002B Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002B Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003A SLD Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003A Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003A Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003B SLD Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003B Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003B Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel SLD - 6.6kV Switchgear - WIL23-HVSG-0001A (Sheet 1 of 3) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel SLD - 6.6kV Switchgear - WIL23-HVSG-0001A (Sheet 2 of 3) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel SLD - 6.6kV Switchgear - WIL23-HVSG-0001A (Sheet 3 of 3) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel SLD - 6.6kV Switchgear - WIL23-HVSG-0001B (Sheet 1 of 3) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel SLD - 6.6kV Switchgear - WIL23-HVSG-0001B (Sheet 2 of 3) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel SLD - 6.6kV Switchgear - WIL23-HVSG-0001B (Sheet 3 of 3) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001A SLD Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001A Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001A Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001A Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001A Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001B SLD Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001B Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001B Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001B Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001B Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002A SLD Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002A Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002A Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002A Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002A Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002B SLD Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002B Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002B Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002B Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002B Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003A SLD Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003A Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003A Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003A Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003A Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003B SLD Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003B Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003B Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003B Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003B Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001A Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001A Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001A Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001A Single Line Diagram - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001A Bill of Material - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001A Bill of Material - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001A Bill of Material - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001B Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001B Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001B Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001B Single Line Diagram - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001B Bill of Material - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001B Bill of Material - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001B Bill of Material - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002A Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002A Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002A Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002A Single Line Diagram - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002A Bill of Material - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002A Bill of Material - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002B Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002B Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002B Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002B Single Line Diagram - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002B Bill of Material - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002B Bill of Material - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003A Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003A Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003A Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003A Single Line Diagram - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003A Bill of Material - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003A Bill of Material - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003A Bill of Material - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003B Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003B Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003B Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003B Bill of Material - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003B Bill of Material - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003B Bill of Material - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004A Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004A Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004A Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004A Single Line Diagram - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004A Single Line Diagram - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004A Bill of Material - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004A Bill of Material - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004B Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004B Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004B Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004B Single Line Diagram - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004B Single Line Diagram - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004B Bill of Material - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004B Bill of Material - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A Single Line Diagram - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A Single Line Diagram - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A Single Line Diagram - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A Bill of Material - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B Single Line Diagram - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B Single Line Diagram - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B Single Line Diagram - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B Bill of Material - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B Bill of Material - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B Bill of Material - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001A SLD Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001A Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001A Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001A Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001B SLD Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001B Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001B Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001B Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002A SLD Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002A Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002A Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002A Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002B SLD Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002B Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002B Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002B Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003A SLD Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003A Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003A Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003A Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003B SLD Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003B Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003B Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003B Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004A SLD Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004A Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004A Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004A Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004B SLD Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004B Single Line Diagram - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004B Single Line Diagram - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004B Bill of Material | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics -22kV Switchgear Battery & Battery Chargers (1 of 6) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics -22kV Switchgear Battery & Battery Chargers (2 of 6) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics -22kV Switchgear Battery & Battery Chargers (3 of 6) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics -22kV Switchgear Battery & Battery Chargers (4 of 6) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics -22kV Switchgear Battery & Battery Chargers (5 of 6) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics -22kV Switchgear Battery & Battery Chargers (6 of 6) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A LV DOOR LAYOUT = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A LV LAYOUT = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A LV DOOR LAYOUT = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A LV LAYOUT = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A LV DOOR LAYOUT = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A LV LAYOUT = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A LV DOOR LAYOUT = JZ03a, JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A LV LAYOUT = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A LV LAYOUT = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A LV DOOR LAYOUT = JZ04, JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A LV LAYOUT = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A LV LAYOUT = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A LV LABEL | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A ATS/ MTS TRANSFER SCHEME & LOGIC DIAGRAM | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A ATS/ MTS TRANSFER SCHEME & LOGIC DIAGRAM | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A ATS/ MTS TRANSFER SCHEME & LOGIC DIAGRAM | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A ATS/ MTS TRANSFER SCHEME & LOGIC DIAGRAM | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A ATS/ MTS TRANSFER SCHEME & LOGIC DIAGRAM | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A POWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A POWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A POWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A POWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A POWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A POWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A POWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A POWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002A TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B LV DOOR LAYOUT = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B LV LAYOUT = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B LV DOOR LAYOUT = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B LV LAYOUT = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B LV DOOR LAYOUT = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B LV LAYOUT = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B LV DOOR LAYOUT = JZ03a, JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B LV LAYOUT = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B LV LAYOUT = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B LV DOOR LAYOUT = JZ04, JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B LV LAYOUT = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B LV LAYOUT = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B LV LABEL | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B ATS/ MTS TRANSFER SCHEME & LOGIC DIAGRAM | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B ATS/ MTS TRANSFER SCHEME & LOGIC DIAGRAM | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B ATS/ MTS TRANSFER SCHEME & LOGIC DIAGRAM | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B ATS/ MTS TRANSFER SCHEME & LOGIC DIAGRAM | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B ATS/ MTS TRANSFER SCHEME & LOGIC DIAGRAM | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B POWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B POWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B POWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B POWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B POWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B POWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B POWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B POWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B INCOMER SCHEMATIC DIAGRAM = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B OUTGOING FEEDER SCHEMATIC = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B BUS SECTION SCHEMATIC = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear WIL00-HVSG-0002B TERMINAL CONNECTION TABLE = JZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | LCS Type 9A General Arrangement | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | LCS Type 9B General Arrangement | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 22kV Switchgear - Battery & Battery Chargers (Sheet 1 of 12) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002A Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002A Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002A Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002A Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002A Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002A Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002A Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002A Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002A Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002B Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002B Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002B Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002B Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002B Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002B Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002B Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002B Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL06-MCC-0002B Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LCS - WIL06-LCS-00xx | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0006 Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0006 Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0006 Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0006 Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0006 Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0006 Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0006 Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0006 Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0006 Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0007 Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0007 Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0007 Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0007 Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0007 Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0007 Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0007 Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0007 Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL13-MCC-0007 Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LCS - WIL13-LCS-00xx | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers ( 3MVA) -WIL21-TRF-0001A & WIL21-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers ( 3MVA) -WIL21-TRF-0001A & WIL21-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers ( 3MVA) -WIL21-TRF-0001A & WIL21-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers ( 3MVA) -WIL21-TRF-0001A & WIL21-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers ( 3MVA) -WIL21-TRF-0001A & WIL21-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers ( 3MVA) -WIL21-TRF-0001A & WIL21-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers ( 3MVA) -WIL21-TRF-0001A & WIL21-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers ( 3MVA) -WIL21-TRF-0001A & WIL21-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers ( 3MVA) -WIL21-TRF-0001A & WIL21-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers ( 3MVA) -WIL21-TRF-0001A & WIL21-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers ( 3MVA) -WIL21-TRF-0001A & WIL21-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers ( 3MVA) -WIL21-TRF-0001A & WIL21-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers ( 3MVA) -WIL21-TRF-0001A & WIL21-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers ( 3MVA) -WIL21-TRF-0001A & WIL21-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001A CONTROL CIRCUIT (Sheet 1 of 11) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001A CONTROL CIRCUIT (Sheet 2 of 11) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001A CONTROL CIRCUIT (Sheet 3 of 11) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001A CONTROL CIRCUIT (Sheet 4 of 11) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001A CONTROL CIRCUIT (Sheet 5 of 11) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001A CONTROL CIRCUIT (Sheet 6 of 11) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001A CONTROL CIRCUIT (Sheet 7 of 11) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001A CONTROL CIRCUIT (Sheet 8 of 11) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001A CONTROL CIRCUIT (Sheet 9 of 11) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001A CONTROL CIRCUIT (Sheet 10 of 11) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001A CONTROL CIRCUIT (Sheet 11 of 11) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001B CONTROL CIRCUIT (Sheet 1 of 10) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001B CONTROL CIRCUIT (Sheet 2 of 10) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001B CONTROL CIRCUIT (Sheet 3 of 10) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001B CONTROL CIRCUIT (Sheet 4 of 10) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001B CONTROL CIRCUIT (Sheet 5 of 10) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001B CONTROL CIRCUIT (Sheet 6 of 10) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001B CONTROL CIRCUIT (Sheet 7 of 10) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001B CONTROL CIRCUIT (Sheet 8 of 10) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001B CONTROL CIRCUIT (Sheet 9 of 10) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LVSG-0001B CONTROL CIRCUIT (Sheet 10 of 10) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL21-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment MCC - WIL21-MCC-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A Control Circuit - 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A Control Circuit - 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A Control Circuit - 11 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A Control Circuit - 12 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A Control Circuit - 13 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A Control Circuit - 14 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A Control Circuit - 15 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A Control Circuit - 16 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A Control Circuit - 17 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002A Control Circuit - 18 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B Control Circuit - 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B Control Circuit - 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B Control Circuit - 11 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B Control Circuit - 12 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B Control Circuit - 13 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B Control Circuit - 14 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B Control Circuit - 15 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0002B Control Circuit - 16 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A Control Circuit - 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A Control Circuit - 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A Control Circuit - 11 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A Control Circuit - 12 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A Control Circuit - 13 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A Control Circuit - 14 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A Control Circuit - 15 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A Control Circuit - 16 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A Control Circuit - 17 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003A Control Circuit - 18 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B Control Circuit - 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B Control Circuit - 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B Control Circuit - 11 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B Control Circuit - 12 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B Control Circuit - 13 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B Control Circuit - 14 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B Control Circuit - 15 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B Control Circuit - 16 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MCC-0003B Control Circuit - 17 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001A CONTROL CIRCUIT LEGEND | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001A CONTROL CIRCUIT -1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001A CONTROL CIRCUIT -2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001A CONTROL CIRCUIT -3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001A CONTROL CIRCUIT -4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001A CONTROL CIRCUIT -5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001A CONTROL CIRCUIT -6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001A CONTROL CIRCUIT -7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001A CONTROL CIRCUIT -8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001A CONTROL CIRCUIT -9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001B CONTROL CIRCUIT LEGEND | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001B CONTROL CIRCUIT -1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001B CONTROL CIRCUIT -2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001B CONTROL CIRCUIT -3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001B CONTROL CIRCUIT -4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001B CONTROL CIRCUIT -5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001B CONTROL CIRCUIT -6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001B CONTROL CIRCUIT -7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001B CONTROL CIRCUIT -8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001B CONTROL CIRCUIT -9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-MDB-0001B CONTROL CIRCUIT -10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LCS - WIL21-LCS-0001xx | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LCS - WIL21-LCS-0001xx | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LCS - WIL21-LCS-0001xx | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LCS - WIL21-LCS-0001xx | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LCS - WIL21-LCS-0001xx | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LCS - WIL21-LCS-0001xx | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LCS - WIL21-LCS-0001xx | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers (2MVA) - WIL22-TRF-0001A, WIL22-TRF-0001B, WIL22-TRF-0002A, WIL22-TRF-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers (2MVA) - WIL22-TRF-0001A, WIL22-TRF-0001B, WIL22-TRF-0002A, WIL22-TRF-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers (2MVA) - WIL22-TRF-0001A, WIL22-TRF-0001B, WIL22-TRF-0002A, WIL22-TRF-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers (2MVA) - WIL22-TRF-0001A, WIL22-TRF-0001B, WIL22-TRF-0002A, WIL22-TRF-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers (2MVA) - WIL22-TRF-0001A, WIL22-TRF-0001B, WIL22-TRF-0002A, WIL22-TRF-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers (2MVA) - WIL22-TRF-0001A, WIL22-TRF-0001B, WIL22-TRF-0002A, WIL22-TRF-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers (2MVA) - WIL22-TRF-0001A, WIL22-TRF-0001B, WIL22-TRF-0002A, WIL22-TRF-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers (2MVA) - WIL22-TRF-0001A, WIL22-TRF-0001B, WIL22-TRF-0002A, WIL22-TRF-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers (2MVA) - WIL22-TRF-0001A, WIL22-TRF-0001B, WIL22-TRF-0002A, WIL22-TRF-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers (2MVA) - WIL22-TRF-0001A, WIL22-TRF-0001B, WIL22-TRF-0002A, WIL22-TRF-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers (2MVA) - WIL22-TRF-0001A, WIL22-TRF-0001B, WIL22-TRF-0002A, WIL22-TRF-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers (2MVA) - WIL22-TRF-0001A, WIL22-TRF-0001B, WIL22-TRF-0002A, WIL22-TRF-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers (2MVA) - WIL22-TRF-0001A, WIL22-TRF-0001B, WIL22-TRF-0002A, WIL22-TRF-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers (2MVA) - WIL22-TRF-0001A, WIL22-TRF-0001B, WIL22-TRF-0002A, WIL22-TRF-0002B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001A Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001A Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001A Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001A Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001A Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001A Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001A Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001A Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001A Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001A Control Circuit - 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001A Control Circuit - 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001B Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001B Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001B Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001B Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001B Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001B Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001B Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001B Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001B Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0001B Control Circuit - 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002A Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002A Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002A Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002A Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002A Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002A Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002A Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002A Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002A Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002A Control Circuit - 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002A Control Circuit - 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002B Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002B Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002B Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002B Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002B Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002B Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002B Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002B Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002B Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-LVSG-0002B Control Circuit - 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001A Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001A Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001A Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001A Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001A Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001A Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001A Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001A Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001A Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001A Control Circuit - 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001A Control Circuit - 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001A Control Circuit - 11 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001A Control Circuit - 12 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001A Control Circuit - 13 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001A Control Circuit - 14 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001B Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001B Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001B Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001B Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001B Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001B Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001B Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001B Control Circuit - 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001B Control Circuit - 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001B Control Circuit - 11 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001B Control Circuit - 12 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001B Control Circuit - 13 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001B Control Circuit - 16 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001B Control Circuit - 17 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0001B Control Circuit - 18 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002A Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002A Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002A Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002A Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002A Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002A Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002A Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002A Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002A Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002A Control Circuit - 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002A Control Circuit - 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002A Control Circuit - 11 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002A Control Circuit - 12 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002A Control Circuit - 13 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002B Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002B Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002B Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002B Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002B Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002B Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002B Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002B Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002B Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002B Control Circuit - 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002B Control Circuit - 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002B Control Circuit - 11 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002B Control Circuit - 12 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0002B Control Circuit - 13 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003A Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003A Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003A Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003A Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003A Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003A Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003A Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003A Control Circuit - 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003A Control Circuit - 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003A Control Circuit - 11 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003A Control Circuit - 12 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003A Control Circuit - 12 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003A Control Circuit - 14 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003A Control Circuit - 15 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003A Control Circuit - 16 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003B Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003B Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003B Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003B Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003B Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003B Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003B Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003B Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003B Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003B Control Circuit - 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003B Control Circuit - 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003B Control Circuit - 11 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003B Control Circuit - 12 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MCC-0003B Control Circuit - 13 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001A Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001A Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001A Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001A Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001A Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001A Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001A Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001A Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001A Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001B Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001B Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001B Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001B Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001B Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001B Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001B Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001B Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0001B Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002A Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002A Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002A Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002A Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002A Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002A Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002A Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002A Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002B Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002B Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002B Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002B Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002B Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002B Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002B Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0002B Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003A Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003A Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003A Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003A Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003A Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003A Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003A Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003A Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003B Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003B Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003B Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003B Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003B Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003B Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003B Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL22-MDB-0003B Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LCS - WIL22-LCS-0001xx | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 250kW LV SS (Sheet 01 of 08) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 250kW LV SS (Sheet 02 of 08) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 250kW LV SS (Sheet 03 of 08) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 250kW LV SS (Sheet 04 of 08) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 250kW LV SS (Sheet 05 of 08) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 250kW LV SS (Sheet 06 of 08) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 250kW LV SS (Sheet 07 of 08) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 250kW LV SS (Sheet 08 of 08) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics -6.6kV Switchgear Battery & Battery Chargers (1 of 6) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics -6.6kV Switchgear Battery & Battery Chargers (2 of 6) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics -6.6kV Switchgear Battery & Battery Chargers (3 of 6) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics -6.6kV Switchgear Battery & Battery Chargers (4 of 6) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics -6.6kV Switchgear Battery & Battery Chargers (5 of 6) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics -6.6kV Switchgear Battery & Battery Chargers (6 of 6) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A LV DOOR LAYOUT= LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A LV LAYOUT= LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A LV DOOR LAYOUT= LZ02, LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A LV LAYOUT= LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A LV LAYOUT= LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A LV DOOR LAYOUT= LZ03, LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A LV LAYOUT= LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A LV LAYOUT= LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A LV DOOR LAYOUT= LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A LV LAYOUT= LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A LV LABEL | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A ATS/ MTS TRANSFER SCHEME & LOGIC DIAGRAM | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A ATS/ MTS TRANSFER SCHEME & LOGIC DIAGRAM | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A ATS/ MTS TRANSFER SCHEME & LOGIC DIAGRAM | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A ATS/ MTS TRANSFER SCHEME & LOGIC DIAGRAM | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A ATS/ MTS TRANSFER SCHEME & LOGIC DIAGRAM | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A POWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A POWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A POWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A POWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A POWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A POWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A POWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A POWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A INCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A INCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A INCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A INCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A INCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A INCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A INCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A INCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A INCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A INCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A INCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A INCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A INCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A INCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A INCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A INCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A INCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A INCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A INCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A INCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A INCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A INCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A INCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A INCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A INCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A INCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A INCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A INCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ02a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A OUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A BUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A BUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A BUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A BUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A BUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A BUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A BUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A BUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A BUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A BUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A BUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A BUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A BUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A BUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A BUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A BUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A BUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A BUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A BUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A BUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A BUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A BUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A BUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A BUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A BUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A BUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A BUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001A TERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BLV DOOR LAYOUT = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BLV LAYOUT = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BLV DOOR LAYOUT = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BLV LAYOUT = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BLV DOOR LAYOUT = LZ03, LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BLV LAYOUT = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BLV LAYOUT = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BLV DOOR LAYOUT = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BLV LAYOUT = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BLV LABEL | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BATS/ MTS TRANSFER SCHEME & LOGIC DIAGRAM | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BATS/ MTS TRANSFER SCHEME & LOGIC DIAGRAM | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BATS/ MTS TRANSFER SCHEME & LOGIC DIAGRAM | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BATS/ MTS TRANSFER SCHEME & LOGIC DIAGRAM | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BATS/ MTS TRANSFER SCHEME & LOGIC DIAGRAM | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BPOWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BPOWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BPOWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BPOWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BPOWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BPOWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BPOWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BPOWER/ BB VT/ BUS VT/ BUS WIRE DIAGRAMS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BINCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BINCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BINCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BINCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BINCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BINCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BINCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BINCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BINCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BINCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BINCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BINCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BINCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BINCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BINCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BINCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BINCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BINCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BINCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BINCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BINCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BINCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BINCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BINCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BINCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BINCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BINCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BINCOMER SCHEMATIC DIAGRAM = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BOUTGOING FEEDER SCHEMATIC = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ03a | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BBUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BBUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BBUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BBUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BBUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BBUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BBUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BBUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BBUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BBUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BBUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BBUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BBUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BBUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BBUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BBUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BBUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BBUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BBUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BBUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BBUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BBUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BBUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BBUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BBUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BBUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BBUS SECTION SCHEMATIC = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear WIL23-HVSG-0001BTERMINAL CONNECTION TABLE = LZ05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV Switchgear - Battery & Battery Chargers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV DOL Starter 510kW- Membrane Air Blower | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV DOL Starter 510kW- Membrane Air Blower (1 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV DOL Starter 510kW- Membrane Air Blower (2 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV DOL Starter 510kW- Membrane Air Blower (3 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV DOL Starter 510kW- Membrane Air Blower (4 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV DOL Starter 510kW- Membrane Air Blower (5 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV DOL Starter 1205kW - Process Air Blower | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV DOL Starter 1205kW - Process Air Blower (1 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV DOL Starter 1205kW - Process Air Blower (2 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV DOL Starter 1205kW - Process Air Blower (3 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV DOL Starter 1205kW - Process Air Blower (4 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 6.6kV DOL Starter 1205kW - Process Air Blower (5 of 5) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/6.6kV Transformers (8/11MVA) - WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/6.6kV Transformers (8/11MVA) - WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/6.6kV Transformers (8/11MVA) - WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/6.6kV Transformers (8/11MVA) - WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/6.6kV Transformers (8/11MVA) - WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/6.6kV Transformers (8/11MVA) - WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/6.6kV Transformers (8/11MVA) - WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/6.6kV Transformers (8/11MVA) - WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/6.6kV Transformers (8/11MVA) - WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/6.6kV Transformers (8/11MVA) - WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/6.6kV Transformers (8/11MVA) - WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/6.6kV Transformers (8/11MVA) - WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/6.6kV Transformers (8/11MVA) - WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/6.6kV Transformers (8/11MVA) - WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/6.6kV Transformers (8/11MVA) - WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Remote-Control Panel Schematic - 22/6.6kV Transformers (8/11MVA) - WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Remote-Control Panel Schematic - 22/6.6kV Transformers (8/11MVA) - WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Remote-Control Panel Schematic - 22/6.6kV Transformers (8/11MVA) - WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Remote-Control Panel Schematic - 22/6.6kV Transformers (8/11MVA) - WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Remote-Control Panel Schematic - 22/6.6kV Transformers (8/11MVA) - WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Remote-Control Panel Schematic - 22/6.6kV Transformers (8/11MVA) - WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Remote-Control Panel Schematic - 22/6.6kV Transformers (8/11MVA) - WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Remote-Control Panel Schematic - 22/6.6kV Transformers (8/11MVA) - WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Remote-Control Panel Schematic - 22/6.6kV Transformers (8/11MVA) - WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Remote-Control Panel Schematic - 22/6.6kV Transformers (8/11MVA) - WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Remote-Control Panel Schematic - 22/6.6kV Transformers (8/11MVA) - WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Remote-Control Panel Schematic - 22/6.6kV Transformers (8/11MVA) - WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Remote-Control Panel Schematic - 22/6.6kV Transformers (8/11MVA) - WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Remote-Control Panel Schematic - 22/6.6kV Transformers (8/11MVA) - WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers (2MVA, 2.5MVA & 3MVA) - WIL23-TRF-0002A, 0002B, 0003A, 0003B, 0004A & 0004B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers (2MVA, 2.5MVA & 3MVA) - WIL23-TRF-0002A, 0002B, 0003A, 0003B, 0004A & 0004B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers (2MVA, 2.5MVA & 3MVA) - WIL23-TRF-0002A, 0002B, 0003A, 0003B, 0004A & 0004B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers (2MVA, 2.5MVA & 3MVA) - WIL23-TRF-0002A, 0002B, 0003A, 0003B, 0004A & 0004B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers (2MVA, 2.5MVA & 3MVA) - WIL23-TRF-0002A, 0002B, 0003A, 0003B, 0004A & 0004B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers (2MVA, 2.5MVA & 3MVA) - WIL23-TRF-0002A, 0002B, 0003A, 0003B, 0004A & 0004B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers (2MVA, 2.5MVA & 3MVA) - WIL23-TRF-0002A, 0002B, 0003A, 0003B, 0004A & 0004B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers (2MVA, 2.5MVA & 3MVA) - WIL23-TRF-0002A, 0002B, 0003A, 0003B, 0004A & 0004B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers (2MVA, 2.5MVA & 3MVA) - WIL23-TRF-0002A, 0002B, 0003A, 0003B, 0004A & 0004B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers (2MVA, 2.5MVA & 3MVA) - WIL23-TRF-0002A, 0002B, 0003A, 0003B, 0004A & 0004B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers (2MVA, 2.5MVA & 3MVA) - WIL23-TRF-0002A, 0002B, 0003A, 0003B, 0004A & 0004B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers (2MVA, 2.5MVA & 3MVA) - WIL23-TRF-0002A, 0002B, 0003A, 0003B, 0004A & 0004B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers (2MVA, 2.5MVA & 3MVA) - WIL23-TRF-0002A, 0002B, 0003A, 0003B, 0004A & 0004B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Local Control Panel Schematic - 22/0.415kV Transformers (2MVA, 2.5MVA & 3MVA) - WIL23-TRF-0002A, 0002B, 0003A, 0003B, 0004A & 0004B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001A Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001A Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001A Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001A Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001A Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001A Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001A Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001A Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001A Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001A Control Circuit - 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001A Control Circuit - 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001A Control Circuit - 11 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001B Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001B Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001B Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001B Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001B Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001B Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001B Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001B Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001B Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001B Control Circuit - 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0001B Control Circuit - 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LVSG - WIL23-LVSG-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002A Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002A Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002A Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002A Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002A Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002A Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002A Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002A Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002A Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002A Control Circuit - 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002A Control Circuit - 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002A Control Circuit - 11 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002B Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002B Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002B Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002B Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002B Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002B Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002B Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002B Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002B Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002B Control Circuit - 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0002B Control Circuit - 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003A Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003A Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003A Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003A Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003A Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003A Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003A Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003A Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003A Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003A Control Circuit - 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003A Control Circuit - 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003A Control Circuit - 11 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003B Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003B Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003B Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003B Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003B Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003B Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003B Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003B Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003B Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003B Control Circuit - 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-LVSG-0003B Control Circuit - 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001A Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001A Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001A Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001A Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001A Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001A Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001A Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001A Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001A Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001A Control Circuit - 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001A Control Circuit - 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001A Control Circuit - 11 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001A Control Circuit - 12 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001A Control Circuit - 13 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001A Control Circuit - 14 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001A Control Circuit - 15 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001B Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001B Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001B Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001B Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001B Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001B Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001B Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001B Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001B Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001B Control Circuit - 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001B Control Circuit - 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001B Control Circuit - 11 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001B Control Circuit - 12 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001B Control Circuit - 13 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001B Control Circuit - 14 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0001B Control Circuit - 15 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002A Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002A Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002A Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002A Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002A Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002A Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002A Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002A Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002A Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002A Control Circuit - 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002A Control Circuit - 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002A Control Circuit - 11 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002A Control Circuit - 12 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002A Control Circuit - 13 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002A Control Circuit - 14 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002B Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002B Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002B Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002B Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002B Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002B Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002B Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002B Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002B Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002B Control Circuit - 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002B Control Circuit - 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002B Control Circuit - 11 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002B Control Circuit - 12 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002B Control Circuit - 13 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0002B Control Circuit - 14 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003A Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003A Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003A Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003A Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003A Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003A Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003A Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003A Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003A Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003A Control Circuit - 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003A Control Circuit - 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003A Control Circuit - 11 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003A Control Circuit - 12 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003A Control Circuit - 13 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003A Control Circuit - 14 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003B Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003B Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003B Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003B Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003B Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003B Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003B Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003B Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003B Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003B Control Circuit - 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003B Control Circuit - 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003B Control Circuit - 11 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003B Control Circuit - 12 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003B Control Circuit - 13 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0003B Control Circuit - 14 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004A Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004A Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004A Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004A Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004A Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004A Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004A Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004A Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004A Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004A Control Circuit - 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004A Control Circuit - 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004A Control Circuit - 11 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004A Control Circuit - 12 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004A Control Circuit - 13 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004A Control Circuit - 14 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004A Control Circuit - 15 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004A Control Circuit - 16 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004B Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004B Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004B Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004B Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004B Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004B Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004B Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004B Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004B Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004B Control Circuit - 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004B Control Circuit - 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004B Control Circuit - 11 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004B Control Circuit - 12 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004B Control Circuit - 13 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004B Control Circuit - 14 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0004B Control Circuit - 15 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A Control Circuit - 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A Control Circuit - 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A Control Circuit - 11 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A Control Circuit - 12 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A Control Circuit - 13 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A Control Circuit - 14 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A Control Circuit - 15 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A Control Circuit - 16 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A Control Circuit - 17 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005A Control Circuit - 18 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B Control Circuit - 9 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B Control Circuit - 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B Control Circuit - 11 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B Control Circuit - 12 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B Control Circuit - 13 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B Control Circuit - 14 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B Control Circuit - 15 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B Control Circuit - 16 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MCC-0005B Control Circuit - 17 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001A Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001A Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001A Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001A Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001A Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001A Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001A Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001A Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001A Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001B Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001B Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001B Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001B Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001B Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001B Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001B Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001B Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0001B Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002A Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002A Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002A Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002A Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002A Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002A Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002A Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002A Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002A Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002B Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002B Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002B Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002B Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002B Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002B Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002B Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002B Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0002B Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003A Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003A Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003A Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003A Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003A Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003A Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003A Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003A Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003A Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003B Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003B Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003B Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003B Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003B Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003B Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003B Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003B Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0003B Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004A Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004A Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004A Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004A Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004A Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004A Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004A Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004A Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004A Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004B Control Circuit Legend | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004B Control Circuit - 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004B Control Circuit - 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004B Control Circuit - 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004B Control Circuit - 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004B Control Circuit - 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004B Control Circuit - 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004B Control Circuit - 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL23-MDB-0004B Control Circuit - 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - Low Voltage System Equipment LCS - WIL23-LCS-0001xx | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 450kW LV VFD (Sheet 01 of 05) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 450kW LV VFD (Sheet 01 of 05) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 450kW LV VFD (Sheet 01 of 05) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 450kW LV VFD (Sheet 01 of 05) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 450kW LV VFD (Sheet 01 of 05) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 315kW LV VFD (Sheet 01 of 04) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 315kW LV VFD (Sheet 02 of 04) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 315kW LV VFD (Sheet 03 of 04) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 315kW LV VFD (Sheet 04 of 04) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 400kW LV VFD (Sheet 10 of 17) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 400kW LV VFD (Sheet 11 of 17) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 400kW LV VFD (Sheet 12 of 17) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 400kW LV VFD (Sheet 13 of 17) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 400kW LV VFD (Sheet 14 of 17) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 400kW LV VFD (Sheet 15 of 17) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 400kW LV VFD (Sheet 16 of 17) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 400kW LV VFD (Sheet 17 of 17) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 280kW LV VFD (Sheet 01 of 05) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 280kW LV VFD (Sheet 02 of 05) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 280kW LV VFD (Sheet 03 of 05) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 280kW LV VFD (Sheet 04 of 05) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 280kW LV VFD (Sheet 05 of 05) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 225kW LV VFD (Sheet 01 of 13) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 225kW LV VFD (Sheet 02 of 13) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 225kW LV VFD (Sheet 03 of 13) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 225kW LV VFD (Sheet 04 of 13) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 225kW LV VFD (Sheet 05 of 13) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 225kW LV VFD (Sheet 06 of 13) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 225kW LV VFD (Sheet 07 of 13) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 225kW LV VFD (Sheet 08 of 13) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 225kW LV VFD (Sheet 09 of 13) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 225kW LV VFD (Sheet 10 of 13) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 225kW LV VFD (Sheet 11 of 13) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 225kW LV VFD (Sheet 12 of 13) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 225kW LV VFD (Sheet 13 of 13) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 160kW LV VFD (Sheet 01 of 13) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 160kW LV VFD (Sheet 02 of 13) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 160kW LV VFD (Sheet 03 of 13) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 160kW LV VFD (Sheet 04 of 13) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 160kW LV VFD (Sheet 05 of 13) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 160kW LV VFD (Sheet 06 of 13) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 160kW LV VFD (Sheet 07 of 13) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 160kW LV VFD (Sheet 08 of 13) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 160kW LV VFD (Sheet 09 of 13) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 160kW LV VFD (Sheet 10 of 13) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 160kW LV VFD (Sheet 11 of 13) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 160kW LV VFD (Sheet 12 of 13) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 160kW LV VFD (Sheet 13 of 13) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 90kW LV VFD (Sheet 01 of 05) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 90kW LV VFD (Sheet 02 of 05) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 90kW LV VFD (Sheet 03 of 05) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 90kW LV VFD (Sheet 04 of 05) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 90kW LV VFD (Sheet 05 of 05) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 90kW LV VFD (Sheet 06 of 12) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 90kW LV VFD (Sheet 07 of 12) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 90kW LV VFD (Sheet 08 of 12) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 90kW LV VFD (Sheet 09 of 12) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 90kW LV VFD (Sheet 10 of 12) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 90kW LV VFD (Sheet 11 of 12) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 90kW LV VFD (Sheet 12 of 12) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 75kW LV VFD (Sheet 01 of 12) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 75kW LV VFD (Sheet 02 of 12) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 75kW LV VFD (Sheet 03 of 12) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 75kW LV VFD (Sheet 04 of 12) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 75kW LV VFD (Sheet 05 of 12) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 75kW LV VFD (Sheet 06 of 12) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 75kW LV VFD (Sheet 07 of 12) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 75kW LV VFD (Sheet 08 of 12) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 75kW LV VFD (Sheet 09 of 12) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 75kW LV VFD (Sheet 10 of 12) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 75kW LV VFD (Sheet 11 of 12) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Panel Schematics - 75kW LV VFD (Sheet 12 of 12) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | SD |  |  |  | 131236-SD-E | Shop Drawings - HV System Equipment - 22kV Switchgears Remote Control Panels | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | SD |  |  |  | 131236-SD-E | Shop Drawings - HV - 6.6kV Switchgears Remote Control Panels | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | Electrical | Stage 2 | SD |  |  |  | 131236-SD-E | Shop Drawings - HV System Equipment - 22/6.6kV Transformers OLTC & Marshalling Panel | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | SD |  |  |  | 131236-SD-E | Shop Drawings - Low Voltage System Equipment - Valve DBs | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | SD |  |  |  | 131236-SD-E | Shop Drawings - Low Voltage System Equipment - Lighting & Small Power DB | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | SD |  |  |  | 131236-SD-E | Shop Drawings - Continuous On-line hot spot temperature Monitoring and Alert System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Site office Lightning Protection System Plan View | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Site office Lightning Protection System Elevation View 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Site office Lightning Protection System Elevation View 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Site office Lightning Protection System Elevation View 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Site office Lightning Protection System Elevation View 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Site office Lightning Protection System Plan & Elevation View | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Site office Lightning Protection System Elevation Installation Details Drawing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | ILM2 Schematic Earthing General Note | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | ILM2 Schematic Earthing Sheet 01 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | ILM2 Schematic Earthing Sheet 02 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | ILM2 Schematic Earthing Sheet 03 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | ILM2 Schematic Earthing Sheet 04 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | ILM2 Schematic Earthing Sheet 05 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | ILM2 Schematic Earthing Sheet 06 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | ILM2 Schematic Earthing Sheet 07 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | ILM2 Schematic Earthing Sheet 08 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | ILM2 Schematic Earthing Sheet 09 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | ILM2 Schematic Earthing Sheet 10 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | ILM2 Schematic Earthing Sheet 11 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | ILM2 Schematic Earthing Sheet 12 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Earthing System Typical Installation Detail 1 - Sheet 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Earthing System Typical Installation Detail 1 - Sheet 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Earthing System Typical Installation Detail 1 - Sheet 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Earthing System Typical Installation Detail 1 - Sheet 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Earthing System Typical Installation Detail 1 - Sheet 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Earthing System Typical Installation Detail 1 - Sheet 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL06 LV Switchroom 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL06 LV Switchroom 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL06 Field LCS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL06 Earthing & Lightning Protection | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Section View - WIL06 LV Switchroom 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Section View - WIL06 LV Switchroom 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | LIGHTNING PROTECTION SYSTEM WIL 06 ELEVATION B & D | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | LIGHTNING PROTECTION SYSTEM WIL 06 ELEVATION A & C | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | LIGHTNING PROTECTION SYSTEM WIL 06 PLAN LAYOUT | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | EARTHING AND EQUIPOTENTIAL BONDING LAYOUT WIL 06 – SFL 5.3 PLAN | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL13 LV Switchroom 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL13 LV Switchroom 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL13 Field WAS LCS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL13 Earthing & Lightning Protection | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Section View - WIL13 LV Switchroom 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Section View - WIL13 LV Switchroom 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-Blower Room Area-Electrical Cable Raceway Plan | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-Cable Chamber 1,2-Electrical Raceway Plan | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-LV Switch Room 1,2-Electrical Cable Raceway Plan | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-EPS Room-Electrical Cable Raceway Plan | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-Transformer Room 1,2-Electrical Cable Raceway Plan | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-Cable Chamber 3-Electrical Cable Raceway Plan | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-Blower Room Area-Electrical Cable Raceway Section View Sheet 1 of 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-Blower Room Area-Electrical Cable Raceway Section View Sheet 2 of 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-Cable Chamber 1,2-Electrical Cable Raceway Section View Sheet 1 of 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-Cable Chamber 1,2-Electrical Cable Raceway Section View Sheet 2 of 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-Cable Chamber Room 1,2-Electrical Cable Raceway Section View Sheet 3 of 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-EPS ROOM-Electrical Cable Raceway Section View Sheet 1 of 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-EPS ROOM-Electrical Cable Raceway Section View Sheet 2 of 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-Transformer Room 1,2-Electrical Cable Raceway Section View Sheet 1 of 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-Cable Chamber 3-Electrical Cable Raceway Section View Sheet 1 of 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | WIL21-Cable Chamber 3-Electrical Cable Raceway Section View Sheet 2 of 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL21 LV Switchroom 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL21 LV Switchroom 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL21 Transformer room 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL21 Transformer room 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL21 Field LCS & LCP | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL21 Earthing & Lightning Protection | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Section View - WIL21 LV Switchroom 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Section View - WIL21 LV Switchroom 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Section View - WIL21 Transformer room 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Section View - WIL21 Transformer room 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | LIGHTNING PROTECTION SYSTEM WIL 21 ELEVATION B & SECTION XX LAYOUT | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | LIGHTNING PROTECTION SYSTEM WIL 21 ELEVATION A & D LAYOUT | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | LIGHTNING PROTECTION SYSTEM WIL 21 PLAN LAYOUT | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | EARTHING AND EQUIPOTENTIAL BONDING LAYOUT WIL 21 – SFL 5.3 PLAN | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | EARTHING AND EQUIPOTENTIAL BONDING LAYOUT WIL 21 – SFL 8.3 PLAN | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | EARTHING AND EQUIPOTENTIAL BONDING LAYOUT WIL 21 – SFL 12.2 PLAN | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | EARTHING AND EQUIPOTENTIAL BONDING LAYOUT WIL 21 – SFL 15.8 PLAN | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | EARTHING AND EQUIPOTENTIAL BONDING LAYOUT WIL 21 – SFL 15.8 EQUIPMENT | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | EARTHING AND EQUIPOTENTIAL BONDING LAYOUT WIL 21 – SFL 21.8 PLAN | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | EARTHING AND EQUIPOTENTIAL BONDING LAYOUT WIL 21 – SFL 23.9 PLAN | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | EARTHING AND EQUIPOTENTIAL BONDING LAYOUT WIL 21 – BASEMENT PLAN | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL22 LV Switchroom 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL22 LV Switchroom 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL22 Transformer room 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL22 Transformer room 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL22 Transformer room 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL22 Transformer room 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL22 Field LCS & LCP | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL22 Earthing & Lightning Protection | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Section View - WIL22 LV Switchroom 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Section View - WIL22 LV Switchroom 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Section View - WIL22 Transformer room 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Section View - WIL22 Transformer room 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Section View - WIL22 Transformer room 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Section View - WIL22 Transformer room 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | LIGHTNING PROTECTION SYSTEM WIL 12 ELEVATION B & C | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | LIGHTNING PROTECTION SYSTEM WIL 22 ELEVATION A & D | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | LIGHTNING PROTECTION SYSTEM WIL 22 PLAN LAYOUT | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | EQUIPOTENTIAL BONDING LAYOUT WIL 22 – SFL 5.3 PLAN | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | EQUIPOTENTIAL BONDING LAYOUT WIL 22 – SFL 15.9 PLAN | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | EQUIPOTENTIAL BONDING LAYOUT WIL 22 – SFL 26.4 PLAN | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | EQUIPOTENTIAL BONDING LAYOUT WIL 22 – SFL 28.9 PLAN | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | EQUIPOTENTIAL BONDING LAYOUT WIL 22 – ROOF PLAN | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | 22kV HT Switchroom Floor Opening | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL23 LV Switchroom 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL23 LV Switchroom 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL23 Transformer room 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL23 Transformer room 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL23 Transformer room 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL23 Transformer room 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL23 Transformer room 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL23 Transformer room 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL23 Transformer room 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL23 Transformer room 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL23 Field LCS & LCP | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL23 Earthing & Lightning Protection | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Section View - WIL23 LV Switchroom 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Section View - WIL23 LV Switchroom 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Section View - WIL23 Transformer room 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Section View - WIL23 Transformer room 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Section View - WIL23 Transformer room 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Section View - WIL23 Transformer room 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Section View - WIL23 Transformer room 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Section View - WIL23 Transformer room 6 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Section View - WIL23 Transformer room 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Section View - WIL23 Transformer room 8 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | NER GA for WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | NER Rating Plate for WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | NER Wiring Diagram for WIL23-TRF-0001A & WIL23-TRF-0001B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Domestic LM2 Secondary Electrical Equipment Arrangement (6.6kV HV Cable Tray Room 1 and 2) Plan at +12.300m | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Domestic LM2 Secondary Electrical Equipment Arrangement (6.6kV HV Cable Tray Room 1 and 2) Section A-A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Domestic LM2 Secondary Electrical Equipment Arrangement (6.6kV HV Cable Tray Room 1 and 2) Section B-B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Domestic LM2 Secondary Electrical Equipment Arrangement (6.6kV HV Cable Tray Room 1 and 2) Section C-C | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | EARTHING AND EQUIPOTENTIAL BONDING LAYOUT WIL 23 – SFL 5.3 PLAN – A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | EARTHING AND EQUIPOTENTIAL BONDING LAYOUT WIL 23 – SFL 5.3 PLAN – B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | EARTHING AND EQUIPOTENTIAL BONDING LAYOUT WIL 23 – SFL 7.4 PLAN | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | EARTHING AND EQUIPOTENTIAL BONDING LAYOUT WIL 23 – SFL 7.4 PLAN | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | EARTHING AND EQUIPOTENTIAL BONDING LAYOUT WIL 23 – SFL 12.0 PLAN – B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | EARTHING AND EQUIPOTENTIAL BONDING LAYOUT WIL 23 – SFL 14.6 PLAN – A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | EARTHING AND EQUIPOTENTIAL BONDING LAYOUT WIL 23 – SFL 19.6 PLAN | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | EARTHING AND EQUIPOTENTIAL BONDING LAYOUT WIL 23 – SFL 22.1 PLAN – A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | EARTHING AND EQUIPOTENTIAL BONDING LAYOUT WIL 23 – SFL 22.1 PLAN | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | EARTHING AND EQUIPOTENTIAL BONDING LAYOUT WIL 23 – SFL 26.4 PLAN | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | EARTHING AND EQUIPOTENTIAL BONDING LAYOUT WIL 23 – SFL 28.9 PLAN | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | EARTHING AND EQUIPOTENTIAL BONDING LAYOUT WIL 23 – SFL 26.4 PLAN | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | EARTHING AND EQUIPOTENTIAL BONDING LAYOUT WIL 23 – SFL 28.9 PLAN | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | SUBSTATION B TO C3D2 HV CABLE ROUTING | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | SUBSTATION B TO C3D2 HV CABLE ROUTING | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | SUBSTATION B TO C3D2 HV CABLE ROUTING | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | SUBSTATION B TO C3D2 HV CABLE ROUTING | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | SUBSTATION B TO C3D2 HV CABLE ROUTING | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | SUBSTATION B TO C3D2 HV CABLE ROUTING | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | SUBSTATION B TO C3D2 HV CABLE ROUTING | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | SUBSTATION B TO C3D2 HV CABLE ROUTING | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | SUBSTATION B TO C3D2 HV CABLE ROUTING | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | SUBSTATION B TO C3D2 HV CABLE ROUTING | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | ILM2 Secondary WIL23 22kV HV Cable Route 1 & Route 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL06 Power Cable Routing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Section View - WIL06 Power Cable Routing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Typical Cable Support - WIL06 Power Cable Routing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL13 Power Cable Routing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Section View - WIL13 Power Cable Routing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Typical Cable Support - WIL13 Power Cable Routing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL21 Power Cable Routing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Section View - WIL21 Power Cable Routing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Typical Cable Support - WIL21 Power Cable Routing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL22 Power Cable Routing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Section View - WIL22 Power Cable Routing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Typical Cable Support - WIL22 Power Cable Routing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL23 Power Cable Routing 3rd Storey Part 1 of 3 +14.60 mm | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL23 Power Cable Routing 3rd Storey Part 2 of 3 +14.60 mm | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL23 Power Cable Routing 3rd Storey Part 3 of 3 +14.60 mm | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Cable Arrangement Detail 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Section View - WIL23 Power Cable Routing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Typical Cable Support - WIL23 Power Cable Routing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL06 Lighting and Small Power | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Typical Installation Details - WIL06 Lighting and Small Power | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL13 Lighting and Small Power | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Typical Installation Details - WIL13 Lighting and Small Power | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | ILM2 Headworks Small Power System Layout Operation Area +15.800m | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Typical Installation Details - WIL21 Lighting and Small Power | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL22 Lighting and Small Power | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Typical Installation Details - WIL22 Lighting and Small Power | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Layout Drawing - Plan View - WIL23 Lighting and Small Power | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Lighting Layout Drawing - 3rd Storey Plan at +14.60m Part 1 of 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Lighting Layout Drawing - 3rd Storey Plan at +14.60m Part 2 of 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-03-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Lighting Layout Drawing - 3rd Storey Plan at +14.60m Part 3 of 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Small Power Systemt Layout - 3rd Storey Plan Part 1 0f 3 at +14.60m | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Small Power Systemt Layout - 3rd Storey Plan Part 2 0f 3 at +14.60m | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | Electrical | Stage 2 | DR |  |  |  | 131236-DR-E | Small Power Systemt Layout - 3rd Storey Plan Part 3 0f 3 at +14.60m | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Raceway FAT and ITP Procedure | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | LV Cables FAT and ITP Procedure | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Main Distribution Board (MDB) FAT Procedure | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Painting Procedure - 22kV GIS (WIL00-HVSG-0001A/B) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Painting Procedure - 6.6kV GIS (WIL23-HVSG-0001A/B & WIL15-HVSG-0001A/B) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Painting Procedure - 6.6kV DOL starter | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Painting Procedure - 415V LV Switchgear & MCC | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Painting Procedure - MDBs, LCS and Sub DBs | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Painting Procedure - 30V DC Battery charger system | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Factory Acceptance Test Procedures - 22kV GIS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Factory Acceptance Test Procedures - 6.6kV GIS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Factory Acceptance Test Procedures - 6.6kV DOL starter | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Factory Acceptance Test procedure - 415V LV Switchgear & MCC | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Factory Acceptance Test procedure - MDBs, LCS and Sub DBs | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Factory Acceptance Test Procedures - 30V DC Battery charger system | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Factory Acceptance Test Procedures - various LV VFDs & Sort Starter | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Factory Acceptance Test and Inspection Test Plan for HT Cables | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Factory Acceptance Test Plan for 22kV and 6.6kV HVSG Battery Charger | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Inspection Test Plan and Factory Acceptance Test for ABB WavePro-R Busway | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Factory Acceptance Test Plan for 6.6kV and 22kV HVSG RCP | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Factory Acceptance Test Procedure For Transformer | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Factory Acceptance Test Procedures - 22/6.6kV 8MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Factory Acceptance Test Procedures - 22/0.415kV 3MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Factory Acceptance Test Procedures - 22/0.415kV 2.75MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Factory Acceptance Test Procedures - 22/0.415kV 2.5MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Factory Acceptance Test Procedures - 22/0.415kV 2MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Factory Acceptance Test Procedure for LV Main Switchboard’s | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Inspection Test Plan - 22kV GIS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Inspection Test Plan - 6.6kV GIS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Inspection Test Plan - 6.6kV DOL starter | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Inspection Test Plan - 415V LV Switchgear & MCC | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Inspection Test Plan - MDBs, LCS and Sub DBs | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Inspection Test Plan - 30V DC Battery charger system | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Inspection Test Plan - various LV VFDs & Soft Starter | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Inspection And Test Plan For Transformer | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Inspection Test Plan - 22/6.6kV 8MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Inspection Test Plan - 22/0.415kV 3MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Inspection Test Plan - 22/0.415kV 2.75MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Inspection Test Plan - 22/0.415kV 2.5MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Inspection Test Plan - 22/0.415kV 2MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Inspection & Test Plan for LV Switchgear, MCC Panels and MDB | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Testing and Commissioning Test procedures, Method statement, Checklist - 22kV GIS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Testing and Commissioning Test procedures, Method statement, Checklist - 6.6kV GIS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Testing and Commissioning Test procedures, Method statement, Checklist - 6.6kV DOL starter | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Testing and Commissioning Test procedures, Method statement, Checklist -415V LV Switchgear & MCC | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Testing and Commissioning Test procedures, Method statement, Checklist - MDB, Sub DB and LCS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Testing and Commissioning Test procedures, Method statement, Checklist - 30V DC Battery charger system | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Testing and Commissioning Test procedures, Method statement, Checklist - various LV VFDs | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Testing and Commissioning Test procedures, Method statement, Checklist - 22/6.6kV 8MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Testing and Commissioning Test procedures, Method statement, Checklist - 22/0.415kV 3MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Testing and Commissioning Test procedures, Method statement, Checklist - 22/0.415kV 2.75MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Testing and Commissioning Test procedures, Method statement, Checklist - 22/0.415kV 2.5MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Testing and Commissioning Test procedures, Method statement, Checklist - 22/0.415kV 2MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Factory Acceptance Test Report - 22kV GIS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Factory Acceptance Test Report- 6.6kV GIS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Factory Acceptance Test Report- 6.6kV DOL starter | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Factory Acceptance Test Report - 415V LV Switchgear & MCC | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Factory Acceptance Test Report - LV Drive | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Factory Acceptance Test Report - LV Soft Starter | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Factory Acceptance Test Report - MDBs, LCS and Sub DBs | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 3 | QA |  |  |  | 131236-QA-E | Factory Acceptance Test Report- 30V DC Battery charger system | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 4 | SH |  |  |  | 131236-SH-E | Packing List, Bill of Lading, Material on Consigment/Delivery Order for 22kV GIS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 4 | SH |  |  |  | 131236-SH-E | Packing List, Bill of Lading, Material on Consigment/Delivery Order for 6.6kV GIS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 4 | SH |  |  |  | 131236-SH-E | Packing List, Bill of Lading, Material on Consigment/Delivery Order for 6.6kV DOL starter | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 4 | SH |  |  |  | 131236-SH-E | Packing List, Bill of Lading, Material on Consigment/Delivery Order for 22/6.6kV 8MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 4 | SH |  |  |  | 131236-SH-E | Packing List, Bill of Lading, Material on Consigment/Delivery Order for 22/0.415kV 3MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 4 | SH |  |  |  | 131236-SH-E | Packing List, Bill of Lading, Material on Consigment/Delivery Order for 22/0.415kV 2.75MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 4 | SH |  |  |  | 131236-SH-E | Packing List, Bill of Lading, Material on Consigment/Delivery Order for 22/0.415kV 2.5MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 4 | SH |  |  |  | 131236-SH-E | Packing List, Bill of Lading, Material on Consigment/Delivery Order for 22/0.415kV 2MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 4 | SH |  |  |  | 131236-SH-E | Packing List, Bill of Lading, Material on Consigment/Delivery Order for 415V LVSG | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 4 | SH |  |  |  | 131236-SH-E | Packing List, Bill of Lading, Material on Consigment/Delivery Order for 415V MCC | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 4 | SH |  |  |  | 131236-SH-E | Packing List, Bill of Lading, Material on Consigment/Delivery Order for 415V MDB | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 4 | SH |  |  |  | 131236-SH-E | Packing List, Bill of Lading, Material on Consigment/Delivery Order for 415V Sub DB | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 4 | SH |  |  |  | 131236-SH-E | Packing List, Bill of Lading, Material on Consigment/Delivery Order for 415V LCS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 4 | SH |  |  |  | 131236-SH-E | Packing List, Bill of Lading, Material on Consigment/Delivery Order for LV VFD | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 4 | SH |  |  |  | 131236-SH-E | Packing List, Bill of Lading, Material on Consigment/Delivery Order for LV Spoft Starter | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 4 | SH |  |  |  | 131236-SH-E | Packing List, Bill of Lading, Material on Consigment/Delivery Order for 30V DC Battery Charger System | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 5 | SH |  |  |  | 131236-SH-E | Lightning Protection System - Risk Assessment | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 5 | SH |  |  |  | 131236-SH-E | WIL21, WIL22 And WIL23 Transformer Plinth Coring | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 5 | SH |  |  |  | 131236-SH-E | MS RA SWP General Electrical Installation Works | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 5 | SH |  |  |  | 131236-SH-E | MS RA SWP For Underground Sub-Station 22kV Cable and Raceway Installation | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 5 | SH |  |  |  | 131236-SH-E | MS RA For Transformer Delivery & Positioning | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 5 | SH |  |  |  | 131236-SH-E | MS RA For Site Acceptance Test of Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 5 | SH |  |  |  | 131236-SH-E | MS RA For Oil Purification & Filling of 11 MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 5 | SH |  |  |  | 131236-SH-E | MS RA for Delivery, Loading, Unloading & Positioning of Electrical Panels, LCS, Sub DB and Accessories | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 5 | SH |  |  |  | 131236-SH-E | MS RA for Low Voltage Panels Installation Works | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 5 | SH |  |  |  | 131236-SH-E | MS RA for Uncrating, Loading, Unloading and Positioning of Panels and Accessories | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 5 | SH |  |  |  | 131236-SH-E | Installation procedures, Method statement, Checklist - 22kV GIS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 5 | SH |  |  |  | 131236-SH-E | Installation procedures, Method statement, Checklist - 6.6kV GIS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 5 | SH |  |  |  | 131236-SH-E | Installation procedures, Method statement, Checklist - 6.6kV DOL starter | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 5 | SH |  |  |  | 131236-SH-E | Installation procedures, Method statement, Checklist - 22/6.6kV 8MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 5 | SH |  |  |  | 131236-SH-E | Installation procedures, Method statement, Checklist - 22/0.415kV 3MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 5 | SH |  |  |  | 131236-SH-E | Installation procedures, Method statement, Checklist - 22/0.415kV 2.75MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 5 | SH |  |  |  | 131236-SH-E | Installation procedures, Method statement, Checklist - 22/0.415kV 2.5MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 5 | SH |  |  |  | 131236-SH-E | Installation procedures, Method statement, Checklist - 22/0.415kV 2MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 5 | SH |  |  |  | 131236-SH-E | Installation procedures, Method statement, Checklist - 415V LV Switchgear & MCC | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 5 | SH |  |  |  | 131236-SH-E | Installation procedures, Method statement, Checklist - MDB, Sub DBs and LCS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 5 | SH |  |  |  | 131236-SH-E | Installation procedures, Method statement, Checklist - 30V DC Battery charger system | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 6 | RT |  |  |  | 131236-RT-E | Testing and Commissioning Report- 22kV GIS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 6 | RT |  |  |  | 131236-RT-E | Testing and Commissioning Report- 6.6kV GIS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 6 | RT |  |  |  | 131236-RT-E | Testing and Commissioning Report- 6.6kV DOL starter | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 6 | RT |  |  |  | 131236-RT-E | Testing and Commissioning Report-22/6.6kV 8MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 6 | RT |  |  |  | 131236-RT-E | Testing and Commissioning Report- 22/0.415kV 3MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 6 | RT |  |  |  | 131236-RT-E | Testing and Commissioning Report- 22/0.415kV 2.75MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 6 | RT |  |  |  | 131236-RT-E | Testing and Commissioning Report- 22/0.415kV 2.5MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 6 | RT |  |  |  | 131236-RT-E | Testing and Commissioning Report- 22/0.415kV 2MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 6 | RT |  |  |  | 131236-RT-E | Installation procedures, Method statement, Checklist - 415V LV Switchgear & MCC | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 6 | RT |  |  |  | 131236-RT-E | Installation procedures, Method statement, Checklist - MDB, Sub DBs and LCS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 6 | RT |  |  |  | 131236-RT-E | Installation procedures, Method statement, Checklist - 30V DC Battery charger system | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 7 | OM |  |  |  | 131236-OM-E | IOM - 22kV GIS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 7 | OM |  |  |  | 131236-OM-E | IOM - 6.6kV GIS | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 7 | OM |  |  |  | 131236-OM-E | IOM- 6.6kV DOL starter | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 7 | OM |  |  |  | 131236-OM-E | IOM - 22/6.6kV 8MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 7 | OM |  |  |  | 131236-OM-E | IOM - 22/0.415kV 3MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 7 | OM |  |  |  | 131236-OM-E | IOM - 22/0.415kV 2.75MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 7 | OM |  |  |  | 131236-OM-E | IOM - 22/0.415kV 2.5MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 7 | OM |  |  |  | 131236-OM-E | IOM - 22/0.415kV 2MVA Transformers | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 7 | OM |  |  |  | 131236-OM-E | IOM - 415V LV Switchgear & MCC | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 7 | OM |  |  |  | 131236-OM-E | IOM - MDBs, LCS and Sub DBs | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | Electrical | Stage 7 | OM |  |  |  | 131236-OM-E | IOM - 30V DC Battery charger system | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | CSA | Stage 1 | VI |  | WIL21 | NO | 131236-WIL21-VI-S-xxxx | Vendor Approval for Structure Fabricator | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | CSA | Stage 1 | DR |  | WNS03 | NO | 131236-WNS03-DR-S-xxxx | WNS03 High Head Surge Vessel Platforms | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | CSA | Stage 1 | DR |  | WNS03 | NO | 131236-WNS03-DR-S-xxxx | WNS03 High Head Surge Vessel Platform Railings | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | CSA | Stage 1 | DR |  | WNS03 | NO | 131236-WNS03-DR-S-xxxx | WNS03 Low Head Surge Vessel Platforms | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | CSA | Stage 1 | DR |  | WNS03 | NO | 131236-WNS03-DR-S-xxxx | WNS03 Low Head Surge Vessel Platform Railings | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | CSA | Stage 1 | DR |  | WNS03 | NO | 131236-WNS03-DR-C-xxxx | WNS03 Plinth Layout and Details for Surge Vessel | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | CSA | Stage 1 | DR |  | WIL06 |  | 131236-WIL06-DR-S-xxxx | WIL06 Cross-over Stairs | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | CSA | Stage 1 | DR |  | WIL06 | NO | 131236-WIL06-DR-S-xxxx | WIL06 Chemical Dosing Bundle Wall Panel and Frame | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-03-01 | CSA | Stage 1 | DR |  | WIL06 | NO | 131236-WIL06-DR-S-xxxx | WIL06 Dosing Cabinet | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-03-01 | CSA | Stage 1 | DR |  | WIL06 | NO | 131236-WIL06-DR-S-xxxx | WIL06 Dosing Cabinet | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-03-01 | CSA | Stage 1 | DR |  | WIL06 | NO | 131236-WIL06-DR-S-xxxx | WIL06 Unloading Coupling Box | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-03-01 | CSA | Stage 1 | DR |  | WIL06 | NO | 131236-WIL06-DR-S-xxxx | WIL06 Unloading Coupling Box | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | CSA | Stage 1 | DR |  | WIL06 | NO | 131236-WIL06-DR-S-xxxx | WIL06 Chemical Dosing Operation Platform | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | CSA | Stage 1 | DR |  | WIL06 | NO | 131236-WIL06-DR-S-xxxx | WIL06 Chemical Dosing Operation Platform | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 1 Grit Hopper and Support | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 1 Headworks Screenings Hopper and Support | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-03-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 1 Misc Support - Below 2m | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 1 Misc Support - 2m and above | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-03-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Mezzanine Level Misc Support - Below 2m | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Mezzanine Level Misc Support - 2m and above | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-03-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 2 Misc Support - Below 2m | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 2 Misc Support - 2m and above | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 2 Grit Tank Lauder and Support | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-11-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 2 Grit Tank Picket Fence | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 2 DN1400 FRP Duck Support Frame A | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-03-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 3 Misc Support - Below 2m | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 3 Misc Support - 2m and above | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 3 Common Service Rack Grid 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 3 Common Service Rack Grid 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 3 Common Service Rack Grid 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 3 Common Service Rack Grid 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 3 Common Service Rack Grid F | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 3 Common Service Rack Grid H | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 3 Common Service Rack Grid K | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 3 Service Platform for EOTC Overhead Crane Grid D | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 3 Service Platform Railing for EOTC Overhead Crane Grid D | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 3 Service Platform for EOTC Overhead Crane Grid H | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 3 Service Platform Railing for EOTC Overhead Crane Grid H | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 3 Runway Beam for Intermediate Screens Crane WIL21-021-CRN-0001 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 3 Runway Beam for Fine Screens Crane WIL21-022-CRN-0001 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 3 Runway Beam for Grease and Scum Wet Wells Crane WIL21-024-CRN-0001 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 3 Runway Beam for Grit Tanks Crane WIL21-024-CRN-0002 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 4 DN1400 FRP Duck Support Frame B | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 4 DN1400 FRP Duck Support Frame C | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 4 DN1400 FRP Duck Support Frame D | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 4 DN1400 FRP Duck Support Frame E | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 3 GRIT Classifier Platform 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 3 GRIT Classifier Platform 1 Railing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 3 GRIT Classifier Damper Platform 2 and 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 3 GRIT Classifier Damper Platform 2 and 3 Railing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 3 Intermediate Screen Platform 4 and 5 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 3 Intermediate Screen Platform 4 and 5 Railing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 3 Intermediate Screen Platform 6 and 7 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL21 Floor 3 Intermediate Screen Platform 6 and 7 Railing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL22 Floor 1 PSI Pump Corssover Platform | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL22 Floor 1 PSI Pump Crossover Platform Railing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL22 Floor 1 PST Tank Laminar Support 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL22 Floor 1 PST Tank Laminar Support 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL22 Floor 1 PST Tank Laminar Support 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL22 Floor 1 PST Tank Top Platform 1 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL22 Floor 1 PST Tank Top Platform 1 Railing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL22 Floor 1 PST Tank Top Platform 2 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL22 Floor 1 PST Tank Top Platform 2 Railing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL22 Floor 1 PST Tank Top Platform 3 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-02-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL22 Floor 1 PST Tank Top Platform 3 Railing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-03-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL22 Floor 3 Misc Support - Below 2m | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL22 Floor 3 Misc Support - 2m and above | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL22 Floor 3 Runway Beam for Crane 1xxx | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL22 Floor 3 Runway Beam for Crane 2xxx | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL22 Floor 3 Service Platform for Crane 1xxx | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL22 Floor 3 Service Platform Railing for Crane 1xxx | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL22 Floor 3 Service Platform for Crane 2xxx | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL22 Floor 3 Service Platform Railing for Crane 2xxx | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL22 Floor 3 Service Platform 4 | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2027-01-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL22 Floor 3 Service Platform 4 Railing | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned | 2026-12-01 | CSA | Stage 1 | DR |  | WIL21 | NO | 131236-WIL21-DR-S-xxxx | WIL22 Floor 3 Service Rack Grid G | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BIM | M2 | PP |  | WSW46 |  | 131236-WSW46-PP-IM-8106 | BIM Execution Plan | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BIM | M2 | DR |  | WSW46 |  | 131236-WSW46-DR-IM-0001 | Drawing list | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BIM | M2 | FM |  | WSW46 |  | 131236-WSW46-FM-IM-0001 | QA/QC Report -Native BIM Model Template | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BIM | M2 | FM |  | WSW46 |  | 131236-WSW46-FM-IM-0002 | QA/QC Report -Federated BIM Model Template | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BIM | M2 | FM |  | WSW46 |  | 131236-WSW46-FM-IM-0003 | QA/QC Report -Drawing template | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BIM | M2 | FM |  | WSW46 |  | 131236-WSW46-FM-IM-0004 | QA/QC Report -4D Template | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BIM | Unassigned | FM |  | WSW46 |  | 131236-WSW46-FM-IM-0005 | QA/QC Report -5D Template | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BIM | M2 | FM |  | WSW46 |  | 131236-WSW46-FM-IM-0006 | QA/QC Report -PID | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BIM | M2 | FM |  | WSW46 |  | 131236-WSW46-FM-IM-0007 | Clash report Check List | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BIM | M2 | FM |  | WSW46 |  | 131236-WSW46-FM-IM-0008 | Major Clash Report | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BIM | M2 | PP |  | WSW46 |  | 131236-WSW46-PP-IM-0003 | LOD Matrix Instruction | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1
Planned |  | BIM | M2 | PP |  | WIL00 |  | 131236-WIL00-PP-PT-1002 | Master Information Delivery Plan (MIDP) | [8 empty] | NFS - Not Yet Submitted | Not Yet Returned |  |  |  | 0 | 1