## Dashboard
Refer to "Procurement-Dashboard.html" file.

## Code
Project Metadata Title | Project Metadata Values | Project Metadata Data Type | Discipline Code | Discipline Description | Criticality Code | Criticality | Status Code | Package Status | Category Code | Item Category | Error Code | Error Description | Severity | Group | Kind | Trigger Check
Project Title | TWRP C3B2 | Text | A | Architecture | 0 | Not Applicable | NS | Not Start | BSW | Building Service Work Package | V-01 | Rows inside the data range with a blank Package Title are skipped | info | Structure / Rows | system | Row in range has no Package Title
Project Code | C3B2 | Text | B | Building Services | 1 | Factory In-house Quality Control | MR | Requisition in Progress | CAB | Cable | V-02 | Value is a number but not a real Excel date | error | Dates | data | Date field is a number but not in the Excel date range (40000–70000)
Client | PUB | Text | C | Civil | 2 | Third Party Inspection | VI | Pending Vendor Approval | CTL | Cable Tray and Ladder | V-03 | Text value cannot be read as a date | error | Dates | data | Date field is text that cannot be parsed
Consultant | Jacobs | Text | D | Design Management | 3 | Witness Point | PP | Pending PO Confirmation | CWP | Construction Work Package | V-04 | Value is not numeric | error | Values / Numeric | data | Quantity or Lead Time is non-numeric
Dashboard Title | Procurement Package Plan | Text | E | Electrical | 4 | FAT Record Submission Only | PO | PO Issued, Prepare Vendor Data Submission | DCS | Design Consultancy Service | V-05 | Criticality must be one of the listed values; empty count is reported separately | error / warning | Criticality | data | Criticality not in the Code sheet (code or description); aggregate blank count
Project Start Date | 2026-03-19 | Date | G | Geotechnical |  |  | VDA | Pending Vendor Data Approval | EBK | EICA Bulk | V-06 | Discipline not found in the Code sheet list | warning | Discipline | data | Discipline not in the Code sheet list
Header Row | 1 | Int | HS | Environmental, Health, Safety & Security |  |  | FAB | Fabrication in Progress | EPN | EICA Panels | V-07 | Status not found in the Code sheet list | error | Status | data | Status not in the Code sheet list (code or description)
List End Row | 300 | Int | I | Instrument, Control & Automation (ICA) |  |  | FAT | FAT Completed | EEQ | Electrical Equipment | V-08 | Stage plan dates are out of sequence | warning | Dates / Stages | data | Stage plan out of sequence (e.g., MR Plan > PO Plan)
S No. | Column-A | Int | IM | Information Management/IT |  |  | DEL | Delivered | EQP | Equipment Package | V-09 | Actual date entered but the Plan is empty | warning | Dates / Stages | data | Actual date present but the matching Plan is empty
Discipline | Column-B | Text | K | Construction Management |  |  | RI | Receive Inspection Done | IEQ | ICA Equipment | V-10 | Actual date is later than today | warning | Dates / Stages | data | Actual date later than today (the as-of date)
Package Title | Column-C | Text | M | Mechanical |  |  |  |  | IPN | ICA Panel | V-11 | Duplicate Package No. — appears N times | warning | Identity | data | Duplicate Package No.
Package No. | Column-D | Text | PI | Piping |  |  |  |  | INS | Instrument | V-12 | Same engineer written different ways — counted as N separate people | warning | Engineer | data | Same engineer written differently (whitespace / slash-spacing variants)
Item Category | Column-E | Text | PR | Process |  |  |  |  | MMI | Misc. Mech Item | V-13 | Rows after List End Row contain a Package Title but are excluded | warning | Structure / Rows | system | PPP rows with a Title beyond List End Row
Area | Column-F | Text | PC | Project Controls |  |  |  |  | PBK | Piping Bulk | V-14 | Lead time missing on N packages (X%) | warning | Lead time | data | Lead time missing on more than 50% of packages
Equipment Tags | Column-G | Text | PM | Project Management |  |  |  |  | PSP | Piping SP | V-15 | Header Row, List End Row, Project Start Date or Data Type issue | error / warning | Config / Code sheet | system | Code-sheet config / Data-Type mismatch (Header / List End / Start / Type)
Package Notes | Column-H | Text | Q | Quantity Survey/Estimating |  |  |  |  | REQ | Rotating Equipment | V-16 | Column C has no Data Type values — fell back to built-in | warning | Config / Code sheet | system | Code sheet column C empty (no Data Types)
Criticality | Column-I | Text | S | Structural |  |  |  |  | SEQ | Static Equipment | V-17 | Item Category not found in the Code sheet list (reference only) | info | Category | data | Item Category not in the Code sheet list
Quantity | Column-J | Number | W | Procurement, Contract |  |  |  |  | VAL | Valve | V-18 | Lookup block not found in row 1 | warning | Config / Lookup | system | A lookup block absent from Code row 1, or its code column empty
Estimate Lead Time | Column-K | Int | Z | General (non-specific) |  |  |  |  | PSV | Pressure Vessel | V-19 | Header Row has no value in the Package Title column | warning | Config / Code sheet | system | PPP Header Row cell at the title column is blank
Package Status | Column-L | Text | [8 empty] | V-20 | Expected N data rows but only M had content | warning | Structure / Rows | system | Expected data rows exceed actual parsed rows
Supplier | Column-M | Text | [8 empty] | V-21 | Rule code has no row in the Code sheet Error table | warning | Config / Workbook | system | A rule code has no row in the Code!Q:R Error table
Design Engineer | Column-N | Text | [8 empty] | V-22 | Lookup code column is empty — values cannot be cross-checked | warning | Config / Lookup | system | A lookup block's CODE column is empty while its description column has values
Buyer | Column-O | Text | [8 empty] | V-23 | No Actual dates entered in any stage for any package | warning | Progress / Execution | data | Execution progress = 0 (no Actual dates in any stage, any package)
Project Engineer | Column-P | Text | [8 empty] | V-24 | Package has no Design Engineer | warning | Engineer | data | Engineer unassigned / blank
MR Plan Date | Column-Q | Date | [8 empty] | V-25 | MR Plan entered for few packages while PO Plan present for many | warning | Dates / Stages | data | Plan-date inconsistency (MR Plan sparse vs PO Plan present)
MR Forecast Date | Column-R | Date
MR Actual Date | Column-S | Date
PO Plan Date | Column-T | Date
PO Forecast Date | Column-U | Date
PO Actual Date | Column-V | Date
VD Approval Plan Date | Column-W | Date
VD Approval Forecast Date | Column-X | Date
VD Approval Actual Date | Column-Y | Date
FAT Plan Date | Column-Z | Date
FAT Forecast Date | Column-AA | Date
FAT Actual Date | Column-AB | Date
ROS Plan Date | Column-AC | Date
ROS Forecast Date | Column-AD | Date
ROS Actual Date | Column-AE | Date

## PPP
S/No. (A1) | Discipline (A2) | Package Title (A3) | Package No. (A4) | Item Category (A5) | Area (A6) | Equipment Tags (A7) | Package Notes (A8) | Criticality (A9) | Quantity (Nos.) (A10) | Estimate Lead Time (Days) (A11) | Package Status (A12) | Supplier (A13) | Design Engineer (B1) | Buyer (B2) | PE (B3) | MR Plan Date (C1) | MR Forecast Date (C2) | MR Actual Date (C3) | PO Plan Date (D1) | PO Forecast Date (D2) | PO Actual Date (D3) | VD Approval Plan Date (E1) | VD Approval Forecast Date (E2) | VD Approval Actual Date (E3) | FAT Plan Date (F1) | FAT Forecast Date (F2) | FAT Actual Date (F3) | ROS Plan Date (G1) | ROS Forecast Date (G2) | ROS Actual Date (G3)
1 | Design Management | CSA Consultant | MR-D-0001 | Design Consultancy Service | All |  |  | Not Applicable |  | 30 | PO Issued, Prepare Vendor Data Submission |  | Mark |  |  | 2026-07-15 |  |  | 2026-08-15 |  | 2026-09-30 | [6 empty] | 2026-09-15
2 | Design Management | HAZOP and ALMOP Consultant | MR-D-0002 | Design Consultancy Service | All |  | [2026/09/11] SO suggested to engage PureTach. | Not Applicable |  | 30 | Not Start |  | Kenny |  |  | 2026-09-02 |  |  | 2026-11-01 | [8 empty] | 2027-01-15
3 | Design Management | M&E Consultant (Building Service) | MR-D-0003 | Design Consultancy Service | All |  |  | Not Applicable |  | 30 | Not Start |  | Fadil |  |  | 2026-05-15 |  |  | 2026-07-15 | 2026-11-15 | [7 empty] | 2026-08-15
4 | Design Management | Mechanical Consultant | MR-D-0004 | Design Consultancy Service | All |  |  | Not Applicable |  | 30 | Not Start |  | Franklin |  |  | 2027-06-02 |  |  | 2027-08-01 | [8 empty] | 2027-09-01
7 | Project Management | Tank PVC Lining Installation Contractor | MR-PM-0007 | Construction Work Package | All |  | [2026/10/05] PO# 22151 | Not Applicable |  | 30 | PO Issued, Prepare Vendor Data Submission | VORTEX | Mark |  |  | 2026-06-16 |  |  | 2026-08-15 |  | 2026-08-14 | [6 empty] | 2026-09-15
8 | Project Management | Mechanical Installation Contractor | MR-PM-0008 | Construction Work Package | All |  |  | Not Applicable |  | 30 | Not Start |  | TBC |  |  | 2026-11-02 |  |  | 2027-01-01 | [8 empty] | 2027-02-01
9 | Project Management | Electrical Installation Contractor | MR-PM-0009 | Construction Work Package | All |  | to consider direct sub contracting. | Not Applicable |  | 30 | Not Start |  | Ammar |  |  | 2026-11-02 |  |  | 2027-01-01 | [8 empty] | 2027-02-01
128 | Project Management | ICA Installation Contractor | MR-PM-0128 | Construction Work Package | All |  |  | Not Applicable |  | 30 | Not Start |  | Ricarte |  |  | 2026-11-02 |  |  | 2027-01-01 | [8 empty] | 2027-02-01
10 | Project Management | Structure Steel Fabricator | MR-PM-0010 | Construction Work Package | All |  |  | Not Applicable |  | 30 | Not Start |  | TBC |  |  | 2026-09-02 |  |  | 2026-11-01
11 | Project Management | Structure Steel Installation Contractor | MR-PM-0011 | Construction Work Package | All |  |  | Not Applicable |  | 30 | Not Start |  | TBC |  |  | 2025-12-03 |  |  | 2027-02-01
12 | Project Management | Concrete Work Contractor | MR-PM-0012 | Construction Work Package | All |  |  | Not Applicable |  | 30 | Not Start |  | TBC |  |  | 2026-09-02 |  |  | 2026-11-01
13 | Civil | GI grating | MR-C-0013 | Construction Work Package | All |  |  | Not Applicable |  | 30 | Not Start |  | TBC |  |  | 2026-12-31 |  |  | 2027-03-01
14 | Structural | Aluminium Railing, Ladder and Cover | MR-S-0014 | Construction Work Package | All |  |  | Not Applicable |  | 30 | Not Start |  | TBC |  |  | 2027-04-02 |  |  | 2027-06-01
20 | Mechanical | Ejector | MR-M-0020 | Static Equipment | WIL23 | WIL23 - ILM2 MBR Filtrate Air Ejector 1~9 (TBC) |  | FAT Record Submission Only | 9 | 60 | Requisition in Progress |  | Fadhli |  |  | 2026-09-09 |  |  | 2026-11-08 |  |  | 2027-01-07 |  |  | 2026-12-08 |  |  | 2027-01-07
26 | Mechanical | CFD analysis/ hydraulic modelling / surge analysis | MR-M-0026 | Design Consultancy Service |  |  |  | FAT Record Submission Only |  | 30 | Requisition in Progress |  | Kenny/Franklin |  |  | 2026-08-01 |  |  | 2026-09-30 | 2026-11-15 |  | 2026-11-29 |  |  | 2026-09-30 |  |  | 2026-10-30
46 | Piping | Pressure Relief Valve | MR-PI-0046 | Valve |  |  |  | FAT Record Submission Only |  | 30 | Requisition in Progress |  | Fadhli |  |  | 2026-08-01 |  |  | 2026-12-30 |  |  | 2027-02-28 |  |  | 2026-12-30 |  |  | 2027-01-29
47 | Piping | Pressure Reducing Valve - Metal | MR-PI-0047 | Valve |  |  |  | FAT Record Submission Only |  | 30 | Requisition in Progress |  | Fadhli |  |  | 2026-08-01 |  |  | 2026-12-30 |  |  | 2027-02-28 |  |  | 2026-12-30 |  |  | 2027-01-29
48 | Piping | Pressure Sustaning Valve - Metal | MR-PI-0048 | Valve |  |  |  | FAT Record Submission Only |  | 30 | Requisition in Progress |  | Fadhli |  |  | 2026-08-01 |  |  | 2026-12-30 |  |  | 2027-02-28 |  |  | 2026-12-30 |  |  | 2027-01-29
49 | Piping | Plastic Valve (Ball, Check, Back Pressure) | MR-PI-0049 | Valve |  |  |  | FAT Record Submission Only |  | 30 | Requisition in Progress |  | Fadhli |  |  | 2026-08-01 |  |  | 2026-12-30 |  |  | 2027-02-28 |  |  | 2026-12-30 |  |  | 2027-01-29
50 | Piping | Condensate Drain | MR-PI-0050 | Valve |  |  |  | FAT Record Submission Only |  | 30 | Not Start |  | TBC |  |  | 2026-08-01 |  |  | 2026-11-30 |  |  | 2027-01-29 |  |  | 2026-11-30 |  |  | 2026-12-30
52 | Piping | Stainless Steel Piping | MR-PI-0052 | Piping Bulk |  | Cast-in piping may be ordered separately. |  | FAT Record Submission Only |  | 60 | Not Start |  | Dilip/Siva |  |  | 2027-01-30 |  |  | 2027-03-01 | [8 empty] | 2027-04-30
53 | Piping | CSEL Piping | MR-PI-0053 | Piping Bulk |  | Cast-in piping may be ordered separately. |  | FAT Record Submission Only |  | 60 | Not Start |  | Dilip/Siva |  |  | 2027-01-30 |  |  | 2027-03-01 | [8 empty] | 2027-04-30
54 | Piping | DI and DIPU Piping | MR-PI-0054 | Piping Bulk |  | Cast-in piping may be ordered separately. |  | FAT Record Submission Only |  | 60 | Not Start |  | Dilip/Siva |  |  | 2026-10-04 |  |  | 2026-12-03 | [8 empty] | 2027-02-01
55 | Piping | FRP Piping | MR-PI-0055 | Piping Bulk |  | Cast-in piping may be ordered separately. |  | FAT Record Submission Only |  | 60 | Not Start |  | Dilip/Siva |  |  | 2026-10-04 |  |  | 2026-12-03 | [8 empty] | 2027-02-01
56 | Piping | PVC and cPVC Piping | MR-PI-0056 | Piping Bulk |  | Cast-in piping may be ordered separately. |  | FAT Record Submission Only |  | 60 | Not Start |  | Dilip/Siva |  |  | 2027-02-01 |  |  | 2027-04-02 | [8 empty] | 2027-06-01
57 | Piping | HDPE Piping | MR-PI-0057 | Piping Bulk |  | Cast-in piping may be ordered separately. |  | FAT Record Submission Only |  | 60 | Not Start |  | Dilip/Siva |  |  | 2026-10-04 |  |  | 2026-12-03 | [8 empty] | 2027-02-01
58 | Piping | Chemical Valve Box | MR-PI-0058 | Piping SP |  |  |  | FAT Record Submission Only |  | 60 | Not Start |  | Dilip/Siva |  |  | 2026-10-04 |  |  | 2027-04-02 | [8 empty] | 2027-06-01
59 | Piping | Piping Gasket | MR-PI-0059 | Piping Bulk |  |  |  | FAT Record Submission Only |  | 60 | Not Start |  | Dilip/Siva |  |  | 2026-10-04 |  |  | 2026-12-03 | [8 empty] | 2027-02-01
60 | Piping | Piping Standard/Primary Support | MR-PI-0060 | Piping Bulk |  |  |  | FAT Record Submission Only |  | 60 | Not Start |  | Dilip/Siva |  |  | 2026-10-04 |  |  | 2026-12-03 | [8 empty] | 2027-02-01
61 | Piping | Piping Bolts and Nuts | MR-PI-0061 | Piping Bulk |  |  |  | FAT Record Submission Only |  | 60 | Not Start |  | Dilip/Siva |  |  | 2026-10-04 |  |  | 2026-12-03 | [8 empty] | 2027-02-01
62 | Piping | Piping SP Items (to be separated) | MR-PI-0062 | Piping SP |  |  |  | FAT Record Submission Only |  | 60 | Not Start |  | Dilip/Siva |  |  | 2026-10-04 |  |  | 2026-12-03 | [8 empty] | 2027-02-01
63 | Piping | Piping Secondary Support (MS) | MR-PI-0063 | Piping Bulk |  |  |  | FAT Record Submission Only |  | 60 | Not Start |  | TBC |  |  | 2026-11-16 |  |  | 2027-01-15 | [8 empty] | 2027-03-16
64 | Piping | Piping Secondary Support (Unistrut) | MR-PI-0064 | Piping Bulk |  |  |  | FAT Record Submission Only |  | 60 | Not Start |  | Dilip/Siva |  |  | 2026-10-04 |  |  | 2026-12-03 | [8 empty] | 2027-02-01
69 | Electrical | VDB | MR-E-0069 | EICA Panels |  |  | Valve Sub-DB(160A) - 5 nos Valve Sub-DB(80A) - 11 nos Valve Sub-DB(63A) - 30 nos Local DB - FP Equipment - 5 nos |  | 51 | 140 |  | Sunlight | Ammar |  |  | 2026-10-27 |  |  | 2026-12-26 |  |  | 2027-02-24 |  |  | 2027-04-15 |  |  | 2027-05-15
73 | Electrical | MV, LV, and Earthing Cable | MR-E-0073 | Cable |  |  |  | FAT Record Submission Only |  | 84 | Pending Vendor Approval | Tai Jie | Ammar |  |  | 2026-09-24 |  |  | 2026-11-23 |  |  | 2027-01-22 |  |  | 2027-01-16 |  |  | 2027-02-15
74 | Electrical | Lighting and Small Power | MR-E-0074 | EICA Bulk |  |  | Main Breaker 80A TPN MCCB 65KA c/w SHT TRIP - Sub breaker 39×1P 50kA MCB/ 4×3P 50kA MCB - Outgoing breaker 39×2P 40A 30mA RCCB/ 4×4P 40A 100mA RCD | FAT Record Submission Only | 33 | 60 | Requisition in Progress |  | Ammar |  |  | 2026-11-20 |  |  | 2027-01-20 |  |  | 2027-03-21 |  |  | 2027-02-28 |  |  | 2027-03-30
78 | Instrument, Control & Automation (ICA) | LCP Panel | MR-I-0078 | EICA Panels | WIL23 | WIL23-LCP-CA-0101 | To confirm LCP panel list Process: 16 nos. Non-process: 1 nos. | FAT Record Submission Only | 17 | 70 | Not Start |  | Ricarte |  |  | 2026-12-06 |  |  | 2027-02-04 |  |  | 2027-04-05 |  |  | 2027-03-16 |  |  | 2027-04-15
79 | Instrument, Control & Automation (ICA) | ICA Field UPS DB | MR-I-0079 | EICA Panels | WIL13 WIL23 | WIL23-UPS-0002 to 0004 WIL13-UPS-0001, 0002 | To confirm UPS panel list | FAT Record Submission Only | 8 | 84 | Not Start |  | Ricarte |  |  | 2027-04-24 |  |  | 2027-06-23 |  |  | 2027-08-22 |  |  | 2027-08-16 |  |  | 2027-09-15
80 | Instrument, Control & Automation (ICA) | ICA Junction Box | MR-I-0080 | EICA Panels |  | Refer to panel master list and panel GA |  | FAT Record Submission Only |  | 56 | Not Start |  | Ricarte |  |  | 2026-11-19 |  |  | 2027-01-18 |  |  | 2027-03-19 |  |  | 2027-02-13 |  |  | 2027-03-15
81 | Instrument, Control & Automation (ICA) | Instrument, Control, and Communication Cable | MR-I-0081 | Cable |  | Refer to instrument cable schedule | Instrument power, control, signal, data, and fibre optic. To consider separate package for early works. | FAT Record Submission Only |  | 70 | Pending Vendor Approval | KEI | Ricarte |  |  | 2026-10-08 |  |  | 2026-12-07 |  |  | 2027-02-05 |  |  | 2027-01-16 |  |  | 2027-02-15
82 | Instrument, Control & Automation (ICA) | Cable Gland | MR-I-0082 | EICA Bulk |  | Refer to ICA Bulk MTO | Include electrical and ICA | FAT Record Submission Only |  | 45 | Not Start |  | Ricarte |  |  | 2027-01-15 |  |  | 2027-03-16 |  |  | 2027-05-15 |  |  | 2027-03-16 |  |  | 2027-04-15
83 | Instrument, Control & Automation (ICA) | Cable Raceway | MR-I-0083 | Cable Tray and Ladder |  | Refer to cable tray MTO | SS and Galv. MS, for Electrical and ICA | FAT Record Submission Only |  | 45 | Pending Vendor Approval | TRI-STAR | Ricarte |  |  | 2026-10-02 |  |  | 2026-12-01 |  |  | 2027-01-30 |  |  | 2026-12-16 |  |  | 2027-01-15
84 | Instrument, Control & Automation (ICA) | Pressure Gauge | MR-I-0084 | Instrument | WIL00 WIL06 | Refer to Process Instrument List |  | FAT Record Submission Only | 48 | 45 | Pending Vendor Approval | BAUMER | Ricarte |  |  | 2026-11-30 |  |  | 2027-01-29 |  |  | 2027-03-30 |  |  | 2027-02-13 |  |  | 2027-03-15
85 | Instrument, Control & Automation (ICA) | Pressure Transmitter | MR-I-0085 | Instrument | WIL00 WIL21 | Refer to Process Instrument List |  | FAT Record Submission Only | 77 | 45 | Pending Vendor Approval | EMERSON | Ricarte |  |  | 2026-11-30 |  |  | 2027-01-29 |  |  | 2027-03-30 |  |  | 2027-02-13 |  |  | 2027-03-15
86 | Instrument, Control & Automation (ICA) | Pressure Switch | MR-I-0086 | Instrument | WIL00 | Refer to Process Instrument List |  | FAT Record Submission Only | 31 | 45 | Pending Vendor Approval | WIKA INSTRUMENTATION | Ricarte |  |  | 2026-11-30 |  |  | 2027-01-29 |  |  | 2027-03-30 |  |  | 2027-02-13 |  |  | 2027-03-15
87 | Instrument, Control & Automation (ICA) | Differential Pressure Transmitter | MR-I-0087 | Instrument | WNS03 | Refer to Process Instrument List |  | FAT Record Submission Only | 6 | 45 | Pending Vendor Approval | EMERSON | Ricarte |  |  | 2026-11-30 |  |  | 2027-01-29 |  |  | 2027-03-30 |  |  | 2027-02-13 |  |  | 2027-03-15
88 | Instrument, Control & Automation (ICA) | Temperature Transmitter c/w RTD | MR-I-0088 | Instrument | WIL21 WIL23 | Refer to Process Instrument List |  | FAT Record Submission Only | 32 | 45 | Pending Vendor Approval | ENDRESS + HAUSER | Ricarte |  |  | 2026-11-30 |  |  | 2027-01-29 |  |  | 2027-03-30 |  |  | 2027-02-13 |  |  | 2027-03-15
89 | Instrument, Control & Automation (ICA) | Temperature Switch c/w RTD | MR-I-0089 | Instrument | WIL22 | Refer to Process Instrument List |  | FAT Record Submission Only | 4 | 45 | Requisition in Progress |  | Ricarte |  |  | 2026-11-30 |  |  | 2027-01-29 |  |  | 2027-03-30 |  |  | 2027-02-13 |  |  | 2027-03-15
90 | Instrument, Control & Automation (ICA) | Room Temperature Sensor | MR-I-0090 | Instrument | WIL21 WIL22 WIL23 | Refer to Process Instrument List |  | FAT Record Submission Only | 34 | 30 | Pending Vendor Approval | KELE & ASSOCIATES | Ricarte |  |  | 2027-01-15 |  |  | 2027-03-16 |  |  | 2027-05-15 |  |  | 2027-03-16 |  |  | 2027-04-15
91 | Instrument, Control & Automation (ICA) | Level Transmitter Radar (Non-Contacting) Level Transmitter – RF Admittance Level Switch – Conductive Probe Level Switch – Tuning Fork | MR-I-0091 | Instrument | WIL21 WIL22 WIL23 | Refer to Process Instrument List |  | FAT Record Submission Only | 108 | 84 | Pending Vendor Approval | ENDRESS + HAUSER | Ricarte |  |  | 2026-10-22 |  |  | 2026-12-21 |  |  | 2027-02-19 |  |  | 2027-02-13 |  |  | 2027-03-15
92 | Instrument, Control & Automation (ICA) | Level Switch Sludge Blanket – Ultrasonic | MR-I-0092 | Instrument |  | Refer to Process Instrument List |  | FAT Record Submission Only |  | 112 | Pending Vendor Approval | PULSAR – MAESTRO | Ricarte |  |  | 2026-09-24 |  |  | 2026-11-23 |  |  | 2027-01-22 |  |  | 2027-02-13 |  |  | 2027-03-15
93 | Instrument, Control & Automation (ICA) | Level Switch - Ultrasonic | MR-I-0093 | Instrument |  | Refer to Process Instrument List |  | FAT Record Submission Only | 3 | 84 | Requisition in Progress |  | Ricarte |  |  | 2026-10-22 |  |  | 2026-12-21 |  |  | 2027-02-19 |  |  | 2027-02-13 |  |  | 2027-03-15
94 | Instrument, Control & Automation (ICA) | Level Gauge - Magnetic Level Switch for Magnetic Level Gauge | MR-I-0094 | Instrument |  | Refer to Process Instrument List |  | FAT Record Submission Only |  | 84 | Requisition in Progress |  | Ricarte |  |  | 2026-10-22 |  |  | 2026-12-21 |  |  | 2027-02-19 |  |  | 2027-02-13 |  |  | 2027-03-15
95 | Instrument, Control & Automation (ICA) | Thermal Mass Flowmeter Thermal Flow Switch | MR-I-0095 | Instrument | WIL00 WIL21 WIL22 WIL23 | Refer to Process Instrument List |  | FAT Record Submission Only | 130 | 112 | Pending Vendor Approval | ENDRESS + HAUSER | Ricarte |  |  | 2026-10-25 |  |  | 2026-12-24 |  |  | 2027-02-22 |  |  | 2027-03-16 |  |  | 2027-04-15
96 | Instrument, Control & Automation (ICA) | Rotameter c/w Flow (Reed) Switch | MR-I-0096 | Instrument | WIL21 WIL23 | Refer to Process Instrument List | with flow switch - 20 nos. | FAT Record Submission Only | 23 | 70 | Requisition in Progress |  | Ricarte |  |  | 2026-12-06 |  |  | 2027-02-04 |  |  | 2027-04-05 |  |  | 2027-03-16 |  |  | 2027-04-15
97 | Instrument, Control & Automation (ICA) | Flowmeter - Electromagnetic | MR-I-0097 | Instrument | WIL00 WIL06 WIL21 WIL22 WIL23 | Refer to Process Instrument List |  | FAT Record Submission Only | 108 | 112 | Requisition in Progress |  | Ricarte |  |  | 2026-10-25 |  |  | 2026-12-24 |  |  | 2027-02-22 |  |  | 2027-03-16 |  |  | 2027-04-15
98 | Instrument, Control & Automation (ICA) | Flowmeter - Open Channel Ultrasonic | MR-I-0098 | Instrument | WIL21 WIL22 | Refer to Process Instrument List |  | FAT Record Submission Only | 11 | 112 | Requisition in Progress |  | Ricarte |  |  | 2026-10-25 |  |  | 2026-12-24 |  |  | 2027-02-22 |  |  | 2027-03-16 |  |  | 2027-04-15
99 | Instrument, Control & Automation (ICA) | Low Point Leak Detector | MR-I-0099 | Instrument | WIL06 WIL23 | Refer to Process Instrument List |  | FAT Record Submission Only | 14 | 70 | Pending Vendor Approval | IFM ELECTRONIC | Ricarte |  |  | 2027-01-05 |  |  | 2027-03-06 |  |  | 2027-05-05 |  |  | 2027-04-15 |  |  | 2027-05-15
100 | Instrument, Control & Automation (ICA) | Hydrogen Sulfide Gas Detector Carbon Monoxide Gas Detector Flammable (LEL) Gas Detector | MR-I-0100 | Instrument | WIL21 | Refer to Process Instrument List | LEL detector display | FAT Record Submission Only | 12 | 112 | Pending Vendor Approval | DRAEGER | Ricarte |  |  | 2026-11-24 |  |  | 2027-01-23 |  |  | 2027-03-24 |  |  | 2027-04-15 |  |  | 2027-05-15
101 | Instrument, Control & Automation (ICA) | Turbidity Analyser Ammonia Analyser Total Suspended Solid (MLSS) Analyser Nitrate / Nitrite Analyser | MR-I-0101 | Instrument | WIL22 WIL23 | Refer to Process Instrument List |  | FAT Record Submission Only | 37 | 112 | Pending Vendor Approval | HACH WATER | Ricarte |  |  | 2026-11-24 |  |  | 2027-01-23 |  |  | 2027-03-24 |  |  | 2027-04-15 |  |  | 2027-05-15
102 | Instrument, Control & Automation (ICA) | pH Analyser Dissolved Oxygen Analyser | MR-I-0102 | Instrument | WIL21 WIL23 | Refer to Process Instrument List |  | FAT Record Submission Only | 52 | 84 | Pending Vendor Approval | EMERSON | Ricarte |  |  | 2026-12-22 |  |  | 2027-02-20 |  |  | 2027-04-21 |  |  | 2027-04-15 |  |  | 2027-05-15
103 | Instrument, Control & Automation (ICA) | Toxicity Analyser | MR-I-0103 | Instrument | WIL21 | Refer to Process Instrument List |  | FAT Record Submission Only | 1 | 168 | Pending Vendor Approval | AI ANALYTICAL | Ricarte |  |  | 2026-09-29 |  |  | 2026-11-28 |  |  | 2027-01-27 |  |  | 2027-04-15 |  |  | 2027-05-15
104 | Instrument, Control & Automation (ICA) | Volatile Organic Compound (VOC) Gas Analyser | MR-I-0104 | Instrument | WIL21 | Refer to Process Instrument List |  | FAT Record Submission Only | 2 | 168 | Pending Vendor Approval | HONEYWELL | Ricarte |  |  | 2026-09-29 |  |  | 2026-11-28 |  |  | 2027-01-27 |  |  | 2027-04-15 |  |  | 2027-05-15
105 | Instrument, Control & Automation (ICA) | Total Solid Analyser | MR-I-0105 | Instrument | WIL22 | Refer to Process Instrument List |  | FAT Record Submission Only | 2 | 120 | Pending Vendor Approval | VALMET - WETEC | Ricarte |  |  | 2026-11-16 |  |  | 2027-01-15 |  |  | 2027-03-16 |  |  | 2027-04-15 |  |  | 2027-05-15
106 | Instrument, Control & Automation (ICA) | Orthophosphate Analyser Conductivity Analyser | MR-I-0106 | Instrument | WIL23 | Refer to Process Instrument List |  | FAT Record Submission Only | 3 | 112 | Pending Vendor Approval | ENDRESS + HAUSER | Ricarte |  |  | 2026-11-24 |  |  | 2027-01-23 |  |  | 2027-03-24 |  |  | 2027-04-15 |  |  | 2027-05-15
107 | Instrument, Control & Automation (ICA) | ORP Analyser | MR-I-0107 | Instrument | WIL23 | Refer to Process Instrument List |  | FAT Record Submission Only | 7 | 84 | Pending Vendor Approval | YOKOGAWA | Ricarte |  |  | 2026-12-22 |  |  | 2027-02-20 |  |  | 2027-04-21 |  |  | 2027-04-15 |  |  | 2027-05-15
108 | Instrument, Control & Automation (ICA) | Portable Analyser | MR-I-0108 | Instrument |  | Refer to Process Instrument List |  | FAT Record Submission Only |  | 70 | Requisition in Progress |  | Ricarte |  |  | 2027-01-05 |  |  | 2027-03-06 |  |  | 2027-05-05 |  |  | 2027-04-15 |  |  | 2027-05-15
109 | Instrument, Control & Automation (ICA) | Auto Sampler | MR-I-0109 | Instrument | WIL21 WIL23 | Refer to Process Instrument List |  | FAT Record Submission Only | 6 | 112 | Pending Vendor Approval | ENDRESS + HAUSER | Ricarte |  |  | 2026-11-24 |  |  | 2027-01-23 |  |  | 2027-03-24 |  |  | 2027-04-15 |  |  | 2027-05-15
110 | Instrument, Control & Automation (ICA) | Weight Transmitter | MR-I-0110 | Instrument | WIL21 | Refer to Process Instrument List | Load cell | FAT Record Submission Only | 4 | 56 | Pending Vendor Approval | METTLER – TOLEDO | Ricarte |  |  | 2027-01-19 |  |  | 2027-03-20 |  |  | 2027-05-19 |  |  | 2027-04-15 |  |  | 2027-05-15
111 | Instrument, Control & Automation (ICA) | Motion Switch | MR-I-0111 | Instrument | WIL21 | Refer to Process Instrument List |  | FAT Record Submission Only | 24 | 56 | Pending Vendor Approval | IFM ELECTRONIC | Ricarte |  |  | 2027-01-19 |  |  | 2027-03-20 |  |  | 2027-05-19 |  |  | 2027-04-15 |  |  | 2027-05-15
112 | Instrument, Control & Automation (ICA) | Limit Switch | MR-I-0112 | Instrument | WIL23 | Refer to Process Instrument List |  | FAT Record Submission Only | 12 | 42 | Requisition in Progress |  | Ricarte |  |  | 2027-02-02 |  |  | 2027-04-03 |  |  | 2027-06-02 |  |  | 2027-04-15 |  |  | 2027-05-15
113 | Instrument, Control & Automation (ICA) | Truck Position Sensor | MR-I-0113 | Instrument | WIL21 | Refer to Process Instrument List |  | FAT Record Submission Only | 4 | 56 | Requisition in Progress |  | Ricarte |  |  | 2027-02-19 |  |  | 2027-04-20 |  |  | 2027-06-19 |  |  | 2027-05-16 |  |  | 2027-06-15
114 | Instrument, Control & Automation (ICA) | Vibration Transmitter | MR-I-0114 | Instrument | WIL23 | Refer to Process Instrument List |  | FAT Record Submission Only | 12 | 84 | Requisition in Progress |  | Ricarte |  |  | 2026-12-22 |  |  | 2027-02-20 |  |  | 2027-04-21 |  |  | 2027-04-15 |  |  | 2027-05-15
116 | Instrument, Control & Automation (ICA) | Solenoid Valve | MR-I-0116 | Valve |  | Refer to Process Instrument List |  | FAT Record Submission Only |  | 56 | Requisition in Progress |  | Ricarte |  |  | 2026-11-19 |  |  | 2027-01-18 |  |  | 2027-03-19 |  |  | 2027-02-13 |  |  | 2027-03-15
117 | Instrument, Control & Automation (ICA) | Surge Protection Device | MR-I-0117 | Instrument |  | Refer to Process Instrument List | for outdoor. To confirm requirements for spare I/Os. | FAT Record Submission Only |  | 36 | Requisition in Progress |  | Ricarte |  |  | 2026-12-09 |  |  | 2027-02-07 |  |  | 2027-04-08 |  |  | 2027-02-13 |  |  | 2027-03-15
118 | Instrument, Control & Automation (ICA) | ICA Nameplate | MR-I-0118 | EICA Bulk |  | Refer to Process Instrument List |  | FAT Record Submission Only |  | 30 | Not Start |  | Ricarte |  |  | 2027-01-14 |  |  | 2027-03-15 |  |  | 2027-05-14 |  |  | 2027-04-15 |  |  | 2027-05-15
119 | Instrument, Control & Automation (ICA) | EICA Labelling | MR-I-0119 | EICA Bulk |  | Refer to EICA cable tray layout |  | FAT Record Submission Only |  | 30 | Not Start |  | Ricarte |  |  | 2027-01-14 |  |  | 2027-03-15 |  |  | 2027-05-14 |  |  | 2027-04-15 |  |  | 2027-05-15
120 | Instrument, Control & Automation (ICA) | Instrument Tubing System | MR-I-0120 | EICA Bulk |  | Refer to ICA tubing system MTO |  | FAT Record Submission Only |  | 60 | Not Start |  | Ricarte |  |  | 2026-12-16 |  |  | 2027-02-14 |  |  | 2027-04-15 |  |  | 2027-03-16 |  |  | 2027-04-15
121 | Instrument, Control & Automation (ICA) | Instrument Stanchion Support | MR-I-0121 | EICA Bulk |  | Refer to support list |  | FAT Record Submission Only |  | 60 | Not Start |  | Ricarte |  |  | 2026-11-15 |  |  | 2027-01-14 |  |  | 2027-03-15 |  |  | 2027-02-13 |  |  | 2027-03-15
122 | Instrument, Control & Automation (ICA) | EICA Unistrut Support | MR-I-0122 | EICA Bulk |  | Refer to support list |  | FAT Record Submission Only |  | 30 | Not Start |  | Ricarte |  |  | 2026-10-18 |  |  | 2026-12-17 |  |  | 2027-02-15 |  |  | 2027-01-16 |  |  | 2027-02-15
123 | Building Services | Fire Protection System | MR-B-0123 | Building Service Work Package |  |  |  | FAT Record Submission Only |  | 60 | Requisition in Progress |  | Fadil |  |  | 2026-12-16 |  |  | 2027-02-14 |  |  | 2027-04-15 |  |  | 2027-03-16 |  |  | 2027-04-15
124 | Building Services | ACMV System | MR-B-0124 | Building Service Work Package |  |  |  | FAT Record Submission Only |  | 60 | Requisition in Progress |  | Fadil |  |  | 2026-12-16 |  |  | 2027-02-14 |  |  | 2027-04-15 |  |  | 2027-03-16 |  |  | 2027-04-15
125 | Building Services | BMS | MR-B-0125 | Building Service Work Package |  |  |  | FAT Record Submission Only |  | 60 | Requisition in Progress |  | Fadil |  |  | 2027-01-15 |  |  | 2027-03-16 |  |  | 2027-05-15 |  |  | 2027-04-15 |  |  | 2027-05-15
126 | Building Services | Air Damper | MR-B-0126 | Building Service Work Package |  |  |  | FAT Record Submission Only |  | 30 | Not Start |  | Fadil |  |  | 2026-12-16 |  |  | 2027-02-14 |  |  | 2027-04-15 |  |  | 2027-03-16 |  |  | 2027-04-15
127 | Building Services | Fire Seal | MR-B-0127 | Building Service Work Package |  |  |  | FAT Record Submission Only |  | 30 | Not Start |  | Fadil |  |  | 2027-04-17 |  |  | 2027-06-16 |  |  | 2027-08-15 |  |  | 2027-07-16 |  |  | 2027-08-15
5 | Design Management | BIM Consultant | MR-D-0005 | Design Consultancy Service | All |  | [2026/10/1] PO#22007 | Not Applicable |  | 30 | PO Issued, Prepare Vendor Data Submission | Southwest Municipal Engg | Lin Ting |  |  | 2026-03-16 |  |  | 2026-05-15 |  | 2026-07-01 | [6 empty] | 2026-06-15
6 | Design Management | Electrical Consultant | MR-D-0006 | Design Consultancy Service | All |  | [2026/10/1] PO# 21704 | Not Applicable |  | 30 | PO Issued, Prepare Vendor Data Submission | RES | Ammar |  |  | 2026-02-14 |  |  | 2026-04-15 |  | 2026-04-13 | [6 empty] | 2026-05-15
15 | Mechanical | High Speed Turbo Blower | MR-M-0015 | Equipment Package | WIL21 | WIL21 - ILM2 Grit Air Blower (WIL21-024-B-0101/0201/0301) |  | FAT Record Submission Only | 3 | 280 | Requisition in Progress |  | Wang Yiqian |  |  | 2026-06-09 |  |  | 2026-08-08 | 2026-11-15 |  |  |  |  | 2027-04-15 |  |  | 2027-05-15
16 | Mechanical | Integrally Geared (Single-Stage Centrifugal) Blower | MR-M-0016 | Equipment Package | WIL23 WIL23 | WIL23 - ILM2 Bioreactor Process Aeration Blowers (WIL23-043-B-0101~0801) WIL23 - ILM2 Membrane Air Scour Blowers (WIL23-043-B-1001~1301) |  | FAT Record Submission Only | 12 | 168 | Requisition in Progress |  | Wang Yiqian |  |  | 2026-07-30 |  |  | 2026-09-28 | 2026-11-15 |  | 2026-08-29 |  |  | 2027-02-13 |  |  | 2027-03-15
17 | Mechanical | Compressed Air System | MR-M-0017 | Equipment Package | WIL23 WIL23 WIL23 | WIL23 - Air Compressor (TBC) WIL23 - Air Dryer (TBC) WIL23 - Air Receiver Tank (TBC) |  | FAT Record Submission Only | 6 | 168 | Requisition in Progress |  | Wu Hongqing |  |  | 2026-10-01 |  |  | 2026-11-30 |  |  | 2026-10-31 |  |  | 2027-04-17 |  |  | 2027-05-17
18 | Mechanical | PST System | MR-M-0018 | Equipment Package | WIL21 WIL21 WIL23 WIL22 WIL22 | WIL21 - ILM2 Intermediate Screens Dewatering Presses (WIL21-021-SW-0301~0501) WIL21 - ILM2 Fine Screens Dewatering Presses (WIL21-022-SW-0301/0401/0501) WIL23 - ILM2 MBR Fine Screens Dewatering Presses (WIL23-041-SCN-0101/0201) WIL22 - ILM2 PST 1/2/3 Lamella Plates (WIL22-034-LPT-0101/0201/0301) WIL22 - ILM2 PST 1/2/3PST Scraper (WIL22-034-SCP-0101/0201/0301) | Include - Dewatering Press and Lamella Plates - Surface Scum Scraper - Skimmer and Bottom Sludge Scrapers | FAT Record Submission Only | 14 | 168 | Pending Vendor Approval | Nova | Fadhli |  |  | 2027-01-30 |  |  | 2027-03-31 |  |  | 2027-03-01 |  |  | 2027-08-16 |  |  | 2027-09-15
19 | Process | Diffusers | MR-PR-0019 | Misc. Mech Item | WIL21 WIL21 WIL21 WIL23 | WIL21 - ILM2 Grit Tanks Inlet Channel Coarse Bubble Diffuser (WIL21-024-CBD-0201/0301/0302/0501) WIL21 - ILM2 Grit Tanks Outlet Channel Coarse Bubble Diffuser (WIL21-024-CBD-0303/0403/0503/0603) WIL21 - ILM2 Grit Tank 3/4/5 Coarse Bubble Diffusers (WIL21-024-CBD-0302/0402/0502) WIL23 - ILM2 Bioreactor 1~6 Aerobic Zone Fine Bubble Diffuser (NA) | [2026/10/1] PO# 22074 | FAT Record Submission Only | 23 | 140 | PO Issued, Prepare Vendor Data Submission | EDI | Wu Hongqing |  |  | 2026-06-29 |  |  | 2026-08-28 |  | 2026-08-18 | 2026-07-29 |  |  | 2026-12-16 |  |  | 2027-01-15
21 | Mechanical | Lifting Equipment | MR-M-0021 | Equipment Package | WIL21 WIL21 WIL21 WIL21 WIL21 WIL21 WIL21 WIL21 WIL21 WIL21 WIL23 WIL23 WIL23 WIL23 WIL23 WIL22 WIL22 WIL22 WIL23 WIL23 WIL23 WIL23 WIL23 WIL23 | WIL21 - ILM2 Intermediate Screens Crane (WIL21-021-CRN-0001) WIL21 - ILM2 Influent Flowmeter Chamber Sump Pump Crane (WIL21-021-CRN-0201) WIL21 - ILM2 Influent Flowmeter Chamber Crane (WIL21-021-CRN-0101) WIL21 - ILM2 Fine Screens Crane (WIL21-022-CRN-0001) WIL21 - ILM2 Grease & Scum Wet Wells Crane (WIL21-024-CRN-0001) WIL21 - ILM2 Grit Tanks Crane (WIL21-024-CRN-0002) WIL21 - ILM2 Grit Pumps Crane (WIL21-024-CRN-0003) WIL21 - ILM2 Grit Tank Inlet Crane 3 (WIL21-024-CRN-0301) WIL21 - ILM2 Grit Tank Inlet Crane 4 (WIL21-024-CRN-0301) WIL21 - ILM2 Grit Tank Inlet Crane 5 (WIL21-024-CRN-0501) WIL23 - ILM2 MBR Fine Screens Crane (WIL23-041-CRN-0001) WIL23 - ILM2 DEOX/RAS Tank 1 Crane (WIL23-047-CRN-0001) WIL23 - ILM2 DEOX/RAS Tank 2 Crane (WIL23-047-CRN-0002) WIL23 - ILM2 Membrane Tanks Crane (WIL23-044-CRN-0001) WIL23 - ILM2 MBR Filtrate Tanks Crane (WIL23-051-CRN-0001) WIL22 - ILM2 PST Lifting Davit Sockets (N.A.) WIL22 - ILM2 Primary Scum Wet Wells Crane (WIL22-026-CRN-0001) WIL22 - ILM2 PST Crane (N.A.) WIL23 - ILM2 Process Air Blowers Crane (WIL23-043-CRN-0001) WIL23 - ILM2 Membrane Air Blowers Crane (WIL23-043-CRN-0002) WIL23 - ILM2 Bioreactor Mixers Mobile Lifting Equipment (N.A.) WIL23 - Mobile Crane (N.A.) WIL23 - ILM2 Bioreactor Lifting Davit Sockets (N.A.) WIL23 - ILM2 Bioreactor Area Pumps Lifting Crane (N.A.) |  | FAT Record Submission Only | 41 | 140 | Requisition in Progress |  | Fadhli |  |  | 2026-09-27 |  | 2026-06-30 | 2026-11-26 |  |  | 2026-10-27 |  |  | 2027-03-16 |  |  | 2027-04-15
22 | Mechanical | MFS Membrane | MR-M-0022 | Equipment Package | WIL23 | WIL23 - ILM2 MFS Membranes (WIL23-044-MB-(0101-0117) ~ (0901~0917)) | [2026/10/1] PO# 21899 | Witness Point | 9 | 747 | PO Issued, Prepare Vendor Data Submission | Veolia | Wu Hongqing |  |  | 2026-10-28 |  |  | 2026-12-27 |  | 2026-06-15 | 2026-11-27 |  | 2026-06-12 | 2028-06-01 |  |  | 2028-07-01
23 | Mechanical | Static Mixer | MR-M-0023 | Static Equipment | WIL23 | WIL23 - ILM2 MBR Cleaning Header Mixer 1/2/3/4 (WIL23-044-SMX-0130/0131/0530/0531) |  | FAT Record Submission Only | 4 | 210 | Requisition in Progress |  | Fadhli |  |  | 2026-07-05 |  |  | 2026-09-03 | 2026-11-15 |  | 2026-08-04 |  |  | 2027-03-02 |  |  | 2027-04-01
24 | Mechanical | Hyperbolic Mixers | MR-M-0024 | Rotating Equipment | WIL23 | WIL23 - ILM2 Bioreactor 1~6 Mixed Liquor Mixer 1/2 (WIL23-042-MXR-0101/0102/0201/0202/0301/0302/0401/0402/0501/0502/0601/0602) | Fix speed, top entry vertical shaft [2026/10/1] PO# 21615 | FAT Record Submission Only | 12 | 180 | PO Issued, Prepare Vendor Data Submission | INVENT UMWELT | Fadhli |  |  | 2026-10-18 |  |  | 2026-12-17 |  | 2026-04-28 | 2026-11-17 |  | 2026-07-10 | 2027-05-16 |  |  | 2027-06-15
25 | Mechanical | Surge Vessel and Accumulator | MR-M-0025 | Static Equipment | WNS03 WNS03 | WNS03 - NW HH BLADDER SURGE VESSEL (WNS03-063-PV-0101/0201/0301/0401) WNS03 - NW LH BLADDER SURGE VESSEL (WNS03-063-0601/0701) | Including portable air compressor [2026/10/1] PO# 22229 | Third Party Inspection | 6 | 168 | PO Issued, Prepare Vendor Data Submission | SYNCHONG HOE | Fadhli |  |  | 2026-07-02 |  |  | 2026-08-31 |  | 2026-09-17 | 2026-08-01 |  | 2026-09-12 | 2027-01-16 |  |  | 2027-02-15
27 | Mechanical | Centrifugal Pump | MR-M-0027 | Rotating Equipment | WIL00 WIL21 WIL21 WIL21 WIL22 WIL23 WIL23 WIL23 WIL23 WIL23 WIL23 WIL23 WIL23 WIL23 | WIL00 - ILM2 Plant Water High Pressure Pump 1/2/3 (WIL00-003-P-0201A/B/C) WIL21 - ILM2 Influent Flowmeter Chamber Drainage Sump Pump 1/2 (WIL21-021-P-0101/0102) WIL21 - ILM2 Grit Tank 3/4/5 Pump (WIL21-024-P-0301/0401/0501) WIL21 - ILM Plant Drainage PS Wet Well Compartment 2 Pump 1/2 (WIL21-008-P-0201A/B) WIL22 - ILM2 PST 1/2/3 Primary Sludge Transfer Pump 1/2 WIL23 - ILM2 Bioreactor Drainage Pump 1 (WIL23-042-P-0101) WIL23 - ILM2 WAS Wet Well 1/2 WAS Pump 1/2/3 (WIL23-048-P-0101/0201 A/B/C) WIL23 - ILM2 DEOX/RAS Tank 1/2 RAS Pump 1/2/3 (WIL23-047-P-0101/0102 A/B/C) WIL23 - ILM2 DEOX/RAS Tank Drainage Pump (WIL23-047-P-0110) WIL23 - ILM2 Membrane Cleaning Pump 1/2/5/6 (WIL23-044-P-0101/0201/0501/0601) WIL23 - ILM2 MBR Filtrate Pump 1~14 (WIL23-045-P-0101~0901, 0102/0304/0506/0708/0910Z) WIL23 - ILM2 MBR Filtrate Tank Drainage Pump 1 (WIL23-051-P-0103) WIL23 - ILM2 G2I Pump 1/2/3/4 (WIL23-051-P-0101/0201 A/B) WIL23 - ILM2 Mixed Liquor Return Pump (WIL23-044-P-0121) | Centrifugal Pump Sump Dewatering Pump Recessed Impeller Pump Submersible Screw Induced Flow Submersible Screw Induced Flow Submersible Pump Submersible Pump Submersible Pump Submersible Pump Centrifugal Pump Centrifugal Pump (Closed Impeller) Vertical Turbine Pump Submersible Pump Submersible Pump | FAT Record Submission Only | 54 | 168 | Requisition in Progress |  | Wang Yiqian |  |  | 2026-10-01 |  |  | 2026-11-30 |  |  | 2026-10-31 |  |  | 2027-04-17 |  |  | 2027-05-17
28 | Mechanical | PC Pump | MR-M-0028 | Rotating Equipment | WIL21 WIL22 WIL23 WIL23 | WIL21 - ILM2 Grit Tanks Inlet Sampling Point Pump 1 (WIL21-024-P-1010) WIL22 - ILM2 PSI Transfer Pump 1/2/3/4 (WIL22-035-P-0101/0201/0301/0401) WIL23 - Bioreactor 1/2/3/4/5/6 Sampling Pump 1/2 (WIL23-042-P-0101A/B~0601A/B) WIL23 - ILM2 MBR Filtrate Tank Membrane Filtrate Sampling Pump 1/2 (WIL23-051-P-1001/1002) | Progressive Cavity Pump | FAT Record Submission Only | 19 | 140 | Requisition in Progress |  | Wu Hongqing |  |  | 2026-08-27 |  |  | 2026-10-26 | 2026-12-15 |  | 2026-09-26 |  |  | 2027-02-13 |  |  | 2027-03-15
29 | Mechanical | Double Disc Centrifugal Pump | MR-M-0029 | Rotating Equipment | WDL21 WIL22 WIL23 | WDL21 - ILM2 Grease and Scum Wet Well 2/3 Pump 1/2 (WIL21-026-P-0201/0301 A/B) WIL22 - ILM2 Primary Scum Wet Well 1/2/3 Pump 1/2 (WIL22-026-P-0101/0201/0301 A/B) WIL23 - ILM2 Membrane Scum Wet Well 1~7 Pump 1/2 (WIL23-044-P-0110~0710 A/B) | Extended Drive Shaft Submersible Double Disc Centrifugal Pump | FAT Record Submission Only | 24 | 140 | Requisition in Progress |  | Wang Yiqian |  |  | 2026-08-27 |  |  | 2026-10-26 | 2026-12-15 |  | 2026-09-26 |  |  | 2027-02-13 |  |  | 2027-03-15
30 | Mechanical | Chemical Dosing Pump | MR-M-0030 | Rotating Equipment | WIL06 WIL06 | WIL06 - ILM2 MFS Citric Acid Dosing Pump 1/2 (WIL06-405-P-0102/0202) WIL06 - ILM2 MFS Sodium Hypochlorite Dosing Pump 1/2 (WIL06-402-P-0102/0202) | Reciprocating Diaphragm | FAT Record Submission Only | 4 | 84 | Requisition in Progress |  | Wu Hongqing |  |  | 2026-08-27 |  |  | 2026-10-26 | 2026-12-15 |  | 2026-09-26 |  |  | 2027-02-13 |  |  | 2027-03-15
31 | Mechanical | Intermediate Screen, Conveyor system, and Grit Classifier | MR-M-0031 | Equipment Package | WIL21 WIL21 WIL21 WIL21 WIL21 WIL21 WIL21 WIL21 | WIL21 - ILM2 Intermediate Screens (WIL21-021-SCN-0301~0501) WIL21 - ILM2 Intermediate Screen 3~5 Cross Conveyors (WIL21-021-CNV-0301~0501) WIL21 - ILM2 Intermediate Screen Loadout Conveyors 1/2/3/4 (WIL21-021-CNV-0102~0402) WIL21 - ILM2 Fine Screen 3~5 Cross Conveyors (WIL21-022-CNV-0301/0401/0501) WIL21 - ILM2 Fine Screen Loadout Conveyors 1/2/3/4 (WDL11-022-CNV-0102/0202/0302/0402) WIL21 - ILM2 Submerged Grit Screw Conveyor (WIL21-024-CNV-0301/0401/0501) WIL21 - ILM2 Grit Loadout Conveyors 1/2 (WIL21-025-CNV-0101/0201) WIL21 - ILM2 Grit Classifiers 1/2 (WIL21-025-GRC-0201/0301 A) | [2026/10/1] PO# 21804 | FAT Record Submission Only | 24 | 168 | PO Issued, Prepare Vendor Data Submission | WMA | Fadhli |  |  | 2026-07-26 |  |  | 2026-09-24 |  | 2026-05-21 | 2026-08-25 |  | 2026-06-28 | 2027-02-09 |  |  | 2027-03-11
32 | Mechanical | Travellng Band Screen (Fine Screen and MBR Fine Screen) | MR-M-0032 | Equipment Package | WIL21 WIL21 WIL21 WIL23 WIL23 WIL23 WIL23 | WIL21 - ILM2 Fine Screens - Dive Unit Band (WIL21-022-SCN-0301/0401/0501 A) WIL21 - ILM2 Fine Screens - Dive Unit Brush (WIL21-022-SCN-0301/0401/0501 B) WIL21 - ILM2 Fine Screens - Discharge Screw (WIL21-022-SCN-0301/0401/0501 C) WIL23 - ILM2 MBR Fine Screen - Drive Unit Band (WIL23-041-SCN-0101/0201/0301 A) WIL23 - ILM2 MBR Fine Screen - Drive Unit Brush (WIL23-041-SCN-0101/0201/0301 B) WIL23 - ILM2 MBR Fine Screen - Discharge Screw (WIL23-041-SCN-0101/0201/0301 C) WIL23 - ILM2 MBR Fine Screen Screenings Channel Launder (NA) |  | FAT Record Submission Only | 19 | 210 | Requisition in Progress |  | Fadhli |  |  | 2026-12-19 |  |  | 2027-02-17 |  |  | 2027-01-18 |  |  | 2027-08-16 |  |  | 2027-09-15
33 | Mechanical | Scum and Grease Removal System | MR-M-0033 | Equipment Package | WIL21 WIL22 | WIL21 - ILM2 Grit Tank Scum Collector (WIL21-024-SC-0301/0401/0501) WIL22 - ILM2 PST 1/2/3 Scum Collector (WIL22-034-SC-0101/0201/0301) | [2026/10/1] PO# 22052 | FAT Record Submission Only | 6 | 168 | PO Issued, Prepare Vendor Data Submission | PROBIG GmbH | Fadhli |  |  | 2026-07-26 |  |  | 2026-09-24 |  | 2026-09-23 | 2026-08-25 | 2026-11-25 |  | 2027-02-09 |  |  | 2027-03-11
34 | Mechanical | Hopper and Hopper slide gate | MR-M-0034 | Static Equipment | WIL21 WIL21 | WIL21 - ILM2 Screenings Hoppers 1/2 (WIL21-023-HO-0101/0201) WIL21 - ILM2 Grit Hoppers 1/2 (WIL21-025-HO-0101/0201) |  | FAT Record Submission Only | 4 | 150 | Requisition in Progress |  | Fadhli |  |  | 2026-09-17 |  |  | 2026-11-16 |  |  | 2026-10-17 |  |  | 2027-03-16 |  |  | 2027-04-15
35 | Mechanical | FRP Tank Cover | MR-M-0035 | Misc. Mech Item |  |  |  | FAT Record Submission Only |  | 168 | Not Start |  | Fadhli |  |  | 2026-07-26 |  |  | 2026-09-24 | 2027-01-15 |  | 2026-08-25 |  |  | 2027-02-09 |  |  | 2027-03-11
36 | Mechanical | Automatic Lubircation System (ALS) | MR-M-0036 | Equipment Package |  |  |  | FAT Record Submission Only |  | 120 | Not Start |  | Fadhli |  |  | 2026-10-31 |  |  | 2026-12-30 |  |  | 2026-11-30 |  |  | 2027-03-30 |  |  | 2027-04-29
37 | Mechanical | Penstock | MR-M-0037 | Equipment Package |  |  |  | FAT Record Submission Only |  | 180 | Not Start |  | Dilip/Siva |  |  | 2026-06-04 |  |  | 2026-08-03 | 2027-01-15 |  | 2026-07-04 |  |  | 2026-12-31 |  |  | 2027-01-30
38 | Mechanical | Spray Nozzle | MR-M-0038 | Piping SP |  |  |  | FAT Record Submission Only |  | 365 | Not Start |  | Fadhli |  |  | 2026-10-01 |  |  | 2026-11-30 |  |  | 2026-10-31 |  |  | 2027-10-31 |  |  | 2027-11-30
39 | Mechanical | Safety Shower and Eye Wash | MR-M-0039 | Piping SP |  |  |  | FAT Record Submission Only |  | 150 | Not Start |  | Fadhli |  |  | 2026-10-31 |  |  | 2026-12-30 |  |  | 2026-11-30 |  |  | 2027-04-29 |  |  | 2027-05-29
40 | Piping | Hose Point and Hose Reel | MR-PI-0040 | Piping SP |  |  |  | FAT Record Submission Only |  | 60 | Requisition in Progress |  | Fadhli |  |  | 2026-08-31 |  |  | 2026-10-30 |  |  | 2026-09-30 |  |  | 2026-11-29 |  |  | 2026-12-29
41 | Piping | Metal Knife Gate Valve (Manual and On-off) | MR-PI-0041 | Valve |  |  |  | FAT Record Submission Only |  | 150 | Requisition in Progress |  | Fadhli |  |  | 2026-10-08 |  |  | 2026-12-07 |  |  | 2026-11-07 |  |  | 2027-04-06 |  |  | 2027-05-06
42 | Piping | Metal Ball Valves (Manual and On-off) | MR-PI-0042 | Valve |  |  |  | FAT Record Submission Only |  | 150 | Requisition in Progress |  | Fadhli |  |  | 2026-10-08 |  |  | 2026-12-07 |  |  | 2026-11-07 |  |  | 2027-04-06 |  |  | 2027-05-06
43 | Piping | Metal Butterfly Valves (Manual and On-off) | MR-PI-0043 | Valve |  |  |  | FAT Record Submission Only |  | 150 | Requisition in Progress |  | Fadhli |  |  | 2026-10-08 |  |  | 2026-12-07 |  |  | 2026-11-07 |  |  | 2027-04-06 |  |  | 2027-05-06
44 | Piping | Metal Gate, Check, Globe Valves (Manual and On-off) | MR-PI-0044 | Valve |  |  |  | FAT Record Submission Only |  | 150 | Requisition in Progress |  | Fadhli |  |  | 2026-10-08 |  |  | 2026-12-07 |  |  | 2026-11-07 |  |  | 2027-04-06 |  |  | 2027-05-06
45 | Piping | Air Release Valve | MR-PI-0045 | Valve |  |  |  | FAT Record Submission Only |  | 150 | Requisition in Progress |  | Fadhli |  |  | 2026-10-08 |  |  | 2026-12-07 |  |  | 2026-11-07 |  |  | 2027-04-06 |  |  | 2027-05-06
51 | Piping | Aeration Control Valve | MR-PI-0051 | Valve |  |  |  | FAT Record Submission Only |  | 150 | Requisition in Progress |  | Wu Hongqing |  |  | 2026-10-08 |  |  | 2026-12-07 |  |  | 2026-11-07 |  |  | 2027-04-06 |  |  | 2027-05-06
65 | Electrical | Transformer | MR-E-0065 | Electrical Equipment |  |  | 22/6.6kV Distribution Transformer, 2 nos 22/0.415 Distrbution Transformer, 10 nos [2026/10/6] expecting delays to installation | FAT Record Submission Only | 12 | 330 | PO Issued, Prepare Vendor Data Submission | Teco | Ammar |  |  | 2026-02-03 |  |  | 2026-04-04 |  | 2026-09-18 | 2026-10-30 |  | 2026-08-15 | 2027-01-29 |  |  | 2027-02-28
66 | Electrical | HVSG Panel | MR-E-0066 | Electrical Equipment | WIL23 | WIL23-HVSG-0001A/B | 22kV-HVSG - 2 nos 6.6kV-HVSG - 2 nos [2026/10/5] PO# 21945 [2026/10/6] expecting delays to installation | FAT Record Submission Only | 4 | 280 | PO Issued, Prepare Vendor Data Submission | Schneider Electric | Ammar |  |  | 2026-03-12 |  |  | 2026-05-11 |  | 2026-08-31 | 2026-12-13 |  | 2026-08-15 | 2027-01-16 |  |  | 2027-02-15
67 | Electrical | LVSG, MCC including VFD, Harmonic Filter | MR-E-0067 | EICA Panels |  |  | LVSG - 10 nos MCC - 24 nos LV VFD 55kW - 10 LV VFD 75kW - 4 LV VFD 132kW - 14 LV VFD 250kW - 6 LCS - Type 1 - 78 LCS - Type 2A - 49 LCS - Type 3 - 2 LCS - Type 4 - 6 LCS - Type 9 - 28 LCS - Type 31 - 4 LCS - Type B2 - 30 LCS - Type B3 - 30 LCS - Type B4 - 2 | FAT Record Submission Only |  | 168 | PO Issued, Prepare Vendor Data Submission | Sunlight | Ammar |  |  | 2026-07-27 |  |  | 2026-09-25 |  | 2026-07-17 | 2026-08-30 |  | 2026-08-15 | 2027-02-10 |  |  | 2027-03-12
129 | Electrical | MDB | MR-E-0129 | EICA Panels |  |  | MDB- 22 nos | FAT Record Submission Only | 22 | 210 | PO Issued, Prepare Vendor Data Submission | Sunlight | Ammar |  |  | 2026-08-18 |  |  | 2026-10-17 |  | 2026-07-30 | 2026-12-16 |  |  | 2027-04-15 |  |  | 2027-05-15
68 | Electrical | LCS | MR-E-0068 | EICA Panels |  |  | LCS - Type 1 - 78 LCS - Type 2A - 49 LCS - Type 3 - 2 LCS - Type 4 - 6 LCS - Type 9 - 28 LCS - Type 31 - 4 LCS - Type B2 - 30 LCS - Type B3 - 30 LCS - Type B4 - 2 | FAT Record Submission Only | 229 | 70 | Requisition in Progress | Sunlight | Ammar |  |  | 2027-02-05 |  |  | 2027-04-06 | 2027-11-15 |  | 2026-08-30 |  | 2026-08-15 | 2027-05-16 |  |  | 2027-06-15
70 | Electrical | Emergency Generator | MR-E-0070 | Electrical Equipment |  |  |  |  | 1 | 180 | Pending PO Confirmation | Vibropower | Ammar |  |  | 2026-08-21 |  |  | 2026-10-15 |  | 2026-10-15 |  |  |  | 2027-03-14 |  |  | 2027-04-13
71 | Electrical | ESSB | MR-E-0071 | Equipment Package |  |  |  |  | 7 | 252 | PO Issued, Prepare Vendor Data Submission | Sunlight | Ammar |  |  | 2026-05-07 |  |  | 2026-07-06 | 2026-11-15 |  |  |  |  | 2027-02-13 |  |  | 2027-03-15
72 | Electrical | 6.6kV DOL STARTER | MR-E-0072 | EICA Panels |  |  | 6.6kV DOL STARTER - 750kW - 8 Nos 6.6kV DOL STARTER - 500kW - 4 Nos |  | 12 | 210 | Requisition in Progress |  | Ammar |  |  | 2026-08-18 |  |  | 2026-10-17 | 2026-11-15 |  |  |  |  | 2027-04-15 |  |  | 2027-05-15
75 | Instrument, Control & Automation (ICA) | PLC Panel | MR-I-0075 | EICA Panels | WIL06 WIL21 WIL22 WIL23 WNS03 | Refer to panel master list and panel GA | To confirm PLC panel list. Grit Air Blower PLC Bio Aeration Blower PLC Membrane Blower PLC | FAT Record Submission Only | 13 | 210 | Not Start |  | Ricarte |  |  | 2026-09-04 |  |  | 2026-11-03 |  |  | 2026-12-03 |  |  | 2027-05-02 |  |  | 2027-06-01
76 | Instrument, Control & Automation (ICA) | RIO Panel Component | MR-I-0076 | EICA Panels |  | Refer to panel master list and panel GA | To confirm RIO panel list Process: 64 nos. (vs 58 os.) Non-process: 32 Nos. | FAT Record Submission Only | 96 | 140 | Not Start |  | Ricarte |  |  | 2026-12-27 |  |  | 2027-02-28 |  |  | 2026-09-30 |  |  | 2027-06-15 |  |  | 2027-07-15
77 | Instrument, Control & Automation (ICA) | RIO Panel Rack and Component Installation | MR-I-0077 | EICA Panels |  | Refer to panel master list and panel GA |  | FAT Record Submission Only | 96 | 168 | Not Start |  | Ricarte |  |  | 2027-01-30 |  |  | 2027-03-31 |  |  | 2026-09-30 |  |  | 2027-08-16 |  |  | 2027-09-15
115 | Instrument, Control & Automation (ICA) | Local Display | MR-I-0115 | Instrument | WIL21 WIL23 | Refer to Process Instrument List |  | FAT Record Submission Only | 44 | 70 | Pending Vendor Approval | ENDRESS + HAUSER | Ricarte |  |  | 2026-10-21 |  |  | 2026-12-20 |  |  | 2026-07-30 |  | 2026-08-13 | 2027-01-29 |  |  | 2027-02-28
Formulas:
PO Plan Date (D1) = [MR Plan Date (C1)]+60
VD Approval Plan Date (E1) = [PO Plan Date (D1)]+60
VD Approval Plan Date (E1) = [PO Plan Date (D1)]-30
FAT Plan Date (F1) = [ROS Plan Date (G1)]-30
ROS Plan Date (G1) = [Estimate Lead Time (Days) (A11)]+[PO Plan Date (D1)]
MR Plan Date (C1) = [PO Plan Date (D1)]-60
Note on A1: if a package is deleted, do not reuse the running numnber for another pakcage.
Note on T1: Estimate 60 days for MRQ, TBE, CBE, VI approval, and PO issuance.
Note on W1: Estimate 60 days from PO issuance.